## Base Year 2018-19-As Accounts
1.1D ABSTRACT OF INVESTMENT PLAN ( FY 2018-19 ) OF CE/CONSTRUCTION
|  |  | Base Year 2018-19 | [24 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | [6 empty] | SOURCE OF FINANCING | [6 empty] | Expenditure incurred in FY 2018-19 |  |  |  | Expenditure upto March 2018 |  |  |  |  | Cumulative Expenditure |  |  |  | Remarks
[14 empty] | Internal Accrual Component of capex in year |  | Debt component of capex in year | [9 empty] | Annual
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  | Equity Component of capex in year | Loan Amount (Crores) | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. crores) | Proposed IDC | Proposed other expence | % Capatalisation | OPENING BALANCE | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year in Crores | IDC incurred | Other expence incurred | % Capatalisation
1 | TOO (CE-Construction) MS NO.198, Dt:04.12.2004 | S-04-01 | APT/TS/220/F-INVT-56/2006 | erection of 220/132/33 kV substation at Shadnagar along with connected EHT lines | System Improvement | 01.04.2006 | 31.03.2019 | 25.0965 | 0.7528 | 2.5096 | 1.5054 | 2.6978 | 32.5621 |  |  | 0 |  |  |  |  | 0.18 |  |  |  | 3.75 |  |  |  |  | 3.93
2 | T.O.O (CE-Construction) MS. No. 226 Dated: 28.01.2005 SI06DISINC | S-05-01 | APT/TS/132/F-INVT-53/2005 | 132/33 KV SS Ieeza in Mahaboobnagra District with connected lines | System Improvement | 28.08.2005 | 31.03.2019 | 13.6834 | 0.14377 | 1.44 | - | 0.57277 | 15.8399 |  |  | 9.9778 |  |  |  | REC | 0 |  |  |  | 0.15 |  |  |  |  | 0.15
3 | T.O.O (CE-Construction) Ms. No. 84 Dated: 14.06.2006. | S-06-01 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132kV DC/SC line withPanther conductor from 132/33 kV Aswaraopet SS to Proposed 132/33 kV Gangaram substation (Radial). | System Improvement | 25.04.2008 | 31.03.2019 | 7.36 | 0.0055 | 0.736 | 0.0012 | 0.0224 | 8.1251 |  |  | 16.19 |  |  |  | KVB | 0 |  |  |  | 0.12 |  |  |  |  | 0.12
4 | T.O.O (ED-Construction) MS. NO.06 Dated: 04 .04.2006 | S-06-05 S-06-06 S-06-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132/33 kV SS at Disincherla in Nalgonda district along with connected 132 kV line (TOO No.06, dt.04.04.2006) | System Improvement | 04.08.2006 | 31.03.2019 | 8.4101 | 0.17656 | 0.93 | 0.0012 | 0.71213 | 10.23 |  |  | 9.3 |  |  |  | KVB | 0 |  |  |  | 0.04 |  |  |  |  | 0.04
5 | (TOO 350, dt. 27.11.2010) PE10MAGA27 | S-07-02 | APT/TS/132kv -Makthal-Gadwal LILO-Invst-2/2012 | Erection of 132 KV LILO to Jurala from e | System Improvement | Dec'2016 | 31.03.2019 | 7.2286 | 0.07849 | 0.761 | 0.0074 | 0.29547 | 8.371 |  |  | 0 |  |  |  | Bankof BarodaS | 0 |  |  |  | 1.64 |  |  |  |  | 1.64
6 | TOO (CE-construction) MS.NO.245 dt:29-09-2011 | S-07-03 |  | Erragadda and O.U GIS &Cables scheme | System Improvement | 27.12.2011 | 31.03.2019 | 437.7 | 13.131 | 43.77 | 26.262 | 47.0527 | 567.9157 |  |  | 415 |  |  |  | PFC | 0.71 |  |  |  | 0 |  |  |  |  | 0.71
7 | T.O.O (CE-Construction-1) Ms. No. 07 Dated: 18.12.2013 SI10NIM132 | S-07-04 |  | TWIN CITIES TRANSMISSION SYSTEM & 132 kV SS NIMS & connected lines & erection of 220/132 kV substations at Gunrock, Imlibun (GIS) & Hayatnagar and 132 kV GIS Substations at Moosarambagh, Miralam Filter bed, Patigadda, Balkampet and OsmanIa University along with connected Under Ground XLPE Cables – Under Modernization and Strengthening of Hyderabad Metropolitan area | System Improvement | 01.08.2014 | 31.03.2019 | 76.8437 | 2.3009 | 8.825 | 0.6132 | 8.4922 | 97.075 |  |  | 85.36 |  |  |  | JICA | 15.32 |  |  |  | 69.14 |  |  |  |  | 84.46
8 | TOO (CE-Construction) MS NO.379, Dt:17.01.2012 |  |  |  |  | 01.08.2014 | 31.03.2019 | 11.75 | 0.3525 | 1.175 | 0.705 | 1.2631 | 15.2456 |  |  | 11.4 |  |  |  | PFC
9 | T.O.O (CE-Construction) Ms. No. 184 Dated: 04.12.2007 | S-07-05 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV substation at Kanagal in Nalgonda district along with connected 132 kV & 33 k V lines | System Improvement | 01.11.2009 | 31.03.2019 | 12.0099 | 0.20028 | 1.275 | 0.0012 | 0.73889 | 14.2253 |  |  | 12.75 |  |  |  | Rajasthan Bank | 0.09 |  |  |  | 0.04 |  |  |  |  | 0.13
10 | T.O.O (CE-Construction) Ms. No.249 Dated: 13.02.2008 SI08GNTP13 | S-08-01 | APT/TS/132kV SS-Guntipally/F-INVST-17/2010 | 132 kV SS Guntipally & Connected Lines | System Improvement | 30.09.2010 | 31.03.2019 | 12.5809 | 0.21706 | 1.36 | 0.0012 | 0.80083 | 14.96 |  |  | 13.6 |  |  |  | Panjab & Sindh | 0 |  |  |  | 0.02 |  |  |  |  | 0.02
11 | T.O.O (CE-Construction) Ms. No.261 Dated: 09 .02.2009 | S-08-02 | CRN.No./TST/TS/132 KV Amarachinta//F.Invst./ App./08/2011 | 132/33 kV substation at Amarchinta in Mahaboobnagar district | System Improvement | 13.12.2010 | 31.03.2019 | 12.9583 | 0.38875 | 1.2958 | 0.7775 | 1.393 | 16.8134 |  |  | 15.55 |  |  |  | Uco Bank | 0.43 |  |  |  | 0 |  |  |  |  | 0.43
12 | T.O.O (CE-Construction) Ms. No. 54 Dated: 13.06.2008 | S-08-16 S-08-04 | CRN.No.TST/TS/132 KVF.INVT-85/2007, dt:10.09.2007 | 132/33 kV sub-station at Midgil in Mahaboobnagar district along with connected 132 kV & 33 kV lines | System Improvement | 26.10.2009 | 31.03.2019 | 11.475 | 0.34425 | 1.1475 | 0.6885 | 1.2336 | 14.8888 |  |  | 13 |  |  |  | KVB | 0 |  |  |  | 0.02 |  |  |  |  | 0.02
13 | T.O.O. (CE-Transmission) Ms. No. 140 Dated. 13.10.2016 (Revised) | S-08-08 | CRN.No./TST/TS/220-132 KV GIS-Hyd/F.Invst./99/2019, Dt:20.02.2009 | 132/33 KV Narayanaguda GIS Sub-station | System Improvement | 31.05.2013 | 31.03.2019 | 130.1917 | 3.9057 | 13.0192 | 7.8115 | 13.9956 | 168.9237 |  |  | 31.19 |  |  |  | PFC | 0.57 |  |  |  | 0 |  |  |  |  | 0.57
14 | T.O.O (CE-Transmission) Ms. No. 59 Dated:19.04.2016 | S-08-11 | CRN.No.TST/TS/132/33 KVSS Mamidpally,R.R.Dist./Invest. Appl(revised)/No. 6/16-2016-17 | 132/33KV Substation, Mamidipally in Ranga Reddy District | System Improvement | 31.12.2008 | 31.03.2019 | 18.2667 | 0.548 | 1.8267 | 1.096 | 1.9637 | 23.701 |  |  | 8.85 |  |  |  | Syndicate bank | 0.2 |  |  |  | 0 |  |  |  |  | 0.2
15 | T.O.O (CE-Construction) Ms. No. 231 Dated: 28.01.2008 | S-08-12 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV substation at Mulkanoor in Karimnagar district along with connected 132 kV & 33 k V lines | System Improvement | 01.04.2011 | 31.03.2019 | 11.481 | 0.217 | 1.25 | 0.0012 | 0.8008 | 13.75 |  |  | 12.5 |  |  |  | Punjab & Sindh Bank | 0.01 |  |  |  | 0.2 |  |  |  |  | 0.21
16 | T.O.O (CE-Transmission) Ms. No. 197 Dated: 17.10.2015 | S-09-03 | (CRN) : APT / TS / 132 / 33 kV / F-INVT-37. | 132 KV DC/SC line from 220 KV SS Nirmal to Kanapur (erection of 132/33 kV Substation at Khanapur in Adilabad ) | System Improvement | 30.12.2015 | 31.03.2019 | 12.3857 | 0.37157 | 1.2386 | 0.74314 | 1.3315 | 16.0704 |  |  | 17.62 |  |  |  | UCO bank | 0 |  |  |  | 2.57 |  |  |  |  | 2.57
17 | T.O.O (CE-Construction) Ms. No. 267 Dated: 6.10.2010 | S-10-02 | CRN.No.APT/TS/132 KVSS/ Asifabad/Invest.24/12 | 132/33 kV Substation at Asifabad in Adilabad district along with connected 132 kV & 33 kV lines | System Improvement | 29.11.2012 | 31.03.2019 | 16.7833 | 0.5035 | 1.6783 | 1.007 | 1.8042 | 21.7763 |  |  | 18.0042 |  |  |  | REC | 0.02 |  |  |  | 0 |  |  |  |  | 0.02
18 | T.O.O (CE-Construction) Ms. No. 257 Dated: 01.10.2010 | S-10-03 | CRN.No.TST/TS/132 KV SS-UtnoorF.INVT-25/2011 | 132/33 kV Substation at Utnoor in Adilabad district along with connected 132 kV & 33 kV lines | System Improvement | 23.01.2012 | 31.03.2019 | 24.5917 | 0.73775 | 2.4592 | 1.4755 | 2.6436 | 31.9077 |  |  | 26.56 |  |  |  | PFC | 0.24 |  |  |  | 0 |  |  |  |  | 0.24
19 | T.O.O (CE-Construction) Ms. No. 99 Dated: 18.06.2010 | S-10-06 | CRN.No.TST/TS/132 KV SS Borabatla/F.INVT-24/2011, dt:21.03.2011 | 132/33 kV Substation at Borapatla in Medak district along with connecting 132 kV and 33 kV lines | System Improvement | 20.08.2011 | 31.03.2019 | 12.8306 | 0.38492 | 1.2831 | 0.76984 | 1.3793 | 16.6477 |  |  | 36.75 |  |  |  | NABARD | 0.12 |  |  |  | 0 |  |  |  |  | 0.12
20 | T.O.O (CE-Construction-I) Ms. No. 365 Dated: 03.12.2010 SI10KESHAM | S-10-11 | APT/TS/132kV SS-Keshampet/F-INVST-40/2013 | 132 kV SS Alwal (Keshampet) & connected lines | System Improvement | 19.04.2014 | 31.03.2019 | 17.3883 | 0.23319 | 1.849 | 0.0012 | 0.86727 | 20.339 |  |  | 16.3032 |  |  |  | REC | 0.07 |  |  |  | 0.38 |  |  |  |  | 0.45
21 | T.O.O (CE-Trans) Ms. No. 27 Dated: 17.02.2016 | S-10-13 | APT/TS/132kv SS- LGM Peta/F-INVST-17/2012 (Revised approval awaited) | 132KV SS LGM Pet & connected lines | System Improvement | 16.09.2011 (SS) 02.09.2011 (Line) | 31.03.2019 | 34.56 | 0.3475 | 3.5508 | 0.0704 | 0.531 | 39.0597 |  |  | 14.79 |  |  |  | Uco Bank | 0.01 |  |  |  | 0 |  |  |  |  | 0.01
22 | T.O.O (CE-Construction-I) Ms.No.18 Dated: 15.04.2014 SI10MANTNI | S-10-14 | APT/TS/220/132 kV - Manthani/ F-INVST - 01/2011 | 220 kV SS Manthani & connected lines | System Improvement | 07.12.2014 | 31.03.2019 | 52.1023 | 0.65951 | 5.521 | 0.008 | 2.4402 | 60.731 |  |  | 49.66 |  |  |  | Uco Bank | 0 |  |  |  | 0.03 |  |  |  |  | 0.03
23 | T.O.O (CE-Construction) Ms. No. 262 Dated: 04.10.2010 | S-10-16 | CRN.No.TST/TS/132 KV SS Narmetta/F.INVT-36/2013, dt:07.11.2012 | 132/33 kV Substation at Narmetta in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 07.08.2014 | 31.03.2019 | 15.5667 | 0.467 | 1.5567 | 0.934 | 1.6734 | 20.1977 |  |  | 15.9792 |  |  |  | REC | 0.36 |  |  |  | 0 |  |  |  |  | 0.36
24 | T.O.O (CE-Construction) MS. No.319 Dated: 06.11.2010 | S-10-20 | CRN.No.TST/TS/220 KV Sw.Stn /F.INVT-2/2013, dt:02.06.2012 | 220 switching station at Thimmajipet in Mahabubnagar district along with 220 kV LILO/DC lines | System Improvement | 25.08.2011 | 31.03.2019 | 62.3 | 1.869 | 6.23 | 3.738 | 6.6973 | 80.8342 |  |  | 70 |  |  |  | PFC | 1.69 |  |  |  | 0 |  |  |  |  | 1.69
25 | TOO (CE-Construction-I) MS NO.107, Dt:23.06.2010 | S-10-22 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV features at 132 kV Switching Station Vikarabad RTSS in Ranga Reddy district - | System Improvement | 22.09.2015 | 31.03.2019 | 4.033 | 0.0587 | 0.447 | - | 0.37828 | 4.917 |  |  | 4.47 |  |  |  | Uco Bank | 0.01 |  |  |  | 0.35 |  |  |  |  | 0.36
26 | T.O.O (CE-Construction) MS. No.319 Dated: 06.11.2010 | S-10-26 | CRN APT/TS/220/ SW-Stn/F-Invest.02/2013 | erection of 220 switching station at Thimmajipet in Mahabubnagar district along with 220 kV LILO/DC lines | System Improvement | 25.08.2011 | 31.03.2019 | 72.4628 | 0.4897 | 7.4012 | - | 1.8075 | 82.1612 |  |  | 70 |  |  |  | PFC | 0.24 |  |  |  | 0.06 |  |  |  |  | 0.3
27 | T.O.O (CE-Construction-I) MS. No. 169 Dated: 23.07.2011 | S-10-30 |  | 132 kV DC line from 220 kV Bhongir SS to 132 kV Bibinagar substation | System Improvement | 01.04.2012 | 31.03.2019 | 33.825 | 1.0148 | 3.3825 | 2.0295 | 3.6362 | 43.8879 |  |  | 0 |  |  |  | Tstransco | 0 |  |  |  | 0.01 |  |  |  |  | 0.01
29 | T.O.O (CE-Construction-I) Ms. No. 504 Dated: 15.03.2011 | S-11-01 | CRN APT/TS/132 KV SS Gudur/F-Invest.13/2014 | 132/33 kV Substation at Gudur in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 16.06.2015 | 31.03.2019 | 11.075 | 0.33225 | 1.1075 | 0.6645 | 1.1906 | 14.3698 |  |  | 12.35 |  |  |  | PFC | 0.34 |  |  |  | 0 |  |  |  |  | 0.34
30 | TOO (CE-Construction-I) MS NO.422, Dt:02.02.2012 | S-11-02 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Substation at Kosgi in Mahaboobnagar district along with connected 132 kV & 33 kV lines | System Improvement | 02.05.2013 | 31.03.2019 | 11.0501 | 0.24692 | 0 | 0.0954 | 0.91759 | 12.31 |  |  | 13.743 |  |  |  | REC | 0.15 |  |  |  | 0 |  |  |  |  | 0.15
31 | T.O.O (CE-Construction-I) MS. No. 447 Dated: 21.01.2011 | S-11-06 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 2 nd Circuit from 132 kV Shaligouraram SS to Aitipamula SS and erection of 132 kV Bays at 132 kV SS Shaligouraram and Aitipamula SS | System Improvement | 01.04.2016 | 31.03.2019 | 3.05 | 0.0915 | 0.305 | 0.183 | 0.6024 | 4.2319 |  |  | 3.66 |  |  |  | OBC | 0.42 |  |  |  | 0.04 |  |  |  |  | 0.46
32 | T.O.O (CE-Construction-I) Ms. No. 34 Dated: 27.04.2011 SI11ALWALP | S-11-07 | APT/TS/132kV SS-Alwalpad/F-INVST-41/2013 | 132 kV SS Ganganpalli (Alwalpadu) & connected lines | System Improvement | 26.10.2015 | 31.03.2019 | 13.5862 | 0.24382 | 1.47 | 0.0012 | 0.8688 | 16.17 |  |  | 12.95 |  |  |  | PFC | 3.99 |  |  |  | 10.97 |  |  |  |  | 14.96
33 | T.O.O (CE-Construction-I) Ms. No. 146 Dated: 08.07.2011 | S-11-10 | CRN APT/TS/132 KV SS Dasnagar/F-Invest.11/2013 | 132/33 kV Substation at Dasnagar in Nizamabad district along with connected 132 kV & 33 kV lines | System Improvement | 01.04.2014 | 31.03.2019 | 13.05 | 0.3915 | 1.305 | 0.783 | 1.4029 | 16.9324 |  |  | 15.21 |  |  |  | South Indian Bank | 0.64 |  |  |  | 0 |  |  |  |  | 0.64
34 | T.O.O (CE-Construction-I) Ms. No. 25 Dated: 16 .04.2011 | S-11-12 | CRN APT/TS/132 KV SS Dornakal/F-Invest.11/2014 | 132/33 kV Substation at Dornakal in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 16.06.2015 | 31.03.2019 | 14.4333 | 0.433 | 1.4433 | 0.866 | 1.5516 | 18.7273 |  |  | 14.427 |  |  |  | REC | 0.22 |  |  |  | 0 |  |  |  |  | 0.22
35 | T.O.O (CE-Construction) Ms. No.3 Dated: 27.06.2014 SI11KAMANP | S-11-18 | APT/TS/132 kV SS -Kamanpur/ F-INVST -19/2013 | 132kv SS Kamanpur & connected lines | System Improvement | 16.07.2014 | 31.03.2019 | 20.952 | 0.60551 | 2.232 | - | 0.76253 | 24.552 |  |  | 15.5276 |  |  |  | PFC | 0 |  |  |  | 12.43 |  |  |  |  | 12.43
36 | T.O.O (CE-Construction-I) Ms. No. 297 Dated: 21.11.2011 SI11KATHLA | S-11-19 | APT/TS/132kV SS- Kathlapur/ F-INVST-09/2014 | 132kV SS Kathlapur & connected lines | System Improvement | 10.12.2015 | 31.03.2019 | 13.1651 | 0.2088 | 1.415 | 0.0012 | 0.77489 | 15.565 |  |  | 14.15 |  |  |  | TMB | 0.28 |  |  |  | 0.29 |  |  |  |  | 0.57
37 | T.O.O (CE-Construction-I) Ms. No.35 Dated: 27.04.2011 SI11MADUGU | S-11-22 | APT/TS/132 kV SS -Madugula/ F-INVST -16/2013 | 132 kV SS Madugula & connected lines | System Improvement | 21.12.2015 | 31.03.2019 | 20.7623 | 0.28152 | 2.209 | 0.0016 | 1.0446 | 24.299 |  |  | 19.05 |  |  |  | PFC | 1.02 |  |  |  | 0 |  |  |  |  | 1.02
38 | T.O.O (CE-Construction-I) MS. No. 251 Dated: 10.10.2011 | S-11-43 S-11-21 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132 kV DC/SC line from 132 /33 kV Dharmapuri SS to 132/33 kV Luxxettipet SS and 132 kV bays at 132 /33kV Dharmapuri SS and 132/33 kV Luxxettipet SS | System Improvement | 16.12.2014 | 31.03.2019 | 9.0916 | 0.2727 | 0.9091 | 0.9091 | 0.9773 | 12.1598 |  |  | 10.19 |  |  |  | PFC | 0.41 |  |  |  | 0.04 |  |  |  |  | 0.45
39 | T.O.O (CE-Construction-I) Ms. No. 10 Dated: 6.04.2011 | S-11-24 | CRN APT/TS/132 KVSS Mogiligiddar/F-Invest.09/2013 | 132/33 kV Substation at Mogiligidda in Mahaboobnagar district along with connected 132 kV & 33 kV lines | System Improvement | 07.08.2014 | 31.03.2019 | 14.0917 | 0.42275 | 1.4092 | 0.8455 | 1.5149 | 18.2839 |  |  | 13.14 |  |  |  | REC | 0.17 |  |  |  | 0 |  |  |  |  | 0.17
40 | T.O.O (CE-Construction-I) Ms. No. 184 Dated: 11.08.2011 SI11MUNUGO | S-11-25 S-11-26 | APT/TS/132kV SS-Munugodu/F-INVST-08/2014 | 132kV SS Munugodu & connected lines | System Improvement | 13.06.2016 | 31.03.2019 | 17.3109 | 0.2455 | 1.847 | 0.0016 | 0.912 | 20.317 |  |  | 16.137 |  |  |  | REC | 0.09 |  |  |  | 1.11 |  |  |  |  | 1.2
41 | T.O.O (CE-Construction-I) Ms. No.8 Dated: 6.04.2011 | S-11-27 | CRN.No.TST/TS/132 KVSS/Nellikoduru/F.Invest. 07/2014 | 132/33 kV Substation at Nellikuduru in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 21.07.2016 | 31.03.2019 | 17.675 | 0.53025 | 1.7675 | 1.0605 | 1.9001 | 22.9333 |  |  | 17.847 |  |  |  | REC | 0.29 |  |  |  | 0 |  |  |  |  | 0.29
42 | TOO (CE-Construction-I) MS NO.180, Dt:09.08.2011 | S-11-30 | APT/TS/220/132 kV SS -Parigi/F-INVST - 1/2013 | erection of 220/132 kV substation at Parigi in Ranga Reddy district | System Improvement | 19.10.2013 | 31.03.2019 | 57.5115 | 0.6051 | 6.035 | - | 2.2334 | 66.385 |  |  | 54.3164 |  |  |  | REC | 0.91 |  |  |  | 0.06 |  |  |  |  | 0.97
43 | T.O.O (CE-Transmission) Ms. No. 78 Dated: 14.06.2016. (Revised) | S-11-37 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Shad Nagar (V) Hamlet of Wattipally in Medak District | System Improvement | 09.09.2015 | 31.03.2019 | 15.8917 | 0.47675 | 1.5892 | 0.9535 | 1.7084 | 20.6194 |  |  | 57.195 |  |  |  | REC | 0.42 |  |  |  | 0 |  |  |  |  | 0.42
44 | T.O.O (CE-Construction-I) Ms. No. 173 Dated: 03.09.2012 SI11YELDUR | S-11-38 | APT/TS/132 kV SS -Yeldurthy/F-INVST - 7/2013 | 132 kV SS Yeldurthy & connected lines | System Improvement | 12.08.2016 | 31.03.2019 | 19.225 | 0.5767 | 0.1922 | 1.1535 | 2.0667 | 23.2141 |  |  | 17.27 |  |  |  | NABARD | 1.59 |  |  |  | 12.2 |  |  |  |  | 13.79
45 | T.O.O (CE-Construction-I) Ms. No. 151 Dated: 13.08.2012 SI11YERRAB | S-11-39 | APT/TS/132kV SS-Yerrabelli/F-INVST-39/2013 | 132kv SS Yerrabelli(V), Nidmanoor(M) & connected lines | System Improvement | 18.09.2015 | 31.03.2019 | 12.5144 | 0.25332 | 1.371 | 0.0016 | 0.94069 | 15.081 |  |  | 13.71 |  |  |  | Dena Bank | 1.09 |  |  |  | 0 |  |  |  |  | 1.09
46 | T.O.O (CE-Construction) MS. NO. 198 Dated: 04 .12.2004 | S-11-42 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132KV DC/SC line from 132KVSS Shadnagar | System Improvement | 01.04.2012 | 31.03.2019 | 1.96 | 0.0588 | 0.196 | 0.117 | 0.2107 | 2.5425 |  |  | 0 |  |  |  | TS Transco | 0 |  |  |  | 0.23 |  |  |  |  | 0.23
47 | T.O.O (CE-Construction-I) Ms. No.35 Dated: 27.04.2011 | S-11-44 | CRN.No. APT/TS/132 KVSS/Madugularu/F.Invest. 16/2013 | 132/33 kV Substation at Madugula in Mahaboobnagar district along with connected 132 kV & 33 kV lines | System Improvement | 21.12.2015 | 31.03.2019 | 18.4083 | 0.55225 | 1.8408 | 1.1045 | 1.9789 | 23.8848 |  |  | 19.05 |  |  |  | PFC | 0 |  |  |  | 0.11 |  |  |  |  | 0.11
48 | T.O.O (CE-Construction) MS. No. 89 Dated: 06 .06.2011 | S-11-47 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | stringing the 2nd circuit of 220 kV Chalakurthy – Kondamallepally line and 220 kV bay extensions at 220 kV Kondamallepally SS and 220 kV Chalakurthy SS in Nalgonda district | System Improvement | 01.04.2012 | 31.03.2019 | 7.6916 | 0.23075 | 0.76916 | 0.4615 | 0.82685 | 9.9799 |  |  | 8.56 |  |  |  | OBC | 0 |  |  |  | 0.01 |  |  |  |  | 0.01
49 | T.O.O (CE-Construction-I) MS. No.376 Dated: 13.01.2012 | S-12-01 | APT/TS/220KV-SS-Kosgi/F-INVST-50/2013 | 220 kV features at proposed 132/33 kV Kosigi SS in Mahaboobnagar district | System Improvement | 07.08.2014 | 31.03.2019 | 43.5417 | 1.3062 | 4.3542 | 2.6125 | 4.6807 | 56.4953 |  |  | 46.5728 |  |  |  | REC | 0.79 |  |  |  | 0 |  |  |  |  | 0.79
50 | T.O.O (CE-Construction) Ms.No. 16 Dated: 22 .06.2015 | S-12-02 | CRN.No./TST/TS/132/33 KVSS/Arempula/F.Invest.App./12/15 | 132/33kV Substation at Arempula along with connected 132kV line in Khammam district | System Improvement | 06.06.2016 | 31.03.2019 | 17.9417 | 0.53825 | 1.7942 | 1.0765 | 1.9287 | 23.2793 |  |  | 19.04 |  |  |  | TMB | 4.02 |  |  |  | 0 |  |  |  |  | 4.02
51 | T.O.O (CE-Construction-I) Ms. No. 278 Dated: 13.12.2012 | S-12-03 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV features at Gangadhara 132/11 kV Lift irrigation substation in Karimnagar district | System Improvement | 29.11.2016 | 31.03.2019 | 3.4833 | 0.1045 | 0.34833 | 0.209 | 0.37446 | 4.5196 |  |  | 7.5124 |  |  |  | REC | 0.21 |  |  |  | 0 |  |  |  |  | 0.21
52 | T.O.O (CE-Construction-I) Ms. No. 460 Dated: 24.02.2012 | S-12-04 | CRN.No.TST/TS/132 KV SS-Inavolu/F-INVST-15/2014/Dt:24.05.2013 | 132/33 kV Substation at Inavole in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 10.11.2016 | 31.03.2019 | 20.09 | 0.6027 | 2.009 | 1.2054 | 2.1597 | 26.0668 |  |  | 20.79 |  |  |  | PFC | 2.79 |  |  |  | 0 |  |  |  |  | 2.79
53 | T.O.O (CE-Construction-I) Ms. No. 283 Dated: 20.12.2012 SI12JNKP33 | S-12-05 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 33 kV features at Jankampet 132/11 kV Lift irrigation substation in Nizamabad district | System Improvement | 09.12.2016 | 31.03.2019 | 6.96 | 0.205 | 0.7 | 0.42 | 0.7488 | 9.0338 |  |  | 8.36 |  |  |  | REC | 2.55 |  |  |  | 2.57 |  |  |  |  | 5.12
54 | T.O.O (CE-Construction-I) MS. No. 261 Dated: 28.11.2012 | S-12-06 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 2nd circuit stringing on existing 220 kV DC/SC line from 220 kV Ramagundam Sub-Station to 220 kV Mandamarri (Bellampally) Sub-Station | System Improvement | 01.10.2014 | 31.03.2019 | 10.4871 | 0.039 | 1.067 | - | 0.1439 | 11.737 |  |  | 9.1575 |  |  |  | REC | 0.1 |  |  |  | 1.87 |  |  |  |  | 1.97
55 | T.O.O (CE-Construction) Ms.No.27 Dated: 12 .02.2015 SI12MDPALL | S-12-10 | TST/TS/132kV / MD Pally, Kattedan /F-INVST- 03/2016 | 132 kV SS MD Pally (Kattedan) & connected lines | System Improvement | 05.08.2015 | 31.03.2019 | 52.6715 | 0.7587 | 5.79 | 1.7015 | 2.7683 | 63.69 |  |  | 33.864 |  |  |  | PFC | 6.7 |  |  |  | 0 |  |  |  |  | 6.7
56 | T.O.O (CE-Construction) Ms. No.127 Dated: 17.07.2015 SI12MUNAGA | S-12-11 | TST/TS/132/33kV SS Munagala / F-INVST- 13/2015 | 132kV SS Munagala(V&M) & connected lines | System Improvement | 20.06.2016 | 31.03.2019 | 33.8827 | 0.3453 | 3.554 | 0.0749 | 1.2371 | 39.094 |  |  | 30.947 |  |  |  | REC | 3.51 |  |  |  | 23.44 |  |  |  |  | 26.95
57 | T.O.O (CE-Construction-I) Ms. No. 399 Dated: 21 .01.2012 | S-12-13 | CRN.No. APT/TS/132 KVSS-palakurthy/F.Invest. 16/2013 | 132/33 kV Substation at Palakurthy in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 12.11.2015 | 31.03.2019 | 16.3583 | 0.49075 | 1.6358 | 0.9815 | 1.7585 | 21.2249 |  |  | 19.11 |  |  |  | TMB | 0.27 |  |  |  | 0 |  |  |  |  | 0.27
58 | T.O.O (CE-Construction-I) Ms. No.182 Dated: 10.09.2012 | S-12-14 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV features in proposed 132 kV Switching station at Ramapuram (Ckoramandal Cements) in Nalgonda district | System Improvement | 09.09.2015 | 31.03.2019 | 3.4833 | 0.1045 | 0.34833 | 0.209 | 0.37446 | 4.5196 |  |  | 4.18 |  |  |  | TMB | 0.02 |  |  |  | 0 |  |  |  |  | 0.02
59 | TOO (CE-Construction) MS NO.30, Dt:18.02.2016 | S-12-15 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Substation at Salkunoor (V) of Vemulapally (M) in Nalgonda district along with connected 132 kV & 33 kV lines | System Improvement | 1.04.2018 | 31.03.2019 | 11.1389 | 0.2566 | 1.238 | 0.0652 | 0.9193 | 13.618 |  |  | 30.947 |  |  |  | REC | 0 |  |  |  | 1.34 |  |  |  |  | 1.34
60 | T.O.O (CE-Construction-I) Ms.No. 42 Dated: 10.05.2013 | S-13-01 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 220/33 kV features at existing Salivagu 220/11 kV Lift irrigation substation in Warangal district | System Improvement | 04.09.2014 | 31.03.2019 | 9.3417 | 0.28025 | 0.93417 | 0.5605 | 1.0042 | 12.1208 |  |  | 9.9717 |  |  |  | REC | 0.08 |  |  |  | 0 |  |  |  |  | 0.08
61 | T.O.O (CE-Transmission)MS.No. 5 Dated:11.01.2016 SI13AYYAGA | S-13-02 | TST/TS / 220/132 kV SS Ayyagaripally, Mahabubabad /F-INVST- 03/16 - 2016-17 | 220/132 kV SS at Ayyagaripally in Mahaboobabad in Warangal district | System Improvement | 02.03.2016 | 31.03.2019 | 74.8417 | 0.6839 | 6.893 | 0.3533 | 2.4511 | 85.223 |  |  | 68.9068 |  |  |  | REC | 5.15 |  |  |  | 0 |  |  |  |  | 5.15
62 | T.O.O (CE-Construction) MS.No .109 Dated:17.05.2018 (Revised) | S-13-06 | TST/TS/132kV SS/ Dommarapochampalli /F-INVST- 04/2015 | 132KV Dommarapochampally & connected lines | System Improvement | 24.12.2016 | 31.03.2019 | 35.9609 | 0.4336 | 4.031 | 2.3413 | 1.5742 | 44.341 |  |  | 32.3488 |  |  |  | REC | 5.54 |  |  |  | 16.75 |  |  |  |  | 22.29
63 | T.O.O (CE-Transmission) Ms.No.193 Dated:07.10.2015 (Revised) | S-13-10 | TST/TS/132kV / Kachapur SS/F-INVST- 17/2016 | 132/33kV SS Kachapur & connected lines | System Improvement | 22.09.2015 | 31.03.2019 | 19.9182 | 0.3337 | 1.8946 | 0.0827 | 1.1954 | 23.4246 |  |  | 21.53 |  |  |  | REC | 0.87 |  |  |  | 10.72 |  |  |  |  | 11.59
64 | T.O.O (CE-Construction) MS.No. 144 Dated:03.08.2015 | S-13-14 | CRN.No./TST/TS/220/132KV Substation /Sircilla /F.Invst./ App./08/2015 | 220/132 kV SS at Sircilla in Karimnagar District | System Improvement | 22.12.2015 | 31.03.2019 | 72.7583 | 2.1827 | 7.2758 | 4.3655 | 7.8215 | 94.4039 |  |  | 59.9992 |  |  |  | REC | 2.32 |  |  |  | 0 |  |  |  |  | 2.32
65 | T.O.O (CE-Construction-I)MS.No. 186 Dated: 11.09.2013 2) T.O.O (CE-Construction) Ms. No. 103 Dated:11.07.2017 | S-13-15 | CRN TST/TS/220/ Switching Station/Mahaboobnagar/132 KV Features /Invest,Approval No.14/17-2017-18 | erection of 132 kV features at 220 kV Thimmajipet Switching Station in Mahaboobnagar District and extending connectivity to 132 kV Jadcherla Sub-Station from Thimmajipet | System Improvement | 01.04.2014 | 31.03.2019 | 24.43 | 0.733 | 2.443 | 1.4858 | 2.6262 | 31.718 |  |  | 26.38 |  |  |  | REC | 0 |  |  |  | 0.06 |  |  |  |  | 0.06
66 | T.O.O (CE-Construction) Ms. No. 02 `Dated: 04.02.2015. | S-15-03 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Chandulapur Village of Chinnakodur Mandal in Medak District along with connected lines | System Improvement | 27.04.2016 | 31.03.2019 | 15.2083 | 0.45625 | 1.5208 | 0.9125 | 1.6349 | 19.7328 |  |  | 30.5565 |  |  |  | REC | 0.19 |  |  |  | 0 |  |  |  |  | 0.19
67 | T.O.O (CE-Transmission) MS.No. 163 Dated: 26.08.2015 | S-15-08 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132 kV DC line for making LILO of one circuit of existing 132kV DC line from 132 KV SS Jakora to 132 KV SS Bichkunda at 132/33 kV SS Banswada under the program for providing 9.00 Hrs Day Time Supply for Agriculture | System Improvement | 09.12.2016 | 31.03.2019 | 6.6667 | 0.2 | 0.66667 | 0.4 | 0.71667 | 8.65 |  |  | 6.53 |  |  |  | PFC | 0.68 |  |  |  | 0 |  |  |  |  | 0.68
68 | T.O.O (CE-Construction) Ms. No 26 Dated: 2.02.2015 | S-15-09 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132 kV line for LILO of Ghanapur – Imlibun SC line to 220/132/33 kV SS Nagole (HMRL) | System Improvement | 08.01.2016 | 31.03.2019 | 9.9833 | 0.2995 | 0.9983 | 0.599 | 1.0732 | 12.9533 |  |  | 10.77 |  |  |  | REC | 0.08 |  |  |  | 0.02 |  |  |  |  | 0.1
69 | T.O.O (CE-Construction) Ms. No. 128 Dated: 17.07 2015. | S-15-10 | CRN.No.TST/TS/132/33 KVSS/Narayanpet, Mahabubnagar/Invest.Apprl.No.5/16,2016-17 | 132/33 kV Substation at Narayanpet in Mahaboobnagar District along with connected 132 kV & 33 kV lines | System Improvement | 21.09.2016 | 31.03.2019 | 17.6917 | 0.53075 | 1.7692 | 1.0615 | 1.9019 | 22.9549 |  |  | 34.9754 |  |  |  | REC | 0.24 |  |  |  | 0 |  |  |  |  | 0.24
70 | T.O.O (CE-Transmission) MS.No. 164 Dated: 06.11.2017 (Revised) | S-15-11 | TST/TS/ 220 kV 2nd circuit / RSS to Nirmal SS and RSS to Jagityal SS / F-INVST- 15/2015 | 220 kV 2nd circuit stringing on 220 kV RSS - Jagityal and 220 kV RSS - Nirmal | System Improvement | 27.11.2015 | 31.03.2019 | 65.6314 | 0.0511 | 6.614 | 0.2699 | 0.1876 | 72.754 |  |  | 38.06 |  |  |  | PFC | 2.06 |  |  |  | 16.7 |  |  |  |  | 18.76
71 | TOO / CE/Trans/ MS No. 179 Dated 7.09.2015 SI15YELLAR | S-15-12 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132/33 kV Sub-Station at Gandimasanipet of Yellareddy Constituency in Nizamabad District. | System Improvement | 25.07.2016 | 31.03.2019 | 14.3771 | 0.3138 | 1.1624 | 0.0749 | 1.1242 | 17.0524 |  |  | 13.4 |  |  |  | PFC | 3.03 |  |  |  | 5.62 |  |  |  |  | 8.65
72 | T.O.O (CE-Construction) Ms. No. 72 Dated: 17.04.2015. | S-15-28 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | second source of supply to 132/33 kV Sub-Station, Dharmapur in Karimnagar District by stringing of 132kV 2nd circuit on existing 132kV DC/SC line from 220/132 kV SS Jagityal to 132/33 kV SS Dharmapuri | System Improvement | 29.11.2016 | 31.03.2019 | 3.8333 | 0.115 | 0.38333 | 0.23 | 0.41208 | 4.9737 |  |  | 4.6 |  |  |  | REC | 0.18 |  |  |  | 2.55 |  |  |  |  | 2.73
73 | TOO / CE/Trans/ MS No. 136 Dated 27.07.2015 SI15LNHZRB | S-15-29 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132 kV line for making LILO of both of the circuits of existing 132 KV Husnabad-Huzurabad DC line at 220/132 kV LI Substation Huzurabad and Erection of 1 No. 100 MVA additional PTR at 220/132 kV LI SS, Huzurabad with equipment totalling to 2 X 100 MVA. | System Improvement | 11.11.2016 | 31.03.2019 | 17.1691 | 0.16 | 1.8 | 0.0978 | 0.5731 | 19.8 |  |  | 0 |  |  |  | REC | 2.31 |  |  |  | 1.89 |  |  |  |  | 4.2
74 | T.O.O (CE-Transmission) MS.No. 167 Dated: 04.09.2015 SI15L2SHAH | S-15-30 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd Circuit stringing on proposed 132 kV DC/SC line from the under construction 400/220/132 kV SS Suryapet to 132/33 kV Shah Ali Gowraram under the program for providing 9.00 Hrs agricultural supply during day time. | System Improvement | 05.04.2016 | 31.03.2019 | 5.9166 | 0.0248 | 0.604 | 0.01 | 0.0886 | 6.644 |  |  | 4.95 |  |  |  | REC | 1.59 |  |  |  | 0.46 |  |  |  |  | 2.05
75 | T.O.O (CE-Transmisssion) MS.No. 211 Dated: 07.11.2015 | S-15-32 | TST/TS/ 220 kV Pedagopati SS / Investment approval No. 19/16-2016 | Erection of 220/132/33 kV SS at Pedagopati in Khammam district | System Improvement | 27.02.2017 | 31.03.2019 | 120.2411 | 0.8479 | 10.9507 | 0.3131 | 3.0383 | 135.3911 |  |  | 121.2483 |  |  |  | REC | 24.86 |  |  |  | 17.22 |  |  |  |  | 42.08
76 | TOO / CE/Trans/ MS No. 31 Dated 18.02.2016 | S-16-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 33 kV Features at existing 132 kV Switching Station, Kodandapur in Nalgonda District. | System Improvement | 18.09.2017 | 31.03.2019 | 7.371 | 0.313 | 0.89 | 0.0945 | 1.1215 | 9.79 |  | 0 | 8.0145 |  |  |  | REC | 3.93 |  |  |  | 1.6 |  |  |  |  | 5.53
77 | T.O.O (CE-Transmission) Ms. No.49 Dated: 06.04.2016. | S-16-09 | CRN.No.TST/TS/220/132/33 KV SS, Regonda,Warangal,Dist./Invest.Appl.No.8/17,2016-17 | 132/33 kV Sub-Station at Regonda in Warangal District. | System Improvement | 07.02.2018 | 31.03.2019 | 20.5138 | 0.334 | 1.9457 | 0.0652 | 1.1968 | 24.0555 |  |  | 19.07 |  |  |  | PFC | 7.93 |  |  |  | 5.13 |  |  |  |  | 13.06
78 | T.O.O (CE-Transmission) Ms. No. 82 Dated: 23.05.2017 | S-17-11 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at existing 132/11 kV LI Sub-Station, CH. Kondur in Nizamabad District | System Improvement | 16.04.2018 | 31.03.2019 | 3.5 | 0.105 | 0.35 | 0.21 | 0.37625 | 4.5412 |  |  | 3.6708 |  |  |  | PFC | 2.18 |  |  |  | 0 |  |  |  |  | 2.18
79 | T.O.O (CE-Construction-I) MS. No. 339 Dated:08.02.2013 | P-11-01 |  | Pulichintala Hydro Electric Project (4x30 MW) – Evacuation arrangements | System Improvement | 12.03.2014 | 31.03.2019 | 27.85 | 0.8355 | 2.785 | 1.671 | 2.9939 | 36.1354 |  |  | 48.61 |  |  |  | OBC | 2.41 |  |  |  | 4.47 |  |  |  |  | 6.88
80 | T. O. O. (CE/Transmission) MS. No.171 Dated:07.09.2015 | P-15-05 |  | 400/220KV 315MVA PTR in place of failed 400/132KV 200MVA PTR at NTPC Ramagundam and connected 220KV line & Bay Works | System Improvement | 01.04.2016 | 31.03.2019 | 25.6666 | 0.77 | 2.5667 | 1.54 | 2.7592 | 33.3024 |  |  | 25.26 |  |  |  | PFC | 0.33 |  |  |  | 2.23 |  |  |  |  | 2.56
81 | T.O.O (CE-Construction) MS. No. 449 Dated: 22.02.2012 | S-12-12 | CRN.No.TST/TS/220 KVSS/Nagole(Metro Rail)F./Invest. 25/2013 | 220/132/33kV Sub-Station at Nagole (Uppal) to meet the load demand of the upcoming Hyderabad Metro Rail | System Improvement | 25.05.2012 | 31.03.2019 | 74.625 | 2.2388 | 7.4625 | 4.4775 | 8.0222 | 96.8259 |  |  | 80.4164 |  |  |  | REC | 0 |  |  |  | 10.88 |  |  |  |  | 10.88
82 | T.O.O (CE-Construction-I) MS. No. 450 Dated: 22.02.2012 | S-12-08 | APT/TS/220KV-Ghanpur-Malkaram-LILO to Moulali/F-INVST-44/2013 | Erection of 220 kV XLPE UG cable for LILO of 220 kV Ghanapur – Malkaram DC Line to 220 kV SS Moulali | System Improvement | 25.05.2013 | 31.03.2019 | 252.29 | 7.5687 | 25.229 | 15.7681 | 27.1212 | 327.977 | [7 empty] | 0.03 |  |  |  | 0 |  |  |  |  | 0.03
83 | T.O.O (CE-Construction-I) MS. No. 6 Dated: 31.01.2014 | S-10-07 | APT/TS/132 kV SS -Burugupalli/ F-INVST -21/2013 | Erection of 132/33 kV Substation at Burugupally (V) in Kuntala (M) in Adilabad district along with connected 132 kV lines | System Improvement | 31.03.2014 | 31.03.2019 | 17.925 | 0.53775 | 2.15 | 1.1203 | 1.9269 | 23.66 |  |  | 17.94 |  |  |  | REC | 0.11 |  |  |  | 0 |  |  |  |  | 0.11
84 | T.O.O (CE-Construction) MS. No. 247 Dated: 25.09.2010 | S-10-09 | APT/TS/132 kV SS -Geesukonda/ F-INVST -20/2012 | Erection of 132/33 kV Substation at Geesukonda in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 30.10.2010 | 31.03.2019 | 10.24 | 0.3072 | 1.22 | 0.64 | 1.1008 | 13.508 |  |  | 10.44 |  |  |  | REC | 0.01 |  |  |  | 0 |  |  |  |  | 0.01
85 | T.O.O (CE-Transmission) Ms. No. 201 Dt: 30.10.2015 | S-11-09 | APT / TS / 132 KVSS-Chippapally / F-INVST/31/2013. | Erection of 132/33 kV Substation at Chippapally in Karimnagar district along with connected lines | System Improvement | 20.01.2016 | 31.03.2019 | 28.4 | 0.852 | 3.41 | 1.775 | 3.053 | 37.49 | [6 empty] | NABARD | 0.17 |  |  |  | 0 |  |  |  |  | 0.17
86 | T.O.O (CE-Construction) Ms. No. 51 Dt: 15.12.2014 | S-14-04 | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | Erection of 132/33 kV Substation at Ganeshpally in Medak District along with connected lines | System Improvement | 12.02.2015 | 31.03.2019 | 19.03 | 0.5709 | 2.28 | 1.1894 | 2.0457 | 25.116 |  |  | 57.2 |  |  |  | REC | 0.91 |  |  |  | 0 |  |  |  |  | 0.91
87 | T.O.O (CE-Construction) Ms. No. 52 Dt: 15.12.2014 | S-14-03 | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | Erection of 132/33 kV Substation at Duddeda in Medak District along with connected lines | System Improvement | 12.02.2015 | 31.03.2019 | 20.5 | 0.615 | 2.46 | 1.2812 | 2.2037 | 27.06 | [6 empty] | REC | 0.97 |  |  |  | 0 |  |  |  |  | 0.97
88 | T.O.O (CE-Construction) Ms. No. 290 Dt: 16.10.2010 | S-08-14 | APT/TS/220/33 KV-Singotam x Roads//F-INVST-20/2011 | Erection of 220/33 kV SS at Singotam ‘X’ Roads, instead of erection of 132/33 kV substation at Singotam ‘X’ Roads, Kollapur Mandal in Mahabubnagar district along with connected lines | System Improvement | 12.02.2011 | 31.03.2019 | 17.64 | 0.5292 | 2.12 | 1.1025 | 1.8963 | 23.288 | [6 empty] | Syndicate Bank | 0.15 |  |  |  | 0 |  |  |  |  | 0.15
89 | T.O.O (CE-Construction-I) Ms. No. 04 Dt: 06.04.2011 | S-11-13 | APT/TS/132kV SS-Doulthabad/F-INVST-38/2013 | erection of 132/33 kV Substation at Doulthabad in Medak district along with connected 132 kV & 33 kV lines | System Improvement | 10.06.2011 | 31.03.2019 | 18.17 | 0.5451 | 2.18 | 1.1356 | 1.9533 | 23.984 |  |  | 18.77 |  |  |  | REC | 0.32 |  |  |  | 0 |  |  |  |  | 0.32
90 | TOO MS.NO.11 dt:07.03.2014 | S-10-17 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 KV Substation at N V Puram in Khammam District | System Improvement | 07.08.2016 | 31.03.2020 | 19.9462 | 0.59838 | 1.9946 | 1.2466 | 2.1442 | 25.93 |  |  | 10.55 |  |  |  | REC | 9.88 |  |  |  | 10.77 |  |  |  |  | 20.65
91 | T.O.O (CE-Construction) MS.No .82 Dated:18.04.2018 | S-11-11 | CRN.No.TST/TS132 kV SSt Donthanpalli/F-INVST-06/2013/Dt:08.10.2014 | 132 kV DC line from the proposed 220/132/33 kV SS Parigi to 132/33 kV SS Dharmasagar (132/33 kV Substation at Donthanpalli ) | System Improvement | 13.12.2016 | 31.03.2020 | 15.9462 | 0.47838 | 1.5946 | 0.99663 | 1.7142 | 20.73 |  |  | 19.2627 |  |  |  | REC | 6.56 |  |  |  | 6.71 |  |  |  |  | 13.27
92 | TOO (CE-Construction) MS NO.83, Dt:21.06.2013 | S-11-16 | CRN.No.APT/TS/220/132 kV SS-Huzurnagar/F-INVST-01/2014/Dt:20.04.2013 | 220/132/33 kV substation at Huzurnagar in Nalgonda District | System Improvement | 31.10.2013 | 31.03.2020 | 45.75 | 1.37 | 5.49 | 2.86 | 4.92 | 60.39 |  |  | 62.65 |  |  |  | PFC | 12.38 |  |  |  | 38.86 |  |  |  |  | 51.24
93 | TOO (CE-Transmission) MS.NO.161 dt:26-08-2015 | S-11-28 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Nimmapalli with connected line in Karimnagar Dist | System Improvement | 23.03.2018 | 31.03.2020 | 18.4688 | 0.2546 | 1.97 | 0.0644 | 0.9122 | 21.67 |  |  | 17.73 |  |  |  | REC | 7.78 |  |  |  | 0.71 |  |  |  |  | 8.49
94 | TOO 61, Dt:25.05.2012 | S-12-09 | APT/TS/132/Yeddumailram/F-INVST-27/2013 | 132 KV DC/SC inter linking lines between substations 220 KV Yeddumailram-132 KV Pashmailaram | System Improvement | 01.12.2018 | 30.09.2020 | 9.086 | 0.0462 | 0.931 | 0.0012 | 0.1766 | 10.241 | [6 empty] | NABARD | 0 |  |  |  | 0.02 |  |  |  |  | 0.02
95 | TOO (CE-Construction-I) MS NO.117, Dt:30.05.2014 | S-13-03 | CRN.No. APT/TS/220 KVSS -Bonguluru/F.Invest-27/2014 | 220/132/33KV SS at Bonguloor in RR District | System Improvement | 01.06.2014 | 31.03.2020 | 56.8088 | 2.1343 | 6.34 | 0.04328 | 4.4136 | 69.74 | [6 empty] | NABARD | 19.76 |  |  |  | 0.47 |  |  |  |  | 20.23
96 | T.O.O (CE-Construction-I) Ms.No. 347 Dated: 13.02.2013 SI13KANDUK | S-13-11 | TST/TS/132 kV SS-Kandukuru/ F-INVST-05/2015 | 132 kV SS Kandukuru & connected lines | System Improvement | 09.09.2016 | 31.03.2020 | 21.4404 | 0.27755 | 2.275 | 0.0024 | 1.0296 | 25.025 |  |  | 20.0578 |  |  |  | REC | 1.74 |  |  |  | 0.09 |  |  |  |  | 1.83
97 | T.O.O (CE-Construction-I) MS.No.08 Dated: 26.02.2014 | S-14-05 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd circuit stringing on 132kV DC/SC line from 220kV Durshed SS to 132kV Water Works SS and 2 Nos. 132 kV bays at 220kV Durshed and 132kV Water works in Karimnagar Town substations | System Improvement | 03.03.2018 | 31.03.2020 | 2.025 | 0.06075 | 0.24 | 0.1215 | 0.21769 | 2.6649 |  |  | 2.1825 |  |  |  | REC | 1.28 |  |  |  | 0.01 |  |  |  |  | 1.29
98 | TOO 22 Dt:10.09.2014 | S-14-12 | APT/TS/132 KV SS Kaithlapur/F-INVST-4/2014 | 132 KV substation Khaithalapur aong with connected lines | System Improvement | 05.07.2016 | 31.08.2020 | 63.5174 | 0.50461 | 5.0851 | 0.1489 | 1.8691 | 71.1251 |  |  | 59.09 |  |  |  | REC | 18.85 |  |  |  | 28.19 |  |  |  |  | 47.04
99 | TOO / CE/Trans/ MS No. 156 Dated 19.08.2015 | S-15-01 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing second source of supply to 132/33 kV Sub-Station, Lalgadi Malakpet in Shameerpet Mandal of Ranga Reddy District | System Improvement | 20.10.2015 | 31.03.2020 | 7.0327 | 0.0559 | 0.731 | 0.0212 | 0.2002 | 8.041 |  |  | 6.2 |  |  |  | PFC | 4.12 |  |  |  | 4.44 |  |  |  |  | 8.56
100 | T.O.O (CE-Transmisssion) MS.No. 159 Dated: 24.08.2015 SI15ASWARA | S-15-02 | TST/TS/ 132/33 kV Aswaraopet SS Up-Gradation to 220/132 kV / F-INVST- 7/2015 | Up-Gradation of 132/33 kV SS Aswaraopet to 220/132 kV SS | System Improvement | 18.01.2017 | 31.03.2020 | 50.2217 | 0.5249 | 4.65 | 0.1926 | 1.8808 | 57.47 |  |  | 42.55 |  |  |  | PFC | 4.62 |  |  |  | 31.83 |  |  |  |  | 36.45
101 | TOO / CE/Trans/ MS No. 140 Dated 30.07.2015 SI15JANGAP | S-15-04 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Sub-Station at Jangapally of Bejjanki Mandal in Karimnagar District. | System Improvement | 03.03.2018 | 31.12.2019 | 18.2773 | 0.3138 | 1.7415 | 0.0749 | 1.1242 | 21.5317 |  |  | 16.68 |  |  |  | PFC | 8.55 |  |  |  | 2.33 |  |  |  |  | 10.88
102 | TOO (CE-Construction) MS NO.2, Dt:03.01.2015 | S-15-05 | CRN TST/TS/132 KVSS -Kondapur/F.Invst.06/2015 | erection of 132/33 kV Substation at Kondapur Village of Dhanwada Mandal in Mahaboobnagar District along with connected lines | System Improvement | 23.03.2017 | 31.03.2020 | 22.8844 | 0.3506 | 1.886 | - | 1.255 | 26.376 |  |  | 21.7104 |  |  |  | REC | 0 |  |  |  | 1.29 |  |  |  |  | 1.29
103 | TOO / CE/Trans/ MS No. 210 Dated 6.11.2015 SI15L2CNKT | S-15-06 S-15-35 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing of alternate supply to 132 /33 kV SS Chennur and 132/33 kV SS Kataram from 220/132 kV SS, Manthani under the program for providing 9.00 Hrs Day Time Supply for Agriculture. | System Improvement | 07.02.2018 | 31.03.2020 | 11.9197 | 0.0421 | 1.213 | 0.0178 | 0.1504 | 13.343 |  |  | 10.917 |  |  |  | REC | 2.01 |  |  |  | 1.29 |  |  |  |  | 3.3
104 | TOO (CE-Construction-I) MS NO.55, Dt:25.03.2015 | S-15-31 | CRN.No.TST/TSAsifnagar SS alternatesource of supply/Invest.App.06/2015 | erection of 2nd circuit from 220kV Shivarampally SS to 132kV Asifnagar SS for providing 2nd source of supply to 132kV Asifnagar substation | System Improvement | 16.02.2018 | 31.03.2020 | 43.7987 | 0.4071 | 4.0454 | 0.2972 | 1.467 | 50.0154 |  |  | 41.3635 |  |  |  | REC | 13.76 |  |  |  | 6.82 |  |  |  |  | 20.58
105 | TOO (CE-Transmission) MS.NO.231 dt:21-12-2015 | S-15-33 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Sarangapur in Adilabad District | System Improvement | 04.04.2018 | 31.01.2020 | 18.4173 | 0.3138 | 1.8685 | 0.0749 | 1.1242 | 21.7987 |  |  | 17.66 |  |  |  | REC | 10.55 |  |  |  | 0.04 |  |  |  |  | 10.59
106 | TOO (CE-Tr) MS NO.225, Dt:10.12.2015 | S-15-34 | CRN.No.TST/TS/Erection of 220 KV DC line Gajwel/Siddipet/Invest.App.04/17-2017-18 | 220 KV D/C Line from 400KV GAJWEL-SIDDIPET | System Improvement | 05.12.2017 | 31.12.2020 | 37.8541 | 0.0515 | 3.8117 | 0.0198 | 0.1846 | 41.9217 |  |  | 74.97 |  |  |  | REC | 17.88 |  |  |  | 8.43 |  |  |  |  | 26.31
107 | T.O.O (CE-Transmission) Ms.No.195 Dated:14.10.2015 | S-15-36 | TST/TS /132/33 kV SS Aipoor , Nalgonda /F-INVST- 01/2016-17 | 132/33 kV SS at Aipoor in Nalgonda district | System Improvement | 05.01.2017 | 31.03.2021 | 19.6933 | 0.3366 | 2.13 | 0.0841 | 1.2057 | 23.4497 |  |  | 18.9106 |  |  |  | REC | 0.01 |  |  |  | 0.52 |  |  |  |  | 0.53
108 | T.O.O (CE-Construction) MS. No. 137 Dated: 29.07.2015 | S-15-37 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection 132 kV line from 220 kV Jurala Sub-Station to 132 kV Ieeza Sub-Station under the program of providing 9.00 Hrs agricultural supply during day time | System Improvement | 12.03.2018 | 31.03.2020 | 16.3816 | 0.0318 | 1.64 | 0.0128 | 0.1138 | 18.18 |  |  | 30.5565 |  |  |  | REC | 12.01 |  |  |  | 0.09 |  |  |  |  | 12.1
109 | TOO / CE/Trans/ MS No. 158 Dated 22.08.2015 | S-15-38 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132 kV lines for making LILO of (i) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Jangaon and (ii) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Kolanpak | System Improvement | 10.03.2017 | 31.03.2020 | 8.1522 | 0.0457 | 0.838 | 0.0186 | 0.1635 | 9.218 |  |  | 7.02 |  |  |  | PFC | 1.92 |  |  |  | 0.62 |  |  |  |  | 2.54
110 | TOO / CE/Trans/ MS No.62 Dated 25.04.2016 | S-16-08 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at existing 220/11 kV LI Sub-Station, Bheemghanpur Warangal District. | System Improvement | 05.05.2017 | 31.03.2020 | 4.775 | 0.14325 | 0.573 | 0.29844 | 0.51331 | 6.303 |  |  | 16.31 |  |  |  | PFC | 3.09 |  |  |  | 2.8 |  |  |  |  | 5.89
111 | TOO / CE/Trans/ MS No.76 Dated 25.05.2016 | S-16-11 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Bachannapet in Warangal District | System Improvement | 20.04.2017 | 31.03.2020 | 18.1064 | 0.2639 | 1.938 | 0.0642 | 0.9455 | 21.318 |  |  | 16.71 |  |  |  | PFC | 6.33 |  |  |  | 0.03 |  |  |  |  | 6.36
112 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | S-16-12 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Kotagiri with connected line & Bay in Nizamabad District | System Improvement | 06.06.2018 | 31.03.2020 | 13.8496 | 0.2419 | 1.505 | 0.0842 | 0.8743 | 16.555 |  |  | 12.98 |  |  |  | PFC | 0.68 |  |  |  | 0 |  |  |  |  | 0.68
113 | TOO No.72 Dt:13.05.2016 | S-16-14 | TST/TS/ 220132/33 kV / Substation, Borampet RR District/ INVST- No. 07/16 - 2016-17 | 220/132/33 kV Substation at Borampet in Ranga Reddy district | System Improvement | 28.11.2016 | 31.03.2020 | 196.487 | 3.3449 | 20.3712 | 0.3778 | 11.9859 | 232.5668 |  |  | 182.98 |  |  |  | PFC | 18.45 |  |  |  | 30.6 |  |  |  |  | 49.05
114 | TOO (CE-Transmission) MS NO.173, Dt:15.12.2016 | S-16-16 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 220/33 kV Sub-Station, at Domalapenta Village of Nagarkurnool District (erstwhile Mahaboobnagar District) | System Improvement | 05.03.2018 | 30.11.2019 | 12.5539 | 0.318 | 1.42 | 0.1885 | 1.1396 | 15.62 |  |  | 12.4108 |  |  |  | PFC | 5.84 |  |  |  | 1.49 |  |  |  |  | 7.33
115 | T.O.O (CE-Transmission) Ms. No. 26, Dated: 27.02.2017. | S-17-01 | CRN TS/TST/220/33 KV, GIS, Chanchaguda/Invest.Approval No.7/17-2017-18 | Erection of 220/33 kV Sub-Station at Chanchalguda | System Improvement | 28.02.2018 | 31.03.2020 | 78.651 | 2.2842 | 8.192 | - | 8.1849 | 97.3121 |  |  | 80.208 |  |  |  | REC | 37.21 |  |  |  | 0.09 |  |  |  |  | 37.3
116 | T.O.O (CE-Transmission) Ms. No. 29, Dated: 27.02.2017. | S-17-06 | CRN TS/TST/132/33 KV, GIS, Petlaburz invest.Approval No.5/17-2017-18 | 132/33 kV Substation at PTO, Petlaburz, Hyderabad District | System Improvement | 02.03.2018 | 31.03.2021 | 35.4257 | 0.9818 | 3.993 | 0.0045 | 3.5183 | 43.9233 |  |  | 35.93 |  |  |  | REC | 20.02 |  |  |  | 0.07 |  |  |  |  | 20.09
117 | T.O.O (CE-Transmission) Ms. No.84, Dated: 27.05.2017 | S-17-09 | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | 220/132/33 kV Substation at Toopran(meenaji pet) in Medak District along with connected lines | System Improvement | 27.01.2016 | 31.03.2020 | 60.8 | 1.824 | 6.08 | 3.8 | 6.536 | 79.04 |  |  | 68.43 |  |  |  | REC | 32.11 |  |  |  | 7.76 |  |  |  |  | 39.87
118 | T.O.O (CE-Construction) MS.No .294 Dated:29.01.2019 | S-18-02 | CRN No: TST/TS/Erecion of 220/132 kV Substation at Ammavaripet, Kazipet(M) in Warangal Urban District.F. Approval/ No.13/18/2018-19 | erection of 220/132 kV Sub-Station at Ammavaripetin Warangal-Urban District | System Improvement | 31.10.2018 | 30.06.2021 | 84.9 | 2.547 | 15.02 | 15.282 | 9.1267 | 126.8757 |  |  | 87.24 |  |  |  | PFC | 0.28 |  |  |  | 0 |  |  |  |  | 0.28
119 | TOO (CE-construction) MS.NO.86 dt:29-05-2017 | S-17-12 | CRN TST/TS/132/33KV, Choppadandi, SS /Invest,Approval No.20/18-2017-18 | 132/33 kV SS with connected line at Choppadandi in Karimnagar Dist. | System Improvement | 06.06.2018 | 31.03.2020 | 21.1755 | 0.3375 | 2.5135 | 0.1282 | 1.2093 | 25.364 |  |  | 19.97 |  |  |  | PFC | 0.02 |  |  |  | 0 |  |  |  |  | 0.02
120 | TOO (CE_Transmission)Ms.No.69 Dt:09.05.2017 | S-17-13 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Yadagirigutta Temple with connected line Town of Yadadri (erstwhile Nalgonda) .District | System Improvement | 01.10.2018 | 31.03.2020 | 13.9285 | 0.2154 | 1.6566 | 0.1312 | 0.7851 | 16.7168 |  |  | 13.16 |  |  |  | PFC | 5.08 |  |  |  | 0 |  |  |  |  | 5.08
121 | T.O.O (CE-Construction) Ms. No.170 Dt;16.11.2017 | S-17-14 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing of 33 kV Features at upcoming 220/132 KV Sub-Station, Mahabubabad in Mahabubabad District | System Improvement | 31.10.2018 | 31.08.2020 | 6.6281 | 0.1807 | 0.854 | 1.0839 | 0.6473 | 9.394 |  |  | 7.44 |  |  |  | REC | 0.35 |  |  |  | 0 |  |  |  |  | 0.35
122 | T.O.O (CE-Construction) Ms. No. 124, Dated: 19.08.2017 | S-17-15 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Chinna Shankarampet in Medak District | System Improvement | 01.04.2018 | 31.03.2020 | 13.3134 | 0.2482 | 1.76 | 1.4891 | 0.8893 | 17.7 |  |  | 13.96 |  |  |  | REC | 0.63 |  |  |  | 0 |  |  |  |  | 0.63
123 | T.O.O (CE-Transmission) Ms. No. 70, Dated 09.05.2017 | S-17-18 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | feeding 132/33 kV SS Ghanpur through Ring Mains | System Improvement | 23.10.2018 | 31.03.2020 | 4.83 | 0.1449 | 0.483 | 0.2898 | 0.51923 | 6.2669 |  |  | 5.07 |  |  |  | PFC | 2.62 |  |  |  | 0 |  |  |  |  | 2.62
124 | TOO (CE-construction) MS.NO.13 dt:20-01-2018 | S-17-19 | CRN No. TST/TS/Erection of 132/33 KV SS at Pitlam in Khammam Dist. Approval/No.04/2018-19 | 132/33 kV SS at Pitlam in Nizamabad District (13, dt.20.1.18 | System Improvement | 31.10.2018 | 31.03.2021 | 29.5454 | 0.2846 | 3.24 | 1.7077 | 1.0198 | 35.7975 |  |  | 31.8 |  |  |  | REC | 0.05 |  |  |  | 0 |  |  |  |  | 0.05
125 | TOO (CE-Transmission) MS.NO.167 dt:04.09.2015 | S-15-30 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd Circuit stringing on proposed 132 kV DC/SC line from the under construction 400/220/132 kV SS Suryapet to 132/33 kV Shah Ali Gowraram under the program for providing 9.00 Hrs agricultural supply during day time | System Improvement | 30.11.2015 | 31.03.2019 | 5.04 | 0.1512 | 0.504 | 0.315 | 0.5418 | 6.552 |  |  | 5.45 |  |  |  | REC | 1.53 |  |  |  | 3.55 |  |  |  |  | 5.08
[7 empty] | Total | [5 empty] | 4792.0307 |  |  | 3437.4963 |  |  |  |  | 409.84 |  |  |  | 431.45 |  |  |  |  | 841.29
Chief Engineer/Construction
76 |  | S-03-04 |  | Erection of 220/132KV SS at Kondamallepa
77 |  |  |  | Sup. Erect. Test & Comm. 220/132/33 KV S
78 |  |  |  | Erection of 132KV DC/SC line from 132KV
75 | T.O.O (CE-Construction-I) Ms.No. 288 Dated: 31.12.2012 | S-12-05.02 |  | erection of 33 kV features at Bagepally 132/11 kV Lift irrigation substation in Nizamabad district
73 | T.O.O (CE-Construction-I) MS. No. 261 Dated: 28.11.2012 | S-07-17 |  | erection of 2nd circuit stringing on existing 220 kV DC/SC line from 220 kV Ramagundam Sub-Station to 220 kV Mandamarri (Bellampally) Sub-Station