## Full Format
ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 and FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2019-20 |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress( Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation
Total
ANNEXURE-II RENOVATION & MODERNISATION SCHEME (For FY:2019-2020 and FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2019-20 |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress( Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation
Total

## Technical part
ANNEXURE
RENOVATION & MODERNISATION SCHEME
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2018-19 |  |  | Please fill in the required details pertaining to each year
( Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress( Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Pepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation
Renovation, Modernisation & Improvement (RMI) |  | Renovation, Modernisation, improvement, replacement of aged & obsolete equipments and strengthing works | 2019-01-04 | 31/3/2020 | [13 empty] | By Loan
[15 empty] | Superintending Engineer/OMC | [12 empty] | Superintending Engineer/OMC/
Chief Engineer/Transmission(I/C)
Chief Engineer/Transmission

## Aug 18-19 (hidden)
ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 and FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  |  | This form captures investments as planned and actually incurred
FY: 2018-19 |  |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
Revised ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 to FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2018-19 |  |  | Please fill in the required details pertaining to each year
(Figures Rs. in crores)
PROJECT DETAILS | [5 empty] | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress (Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Expenditure as on 31.03.2018 by CWIP Position as on 31.03.2018 | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[15 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation |  |  |  | PTRCharging dates
---- | Augmentation of PTR capacities at 132KV Chilakalguda SS and 132 KV Hussainsagar | To meet the Industrial, Agriculture and etc., loads | 0 | 12.02.2015 | 2019-03-31 | 6.8 | 0.29 | 0 | 0 | 0.12 | 1.1 | 8.31 |  |  | 7.42 |  |  |  | PFC 37203015 | 8.31 |  |  | 100% | 8.31 |  |  | 100% | 8.31 |  |  | 100% |  | ( TOO 28 Dt 12-02-2015 ) | A-15-02
---- | Augmentation of PTR capacities at132KV Gunrock SS | To meet the Industrial, Agriculture and etc., loads | 1.16 | 14.02.2015 | 2019-03-31 | 3.9 | 0.12 | 0 | 0 | 0.07 | 0.42 | 4.51 | [7 empty] | 3.35 |  |  | 74.28% | 3.35 |  |  | 74.28% | 4.51 |  |  | 100% |  | (TOO 33 Dt 14-02-2015) | A-15-24
---- | Augmentation of PTR capacities at 220KV Gunrock SS & 220KV Ghanapur SS | To meet the Industrial, Agriculture and etc., loads | 0.95 | 2016-12-08 | 2019-03-31 | 11.83 | 0.4 | 0 | 0 | 0.36 | 1.46 | 14.05 | [7 empty] | 13.1 |  |  | 93.24% | 13.1 |  |  | 93.24% | 14.05 |  |  | 100% |  | T.O.O Ms No.167, 08.12.2016 | A-16-10
---- | Augmentation of PTR capacities at 132 KV Malyalapally SS | To meet the Industrial, Agriculture and etc., loads | 0 | 2016-12-09 | 1900-01-03 09:07 | 4.39 | 0.18 | 0 | 0 | 0.15 | 0.66 | 5.38 |  |  | 4.84 |  |  |  | REC 13979 | 5.38 |  |  | 100% | 5.38 |  |  | 100% | 5.38 |  |  | 100% |  | T.O.O Ms No.169, 09.12.2016 | A-16-09
TST/ TS/ Augmentation of Transformer capacities (24 Hrs. Agricultural supply) / Investment approval No.13/17, 2017-18 | Augmentation of PowerTransformer capacities at various EHT SS in Warangal and Karimnagar Zones | For extending 24 Hrs. Agricultural Supply | 0.25 | 2017-05-20 | 2019-03-31 | 59.91 | 2.2 | 0 | 0 | 2.23 | 7.89 | 72.23 |  |  | 63.13 |  |  |  | PFC:37203017 | 71.98 |  |  | 99.65% | 71.98 |  |  | 99.65% | 72.23 |  |  | 100% |  | T.O.O Ms No.77, 20.05.2017 | A-17-01
| Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Metro and Rural Zones | For extending 24 Hrs. Agricultural Supply | 0 | 2017-06-02 | 2019-03-31 | 42.15 | 1.67 | 0 | 0 | 1.5 | 5.97 | 51.29 |  |  | 41.32 |  |  |  | PFC:37203017 | 51.29 |  |  | 100% | 51.29 |  |  | 100% | 51.29 |  |  | 100% |  | T.O.O Ms No.87, 02.06.2017 | A-17-02
---- | Augmentation of PTR capacities at 132 KV Manoharabad SS | To meet the Industrial, Agriculture and etc., loads | 0 | 2018-03-16 | 2019-03-31 | 2.49 | 0.12 | 0 | 0 | 0.6 | 0.42 | 3.63 | [7 empty] | 3.63 |  |  | 100% | 3.63 |  |  | 100% | 3.63 |  |  | 100% |  | T.O.O Ms No.55, Dt.16.03.2018 | A-17-05
---- | Augmentation of PTR capacities at 220KV Gachibowli SS & 132KV Malkaram SS | To meet the Industrial, Agriculture and etc., loads | 0 | 2018-03-16 | 2019-03-31 | 7.86 | 0.32 | 0 | 0 | 1.65 | 1.16 | 10.99 | [7 empty] | 10.99 |  |  | 100% | 10.99 |  |  | 100% | 10.99 |  |  | 100% |  | T.O.O Ms No.56, Dt.16.03.2018 | A-17-06
---- | Augmentation of PTR capacities at 220KV Chandrayangutta SS | To meet the Industrial, Agriculture and etc., loads | 0 | 2018-04-13 | 2019-03-31 | 5.58 | 0.27 | 0 | 0 | 1.4 | 1 | 8.25 | [7 empty] | 8.25 |  |  | 100% | 8.25 |  |  | 100% | 8.25 |  |  | 100% |  | T.O.O Ms No. 78, Dt:13.04.2018 | A-18-01
---- | Augmentation of PTR capacities at 132KV Yerraballi ss, 220KV Waddekthapally SS, 132KV Ghanpur SS, 132KV Inavole SS. | To meet the Industrial, Agriculture and etc., loads | 0 | 2018-07-18 | 2019-03-31 | 4.61 | 0.21 | 0 | 0 | 1.09 | 0.77 | 6.68 | [7 empty] | 6.68 |  |  | 100% | 6.68 |  |  | 100% | 6.68 |  |  | 100% |  | T.O.O Ms No. 152, Dt 18.07.2018 | A-18-02
PROJECT DETAILS | [5 empty] | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress (Year on Year) |  |  |  | Remarks | File Under Circulation, T.O.O to be issued
Project Code* | Project Title | Project Purpose** | Expenditure as on 31.03.2018 (from s_alr_87013558) | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year | [17 empty] | File Under Circulation, T.O.O to be issued
[15 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation |  | 0 | 0
---- | Augmentation of PTR capacities at 132KV RC Puram SS, 220KV Alwal SS, 132KV Kathlapur SS, 132KV Mulkamur SS & 132KV Korutlu SS. | To meet the Industrial, Agriculture and etc., loads | 0 | 2018-11-01 | 2020-03-31 | 6.86 | 0.23 | 0 | 0 | 1.17 | 0.82 | 9.08 | [7 empty] | 4.54 |  |  | 50% | 4.54 |  |  | 50% | 4.54 |  |  | 50%
---- | Augmentation of PTR capacities at 132KV Jadcherla SS, 132KV Ramapuram SS, 220KV SS, 132KV Wardhanapet SS, 132KV Inavole SS & 132KV Arempula SS. | To meet the Industrial, Agriculture and etc., loads | 0 | 2018-11-01 | 2020-03-31 | 3.02 | 0.1 | 0 | 0 | 0.53 | 0.37 | 4.02 | [7 empty] | 2.01 |  |  | 50% | 2.01 |  |  | 50% | 2.01 |  |  | 50%
Total |  |  | 2.36 |  |  | 159.4 | 6.11 |  |  | 10.87 | 22.04 | 198.42 | 0 | 0 | 116.71 | 0 | 0 | 0 | 0 | 189.51 | 0 | 0 |  | 189.51 | 0 | 0 |  | 191.87 | 0 | 0 |  | 0
150.06

## Aug 18-19 CWIP
ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 and FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2018-19 |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
Revised ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 to FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2018-19 |  |  | Please fill in the required details pertaining to each year
(Figures Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulative Progress (Year on Year) |  |  |  | Remarks | WBS Element |  | Expenditure as on 31.03.2019
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year | [18 empty] | Expenditure as on 31.03.2018 (from s_alr_87013558) |  | Amount Capitalizes as on 31.03.2018
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | [9 empty] | Sl No | Project Title | TOO Reference & Amount of Total/TS | WBS Element in SAP | Expenditure as on 31.03.2018 (from s_alr_87013558) | Expenditure as on 31.03.2018 by CWIP Position as on 31.03.2018 | Amount Proposed to be invested in current FY-2018-19 | Proposed amount to be capitlized in the current FY:18-19
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34) | (34) | (6) |  |  | Too Total |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
---- | Erection of 2nd 160MVA PTR in place of 100 at Chandrayangutta SS | To Enhance PTR Capacities of Metro zone to avoid load relief/ Powercuts | 22.12.2005 | 31.03.2019 | 114.46 | Incl | Incl | Incl | Incl | Incl | 114.46 | [7 empty] | 0 |  |  | 0% | 0.03 |  |  | 100% | 0.03 |  |  | 100% | T.O.O M.S.No.215 Dt. 22-12-2005 | A-05-03 | 0.03 | 0.03 | 114.43 | AP/TS | In the TOO Chilakalaguda 2x50 to 3x50 not completed | 114.46 | Space problem | 1 | Erection of 2nd 160MVA PTR in place of 100 at Chandrayangutta SS | T.O.O M.S.No.215 Dt. 22-12-2005 114.46Cr/114.46Cr | A-05-03 | 0.03 | 0.03 | 0 | 0.03
(1): ----; (2): Augmentation of PTRs at Various EHT Sub-stations; (4): 23.09.2009; (5): 31.03.2019; (6): 88.59; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 88.59; (20): 0; (23): 0%; (24): 0.05; (27): 100%; (28): 0.05; (31): 100%; (32): TOO MS No 50 Dt 23.05.2009; (33): A-09-02 | 2.46 | 0.05 | 88.54 | AP/TS |  | 106.91 |  | 2 | Augmentation of PTRs at Various EHT Sub-stations | TOO MS No 50 Dt 23.05.2009 106.91Cr/88.59Cr | A-09-02 | 2.46 | 0.05 | 0 | 0.05
(1): ----; (2): Enhancement of Transformer Capacities; (4): 13.09.2010; (5): 31.03.2019; (6): 71.95; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 71.95; (20): 0; (23): 0%; (24): 0.23; (27): 100%; (28): 0.23; (31): 100%; (32): TOO MS No 222 Dt 13.09.10; (33): A-10-04 | 0.23 | 0.23 | 71.72 | AP/TS |  | 210.22 |  | 3 | Enhancement of Transformer Capacities | TOO MS No 222 Dt 13.09.10 210.22Cr/71.95Cr | A-10-04 | 0.23 | 0.23 | 0 | 0.23
(1): ----; (2): Augmentation of PTRs capacities at 132kV SS Ieeza; (4): 19.03.2012; (5): 31.03.2019; (6): 1.41; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 1.41; (20): 0; (23): 0%; (24): 0.1; (27): 100%; (28): 0.1; (31): 100%; (32): TOO MS No 489 Dt 19.03.2012; (33): A-12-07 | 0.1 | 0.1 | 1.31 | AP/TS |  | 4.46 |  | 4 | Augmentation of PTRs capacities at 132kV SS Ieeza | TOO MS No 489 Dt 19.03.2012 4.46Cr/1.41Cr | A-12-07 | 0.1 | 0.1 | 0 | 0.1
(1): ----; (2): Augmentation in Warangal zone & Bandlaguda SS in Metro Zone; (4): 09.07.2013; (5): 31.03.2019; (6): 12.5; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 12.5; (20): 0; (23): 0%; (24): 0.08; (27): 100%; (28): 0.08; (31): 100%; (32): TOO MS No 110 Dt 09.07.2013; (33): A-13-03 | 0.34 | 0.08 | 12.42 | AP/TS |  | 19.61 |  | 5 | Augmentation in Warangal zone & Bandlaguda SS in Metro Zone | TOO MS No 110 Dt 09.07.2013 19.61Cr/12.5Cr | A-13-03 | 0.34 | 0.08 | 0 | 0.08
(1): ----; (2): Augmentation of PTR at 132KV SS Ichoda; (4): 18.01.2013; (5): 31.03.2019; (6): 0.61; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 0.61; (20): 0; (23): 0%; (24): 0.59; (27): 100%; (28): 0.59; (31): 100%; (32): TOO MS No 313 Dt 18.01.2013; (33): A-13-05 | 0.59 | 0.59 | 0.02 | AP/TS |  | 4.82 |  | 6 | Augmentation of PTR at 132KV SS Ichoda | TOO MS No 313 Dt 18.01.2013 4.82Cr/0.61Cr | A-13-05 | 0.59 | 0.59 | 0 | 0.59
(1): ----; (2): Augmentation of PTR capacities at various substations; (4): 28.01.2014; (5): 31.03.2019; (6): 17.41; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 17.41; (20): 0; (23): 0%; (24): 0.02; (27): 100%; (28): 0.02; (31): 100%; (32): TOO MS No 23 Dt 28.01.14; (33): A-14-02 | 0.02 | 0.02 | 17.39 | AP/TS |  | 18.83 |  | 7 | Augmentation of PTR capacities at various substations | TOO MS No 23 Dt 28.01.14 18.83Cr/17.41Cr | A-14-02 | 0.02 | 0.02 | 0 | 0.02
(1): ----; (2): Augmentation of PTRs at various EHT SS for extending 9Hrs Rural,Metro Zone; (4): 01.05.2015; (5): 31.03.2019; (6): 283.03; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 283.03; (20): 0; (23): 0%; (24): 3.45; (27): 100%; (28): 3.45; (31): 100%; (32): TOO MS No 82 Dt 01.05.2015; (33): A-15-05 A-15-08 A-15-18 A-15-19 | 24.863 | 3.45 | 279.58 |  |  |  |  | 8 | Augmentation of PTRs at various EHT SS for extending 9Hrs Rural,Metro Zone | TOO MS No 82 Dt 01.05.2015 | A-15-05 A-15-08 A-15-18 A-15-19 | 24.863 | 3.45 | 0 | 3.45
(1): ----; (2): Augmentation of PTR capacities at various Substation Extending 9Hrs Agriculture during daytime Supply in Warangal; (4): 01.05.2016; (5): 31.03.2019; (6): 233.75; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 233.75; (20): 0; (23): 0%; (24): 0.874; (27): 100%; (28): 0.874; (31): 100%; (32): TOO MS No 83 Dt 01.05.2015; (33): A-15-06 A-15-12 A-15-15 A-15-16 A-15-17 A-15-20 | 8.82 | 0.874 | 232.876 |  |  |  |  | 9 | Augmentation of PTR capacities at various Substation Extending 9Hrs Agriculture during daytime Supply in Warangal | TOO MS No 83 Dt 01.05.2015 | A-15-06 A-15-12 A-15-15 A-15-16 A-15-17 A-15-20 | 8.82 | 0.874 | 0 | 0.874
(1): ----; (2): Augmentation of PTR capacities at 220kV Narketpally, KM Pally and Miryalguda SS; (4): 02.07.2015; (5): 31.03.2019; (6): 11.35; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 11.35; (20): 0; (23): 0%; (24): 1.17; (27): 100%; (28): 1.17; (31): 100%; (32): TOO MS No 114 Dt 02.07.2015; (33): A-15-07 | 3.47 | 1.17 | 10.18 |  |  |  |  | 10 | Augmentation of PTR capacities at 220kV Narketpally, KM Pally and Miryalguda SS | TOO MS No 114 Dt 02.07.2015 | A-15-07 | 3.47 | 1.17 | 0 | 1.17
(1): ----; (2): Augmentation at 220KV SS Gachibowli ADDL. 50MVA.; (4): 23.06.2015; (5): 31.03.2019; (6): 5.7; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 5.7; (20): 0; (23): 0%; (24): 0.25; (27): 100%; (28): 0.25; (31): 100%; (32): TOO MS No 108 Dt 23.06.2015; (33): A-15-25 | 0.25 | 0.25 | 5.45 |  |  |  |  | 11 | Augmentation at 220KV SS Gachibowli ADDL. 50MVA. | TOO MS No 108 Dt 23.06.2015 | A-15-25 | 0.25 | 0.25 | 0 | 0.25
(1): ----; (2): Augmentation with 160MVA in place of 100MVA at Gajwel & Tumkibollaram; (4): 23.04.2016; (5): 31.03.2019; (6): 8.95; (7): Incl; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): 8.95; (20): 0; (23): 0%; (24): 0; (27): 100%; (28): 0; (31): 100%; (32): TOO MS No 61 Dt 23.04.2016; (33): A-16-06 | 5.02 | 0 | 8.95 |  |  |  |  | 12 | Augmentation with 160MVA in place of 100MVA at Gajwel & Tumkibollaram | TOO MS No 61 Dt 23.04.2016 | A-16-06 | 5.02 | 0 | 0 | 0
---- | Erection of 33KV bay Extension Works for extending 9 Hrs Agl Supply day time for TSNPDCL | DC Works for TSNPDCL | 31.03.2016 | 31.03.2019 | 27.79 | Incl | Incl | Incl | Incl | Incl | 27.79 | [7 empty] | 0 |  |  | 0% | 0.05 |  |  | 100% | 0.05 |  |  | 100% | TOO MS No 46 Dt 31.03.2016 | D-16-06 | 12.52 | 0.05 | 27.74 |  |  |  |  | 13 | Erection of 33KV bay Extension Works for extending 9 Hrs Agl Supply day time for TSNPDCL | TOO MS No 46 Dt 31.03.2016 | D-16-06 | 12.52 | 0.05 | 0 | 0.05
---- | Augmentation of PTR capacities at132KV Gunrock SS | To meet the Industrial, Agriculture and etc., loads | 14.02.2015 | 2019-03-31 | 3.9 | 0.12 | 0 | 0 | 0.07 | 0.42 | 4.51 | [7 empty] | 3.34 |  |  | 74.06% | 2.07 |  |  | 45.9% | 2.07 |  |  | 45.9% | TOO 33 Dt 14-02-2015 | A-15-24 | 1.17 | 2.07 | -0.9
---- | Augmentation of PTR capacities at 220KV Gunrock SS & 220KV Ghanapur SS | To meet the Industrial, Agriculture and etc., loads | 2016-12-08 | 2019-03-31 | 11.83 | 0.4 | 0 | 0 | 0.36 | 1.46 | 14.05 | [7 empty] | 13.1 |  |  | 93.24% | 5.44 |  |  | 38.72% | 5.44 |  |  | 38.72% | T.O.O Ms No.167, 08.12.2016 | A-16-10 | 0.95 | 5.44 | -4.49
---- | Augmentation of PTR capacities at 132 KV Malyalapally SS | To meet the Industrial, Agriculture and etc., loads | 2016-12-09 | 2019-03-31 | 4.39 | 0.18 | 0 | 0 | 0.15 | 0.66 | 5.38 |  |  | 4.84 |  |  |  | REC 13979 | 5.38 |  |  | 100% | 0.19 |  |  | 3.532% | 0.19 |  |  | 3.532% | T.O.O Ms No.169, 09.12.2016 | A-16-09 | 0 | 0.19 | -0.19
TST/ TS/ Augmentation of Transformer capacities (24 Hrs. Agricultural supply) / Investment approval No.13/17, 2017-18 | Augmentation of PowerTransformer capacities at various EHT SS in Warangal and Karimnagar Zones | For extending 24 Hrs. Agricultural Supply | 2017-05-20 | 2019-03-31 | 59.91 | 2.2 | 0 | 0 | 2.23 | 7.89 | 72.23 |  |  | 63.13 |  |  |  | PFC:37203017 | 54.29 |  |  | 75.16% | 37.07 |  |  | 75.16% | 37.07 |  |  | 51.32% | T.O.O Ms No.77, 20.05.2017 | A-17-01 | 17.94 | 37.07 | -19.13
| Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Metro and Rural Zones | For extending 24 Hrs. Agricultural Supply | 2017-06-02 | 2019-03-31 | 42.15 | 1.67 | 0 | 0 | 1.5 | 5.97 | 51.29 |  |  | 41.32 |  |  |  | PFC:37203017 | 41.2 |  |  | 80.33% | 41.92 |  |  | 80.33% | 41.92 |  |  | 81.73% | T.O.O Ms No.87, 02.06.2017 | A-17-02 | 10.09 | 41.92 | -31.83
---- | Augmentation of PTR capacities at 132 KV Manoharabad SS | To meet the Industrial, Agriculture and etc., loads | 2018-03-16 | 2019-03-31 | 2.49 | 0.12 | 0 | 0 | 0.6 | 0.42 | 3.63 | [6 empty] | REC 14453 | 1.22 |  |  | 33.61% | 2.41 |  |  | 33.61% | 2.41 |  |  | 66.39% | T.O.O Ms No.55, Dt.16.03.2018 | A-17-05 | 0.007 | 2.41 | -2.403
---- | Augmentation of PTR capacities at 220KV Gachibowli SS & 132KV Malkaram SS | To meet the Industrial, Agriculture and etc., loads | 2018-03-16 | 2019-03-31 | 7.86 | 0.32 | 0 | 0 | 1.65 | 1.16 | 10.99 | [6 empty] | REC 14453 | 6.93 |  |  | 63.06% | 4.06 |  |  | 63.06% | 4.06 |  |  | 36.94% | T.O.O Ms No.56, Dt.16.03.2018 | A-17-06 | 0 | 4.06 | 0
---- | Augmentation of PTR capacities at 220KV Chandrayangutta SS | To meet the Industrial, Agriculture and etc., loads | 2018-04-13 | 2019-03-31 | 5.58 | 0.27 | 0 | 0 | 1.4 | 1 | 8.25 | [6 empty] | REC 14455 | 3.91 |  |  | 47.39% | 4.34 |  |  | 47.39% | 4.34 |  |  | 52.61% | T.O.O Ms No. 78, Dt:13.04.2018 | A-18-01 | 0 | 4.34 | 0
---- | Augmentation of PTR capacities at 132KV Yerraballi ss, 220KV Waddekthapally SS, 132KV Ghanpur SS, 132KV Inavole SS. | To meet the Industrial, Agriculture and etc., loads | 2018-07-18 | 2019-03-31 | 4.61 | 0.21 | 0 | 0 | 1.09 | 0.77 | 6.68 | [6 empty] | REC 14455 | 4.67 |  |  | 69.91% | 2.01 |  |  | 69.91% | 2.01 |  |  | 30.09% | T.O.O Ms No. 152, Dt 18.07.2018 | A-18-02 | 0 | 2.01 | 0
(1): New Scheme; (2): Augmentation of PTR capacities at 132KV RC Puram SS, 220KV Alwal SS, 132KV Kathlapur SS, 132KV Mulkamur SS & 132KV Korutlu SS.; (3): To meet the Industrial, Agriculture and etc., loads; (4): 2018-12-01; (5): 2020-03-31; (6): 6.86; (7): 0.23; (8): 0; (9): 0; (10): 1.17; (11): 0.82; (12): 9.08; (20): 3.05; (23): 33.59%; (24): 2.98; (27): 33.59%; (28): 2.98; (31): 32.82% | 0 | 2.98 | 0
(1): New Scheme; (2): Augmentation of PTR capacities at 132KV Jadcherla SS, 132KV Ramapuram SS, 220KV SS, 132KV Wardhanapet SS, 132KV Inavole SS & 132KV Arempula SS.; (3): To meet the Industrial, Agriculture and etc., loads; (4): 2018-12-01; (5): 2020-03-31; (6): 3.02; (7): 0.1; (8): 0; (9): 0; (10): 0.53; (11): 0.37; (12): 4.02; (20): 1.9; (23): 47.26%; (24): 0.23; (27): 47.26%; (28): 0.23; (31): 5.721% | 0 | 0.23 | 0
(2): Total; (20): 138.99; (24): 109.614; (28): 109.614 | 88.87 | 109.614 | 811.663
---- | Augmentation of PTR capacities at 132KV Chilakalguda SS and 132 KV Hussainsagar | To meet the Industrial, Agriculture and etc., loads | 12.02.2015 | 2019-03-31 | 6.8 | 0.29 | 0 | 0 | 0.12 | 1.1 | 8.31 |  |  | 7.42 |  |  |  | PFC 37203015 | 5.74 |  |  | 69.07% | 5.74 |  |  | 69.07% | 8.31 |  |  | 100% | ( TOO 28 Dt 12-02-2015 ) WBS A-15-02 | A-15-02 | 2.57 | 0 | 2.57 | ( TOO 28 Dt 12-02-2015 )
Total
(1): A-15-08; (2): ERECTION OF 31.5 MVA PTR IN PLACE OF 10/; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): 0.02; (27): #DIV/0!; (28): 0.02; (31): #DIV/0!; (32): Unidentified | 0.02 | 0.02 | 0
(1): A-15-12; (2): Erection of 3rd 31.5 MVA PTR Bay at 132/; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): 0.06; (27): #DIV/0!; (28): 0.06; (31): #DIV/0!; (32): Unidentified | 0.06 | 0.06 | 0
(1): A-15-15; (2): Erection of 3rd 31.5 MVA PTR Bay at 132/; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): 0.11; (27): #DIV/0!; (28): 0.11; (31): #DIV/0!; (32): Unidentified | 0.11 | 0.11 | 0
(1): A-15-16; (2): 3rd 50MVA PTR at Nirmal SS; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): -0.05; (27): #DIV/0!; (28): -0.05; (31): #DIV/0!; (32): Unidentified | -0.05 | -0.05 | 0
(1): A-15-17; (2): 3rd 100MVA PTR at Nirmal; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): 0.09; (27): #DIV/0!; (28): 0.09; (31): #DIV/0!; (32): Unidentified | 0.09 | 0.09 | 0
(1): A-15-18; (2): Erection of 100 MVA PTR in place at 220/; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): 0.11; (27): #DIV/0!; (28): 0.11; (31): #DIV/0!; (32): Unidentified | 0.11 | 0.11 | 0
(1): A-15-19; (2): Dismatling of 10/16MVAPTR-II & Erect.of; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): 0.01; (27): #DIV/0!; (28): 0.01; (31): #DIV/0!; (32): Unidentified | 0.01 | 0.01 | 0
(1): A-15-20; (2): Erection of 3rd 31.5 MVA PTR Bay at 132/; (5): 31.03.2019; (20): 0; (23): #DIV/0!; (24): 0.49; (27): #DIV/0!; (28): 0.49; (31): #DIV/0!; (32): Unidentified | 0.49 | 0.49 | 0
150.06

## Aug 19-20
Revised ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 to FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  |  | This form captures investments as planned and actually incurred
FY: 2019-20 |  |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
PROJECT DETAILS | [5 empty] | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress (Year on Year) |  |  |  | Remarks | Expenditure as on 31.03.2019 by S_ALR_ 87013558 as on 31.03.2019
Project Code* | Project Title | Project Purpose** | Expenditure as on 31.03.2019 | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year | [19 empty] | Gross | Expence | Taxes | Contengency | Base cost
[15 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation |  |  |  |  | 0.1075 | 0.18 | 0.03
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) |  | (34) | (34) | (6) |  |  | Too Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
(1): ----; (2): Erection of 2nd 160MVA PTR in place of 100 at Chandrayangutta SS; (3): To Enhance PTR Capacities of Metro zone to avoid load relief/ Powercuts; (4): 0.03; (5): 22.12.2005; (6): 31.03.2019; (7): 114.46; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): Incl; (13): 114.46; (29): 0.03; (32): 100% | 0.03 | A-05-03
(1): ----; (2): Augmentation of PTR at 132KV SS Ichoda; (4): 0.59; (5): 18.01.2013; (6): 31.03.2019; (7): 0.61; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): Incl; (13): 0.61; (29): 0.59; (32): 100% | 0.59 | A-13-05
(1): ----; (2): Augmentation of PTRs at various EHT SS for extending 9Hrs Rural,Metro Zone; (4): 0.03; (5): 01.05.2015; (6): 31.03.2019; (7): 283.03; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): Incl; (13): 283.03; (29): 0.03; (32): 100% | 3.45 | A-15-08 A-15-19 | 267728
(1): ----; (2): Augmentation of PTR capacities at various Substation Extending 9Hrs Agriculture during daytime Supply in Warangal; (4): 0.874; (5): 01.05.2016; (6): 31.03.2019; (7): 233.75; (8): Incl; (9): Incl; (10): Incl; (11): Incl; (12): Incl; (13): 233.75; (29): 0.874; (32): 100% | 0.874 | A-15-16
0
---- | Augmentation of PTR capacities at132KV Gunrock SS | To meet the Industrial, Agriculture and etc., loads | 2.07 | 14.02.2015 | 2019-03-31 | 3.9 | 0.12 | 0 | 0 | 0.07 | 0.42 | 4.51 | [7 empty] | 2.44 |  | 0 | 54.1% | 2.44 |  |  | 54.1% | 4.51 |  |  | 100% |  | 2.07 | A-15-24
---- | Augmentation of PTR capacities at 220KV Gunrock SS & 220KV Ghanapur SS | To meet the Industrial, Agriculture and etc., loads | 5.44 | 2016-12-08 | 2019-03-31 | 11.83 | 0.4 | 0 | 0 | 0.36 | 1.46 | 14.05 | [7 empty] | 8.61 |  | 0 | 61.28% | 8.61 |  |  | 61.28% | 14.05 |  |  | 100% |  | 5.44 | A-16-10
---- | Augmentation of PTR capacities at 132 KV Malyalapally SS | To meet the Industrial, Agriculture and etc., loads | 0.19 | 2016-12-09 | 2019-03-31 | 4.39 | 0.18 | 0 | 0 | 0.15 | 0.66 | 5.38 |  |  | 4.84 |  |  |  | REC 13979 | 5.19 |  | 0 | 96.47% | 5.19 |  |  | 96.47% | 5.38 |  |  | 100% |  | 0.19 | A-16-09
TST/ TS/ Augmentation of Transformer capacities (24 Hrs. Agricultural supply) / Investment approval No.13/17, 2017-18 | Augmentation of PowerTransformer capacities at various EHT SS in Warangal and Karimnagar Zones | For extending 24 Hrs. Agricultural Supply | 37.07 | 2017-05-20 | 2019-03-31 | 59.91 | 2.2 | 0 | 0 | 2.23 | 7.89 | 72.23 |  |  | 63.13 |  |  |  | PFC:37203017 | 35.16 |  | 0 | 48.68% | 35.16 |  |  | 48.68% | 72.23 |  |  | 100% |  | 37.07 | A-17-01
| Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Metro and Rural Zones | For extending 24 Hrs. Agricultural Supply | 41.92 | 2017-06-02 | 2019-03-31 | 42.15 | 1.67 | 0 | 0 | 1.5 | 5.97 | 51.29 |  |  | 41.32 |  |  |  | PFC:37203017 | 9.37 |  | 0 | 18.27% | 9.37 |  |  | 18.27% | 51.29 |  |  | 100% |  | 41.92 | A-17-02
---- | Augmentation of PTR capacities at 132 KV Manoharabad SS | To meet the Industrial, Agriculture and etc., loads | 2.41 | 2018-03-16 | 2019-03-31 | 2.49 | 0.12 | 0 | 0 | 0.6 | 0.42 | 3.63 | [7 empty] | 1.22 |  | 0 | 33.61% | 1.22 |  |  | 33.61% | 3.63 |  |  | 100% |  | 2.41 | A-17-05
---- | Augmentation of PTR capacities at 220KV Gachibowli SS & 132KV Malkaram SS | To meet the Industrial, Agriculture and etc., loads | 4.06 | 2018-03-16 | 2019-03-31 | 7.86 | 0.32 | 0 | 0 | 1.65 | 1.16 | 10.99 | [7 empty] | 6.93 |  | 0 | 63.06% | 6.93 |  |  | 63.06% | 10.99 |  |  | 100% |  | 4.06 | A-17-06
---- | Augmentation of PTR capacities at 220KV Chandrayangutta SS | To meet the Industrial, Agriculture and etc., loads | 4.34 | 2018-04-13 | 2019-03-31 | 5.58 | 0.27 | 0 | 0 | 1.4 | 1 | 8.25 | [7 empty] | 3.91 |  | 0 | 47.39% | 3.91 |  |  | 47.39% | 8.25 |  |  | 100% |  | 4.34 | A-18-01
---- | Augmentation of PTR capacities at 132KV Yerraballi ss, 220KV Waddekthapally SS, 132KV Ghanpur SS, 132KV Inavole SS. | To meet the Industrial, Agriculture and etc., loads | 2.01 | 2018-07-18 | 2019-03-31 | 4.61 | 0.21 | 0 | 0 | 1.09 | 0.77 | 6.68 | [7 empty] | 4.67 |  | 0 | 69.91% | 4.67 |  |  | 69.91% | 6.68 |  |  | 100% |  | 2.01 | A-18-02
---- | Augmentation of PTR capacities at 132KV RC Puram SS, 220KV Alwal SS, 132KV Kathlapur SS, 132KV Mulkamur SS & 132KV Korutlu SS. | To meet the Industrial, Agriculture and etc., loads | 2.98 | 2018-12-01 | 2020-03-31 | 6.86 | 0.23 | 0 | 0 | 1.17 | 0.82 | 9.08 | [7 empty] | 6.1 |  | 0 | 67.18% | 6.1 |  |  | 67.18% | 9.08 |  |  | 100% |  | 2.98 | A-18-03
---- | Augmentation of PTR capacities at 132KV Jadcherla SS, 132KV Ramapuram SS, 220KV SS, 132KV Wardhanapet SS, 132KV Inavole SS & 132KV Arempula SS. | To meet the Industrial, Agriculture and etc., loads | 0.23 | 2018-12-01 | 2020-03-31 | 3.02 | 0.1 | 0 | 0 | 0.53 | 0.37 | 4.02 | [7 empty] | 3.79 |  | 0 | 94.28% | 3.79 |  |  | 94.28% | 4.02 |  |  | 100% |  | 0.23 | A-18-04
0
(1): New Scheme; (2): Augmentation of PTR Capacities at various 220KV Sub-station; (3): To meet the Industrial, Agriculture and etc., loads; (5): 2019-04-01; (6): 2020-03-31; (7): 9.81; (8): 0.29; (11): 1.82; (12): 1.28; (13): 13.2; (21): 13.2; (23): 0; (24): 100%; (25): 13.2; (28): 100%; (29): 13.2; (32): 100% |  |  | 134.6055 | 13.0655 | 18.54 | 3 | 100
(1): New Scheme; (2): Augmentation of PTR Capacities at various 132KV Sub-station; (3): To meet the Industrial, Agriculture and etc., loads; (5): 2019-04-01; (6): 2020-03-31; (7): 55.07; (8): 1.65; (11): 10.21; (12): 7.19; (13): 74.12; (21): 74.12; (23): 0; (24): 100%; (25): 74.12; (28): 100%; (29): 74.12; (32): 100% |  |  | 134.6055 | 0.097065 | 0.13774 | 0.022287 | 0.74291
(1): New Scheme; (2): Supply and Erection of Capacitor banks at various 220 KV Sub-stations; (3): To improve the Power factor of the EHT SS; (5): 2019-04-01; (6): 2020-03-31; (7): 0.45; (8): 0.01; (11): 0.08; (12): 0.06; (13): 0.6; (21): 0.6; (23): 0; (24): 100%; (25): 0.6; (28): 100%; (29): 0.6; (32): 100% |  |  | 10.64 | 1.03 | 1.47 | 0.24 | 7.9
New Scheme | Supply and Erection of Capacitor banks at various 132KV Sub-stations | To improve the Power factor of the EHT SS |  | 2019-04-01 | 2020-03-31 | 10.29 | 0.31 |  |  | 1.91 | 1.34 | 13.85 | [7 empty] | 13.85 |  | 0 | 100% | 13.85 |  |  | 100% | 13.85 |  |  | 100%
(1): New Scheme; (2): Augmentation of PTR capacities at 220KV Gachibowli SS; (3): To meet the Industrial, Agriculture and etc., loads; (5): 03.07.2019; (6): 03.07.2019; (7): 4.61; (8): 0.14; (11): 0.86; (12): 0.6; (13): 6.21; (21): 6.21; (23): 0; (24): 100%; (25): 6.21; (28): 100%; (29): 6.21; (32): 100% |  | A-19-01 | A-18-01 |  | 0 | 4.34 | 0
(1): Total; (4): 104.244; (21): 195.37; (25): 195.37; (29): 299.614 | 107.664
191.95

## Aug 20 -21
Revised ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 to FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2020-21 |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress (Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year | [17 empty] | Gross | Expence | Taxes | Contengency | Base cost
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation |  |  | 0.1075 | 0.18 | 0.03
New Scheme | Augmentation of PTR Capacities at various 220KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2020-04-01 | 2021-03-31 | 41.06 | 1.23 |  |  | 7.61 | 5.36 | 55.26 | [7 empty] | 55.26 |  |  | 100% | 55.26 |  |  | 100% | 55.26 |  |  | 100%
New Scheme | Augmentation of PTR Capacities at various 132KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2020-04-01 | 2021-03-31 | 40.23 | 1.21 |  |  | 7.46 | 5.26 | 54.16 | [7 empty] | 54.16 |  |  | 100% | 54.16 |  |  | 100% | 54.16 |  |  | 100%
New Scheme | Supply and Erection of Capacitor banks at various 220 KV and 132 KV Sub-stations | To improve the Power factor of the EHT SS | 2020-04-01 | 2021-03-31 | 2.23 | 0.07 |  |  | 0.41 | 0.29 | 3 | [7 empty] | 3 |  |  | 100% | 3 |  |  | 100% | 3 |  |  | 100%
Total | [10 empty] | 112.42 | [7 empty] | 112.42 |  |  |  | 112.42 |  |  |  | 112.42

## Aug 21-22
Revised ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 to FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2021-22 |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress (Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation
New Scheme | Augmentation of PTR Capacities at various 220KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2021-04-01 | 2022-03-31 | 19 | 0.57 |  |  | 3.52 | 2.48 | 25.57 | [7 empty] | 25.57 |  |  | 100% | 25.57 |  |  | 100% | 25.57 |  |  | 100%
New Scheme | Augmentation of PTR Capacities at various 132KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2021-04-01 | 2022-03-31 | 35.58 | 1.07 |  |  | 6.6 | 4.65 | 47.9 | [7 empty] | 47.9 |  |  | 100% | 47.9 |  |  | 100% | 47.9 |  |  | 100%
New Scheme | Supply and Erection of Capacitor banks at various 220 KV and 132 KV Sub-stations | To improve the Power factor of the EHT SS | 2021-04-01 | 2022-03-31 | 4.234 | 0.13 |  |  | 0.79 | 0.55 | 5.704 | [7 empty] | 5.704 |  |  | 100% | 5.704 |  |  | 100% | 5.704 |  |  | 100%
Total | [10 empty] | 79.174 | [7 empty] | 79.174 |  |  |  | 79.174 |  |  |  | 79.174

## Aug 22-23
Revised ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 to FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2022-23 |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress (Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation
New Scheme | Augmentation of PTR Capacities at various 220KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2022-04-01 | 2023-03-31 | 19.9 | 0.6 |  |  | 3.69 | 2.6 | 26.79 | [7 empty] | 26.79 |  |  | 100% | 26.79 |  |  | 100% | 26.79 |  |  | 100%
New Scheme | Augmentation of PTR Capacities at various 132KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2022-04-01 | 2023-03-31 | 32.19 | 0.97 |  |  | 5.97 | 4.21 | 43.34 | [7 empty] | 43.34 |  |  | 100% | 43.34 |  |  | 100% | 43.34 |  |  | 100%
New Scheme | Supply and Erection of Capacitor banks at various 220 KV and 132 KV Sub-stations | To improve the Power factor of the EHT SS | 2022-04-01 | 2023-03-31 | 1.67 | 0.05 |  |  | 0.31 | 0.22 | 2.25 | [7 empty] | 2.25 |  |  | 100% | 2.25 |  |  | 100% | 2.25 |  |  | 100%
Total | [10 empty] | 72.38 | [7 empty] | 72.38 |  |  |  | 72.38 |  |  |  | 72.38

## Aug 23-24
Revised ANNEXURE-I Augmentation of PTRs (For FY:2019-2020 to FY:2023-2024 each year)
Form 1.1d
Investment Plan |  |  | This form captures investments as planned and actually incurred
FY: 2023-24 |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
PROJECT DETAILS |  |  |  |  | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Comulativr Progress (Year on Year) |  |  |  | Remarks
Project Code* | Project Title | Project Purpose** | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[14 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation
New Scheme | Augmentation of PTR Capacities at various 220KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2023-04-01 | 2024-03-31 | 4.98 | 0.15 |  |  | 0.92 | 0.65 | 6.7 | [7 empty] | 6.7 |  |  | 100% | 6.7 |  |  | 100% | 6.7 |  |  | 100%
New Scheme | Augmentation of PTR Capacities at various 132KV Sub-station | To meet the Industrial, Agriculture and etc., loads | 2023-04-01 | 2024-03-31 | 41.2 | 1.24 |  |  | 7.64 | 5.38 | 55.46 | [7 empty] | 55.46 |  |  | 100% | 55.46 |  |  | 100% | 55.46 |  |  | 100%
New Scheme | Supply and Erection of Capacitor banks at various 220 KV and 132 KV Sub-stations | To improve the Power factor of the EHT SS | 2023-04-01 | 2024-03-31 | 7.9 | 0.24 |  |  | 1.47 | 1.03 | 10.64 | [7 empty] | 10.64 |  |  | 100% | 10.64 |  |  | 100% | 10.64 |  |  | 100%
Total | [10 empty] | 72.8 | [7 empty] | 72.8 |  |  |  | 72.8 |  |  |  | 72.8
| Previous |  |  | Modified
19-20 | 203.41 | 195.37 |  | 101.77
20-21 | 154.8 | 112.42 |  | 112.42
21-22 | 137.63 | 79.17 |  | 79.17
22-23 | 115.64 | 72.38 |  | 72.38
23-24 | 117.86 | 72.8 |  | 72.8
| 729.34 | 532.14 |  | 438.54

## Resource Plan 19-24
220 KV Substations: Augmentation of Power Transformers
Sl. No. | Name of the substation at which augmentation of Power Transformer is proposed | Present capacity of Power Transformer (in MVA) | After Augmentation of Power Transformer capacity (in MVA) | Estimated cost (in Rs. Crores) including cost of erection
2019-20 |  |  |  |  | New | released
1 | 400 KV SS Suryapet | 2×100 | 3×100 | 5 | 100 | 0
2 | 220 KV SS Gangaram | 1x31.5+5x50 | 6x50 | 2.5 | 50 | 31.5
3 | 220 KV SS Salivagu | 2x31.5 | 1x31.5+1x50 | 2.5 | 50 | 31.5
4 | 220 KV SS Siddipet | 2x100+1x160 | 1x100+2x160 | 5.135 | 160 | 100
5 | 220 KV SS Nagole | 2x100 | 1x100+ 1x160 | 4.1
6 | 220 KV SS Jagtial | 2x100+1x160 | 1x100+2x160 | 4.2
7 | 220 KV SS Sircilla | 3x100 | 1x100+2x160 | 8.4
8 | 220 KV SS Huzurabad | 2x100 | 3x100 | 4.2
9 | 220 KV SS Parigi | 2 x 100 | 1x100+1x160 | 5
10 | 220 KV SS Bhootpur | 1x16+1x50 | 1x31.5+1x50 | 2
11 | 220 KV SS Kosigi | 1x16+1x31.5 | 2x31.5 | 2
| Sub Total |  |  | 45.035
2020-21
1 | 220 KV SS Kalwakurthy | 1x100+2x160 | 3x160 | 5.135
2 | 220 KV SS Jagtial | 1x100+2x160 | 3x160 | 4.2
3 | 220 KV SS Sircilla | 1x100+2x160 | 3x160 | 4.2
4 | 220 KV SS Bhongir | 3x100 | 2x100+1x160 | 4.99
5 | 220 KV SS Miryalaguda | 2×80+2×100+2×160 | 2×80+1×100+3×160 | 5.135
6 | 220 KV SS Salivagu | 1x31.5+1x50 | 2x50 | 2.5
7 | 220 KV SS Siddipet | 1x100+ 2x160 | 3x160 | 5.135
8 | 220 KV SS Yeddumailaram | 1x100+ 2x160 | 3x160 | 5.135
9 | 220 KV SS Sadashivapet | 1x100+1x160 | 2x160 | 5.135
10 | 220 KV SS Hayathnagar | 2x50 | 3x50 | 3.2
11 | 220 KV SS Mandamarri | 3x100 | 2x100+1x160 | 5.135
12 | 220 KV SS Malyalapally | 1x100+1x160 | 2x160 | 6
13 | 220 KV SS Manthani | 2x100 | 2x100+1x160 | 7
| Sub Total |  |  | 62.9
2021-22
1 | 220 KV SS Jurala | 3x100 | 2x100+1x160 | 5.135
2 | 220 KV SS Narketpally | 2x100+ 2x160 | 1x100+3x160 | 11.66
3 | 220 KV SS Miryalaguda | 2×80+1×100+3×160 | 2×80+4×160 | 5.135
4 | 220 KV SS Kondamallepally | 4×100 | 3×100+ 1×160 | 5.2
5 | 400 KV SS Suryapet | 3×100 | 3×160 | 10
6 | 220 KV SS Bheemgal | 1x100 +1x160 | 2x160 | 4.96
7 | 220 KV SS Nirmal | 2x100+1x160 | 1x100+2x160 | 5.135
| Sub Total |  |  | 47.225
2022-23
1 | 220 KV SS Jurala | 2x100+1x160 | 1x100+2x160 | 5.135
2 | 220 KV SS Gunrock | 2x160 | 3x160 | 8.6545
3 | 220 KV GIS Erragadda | 2x160 | 3x160 | 3.8697
4 | 220 KV SS Bhongir | 2x100+1x160 | 1x100+2x160 | 8.32
5 | 220 KV SS Nagole | 1x100+1x160 | 2x160 | 4.1
6 | 220 KV SS Shamshabad | 3x100 | 2x100+1x160 | 4.1
7 | 220 KV SS Mandamarri | 2x100+1x160 | 1x100+2x160 | 5.135
| Sub Total |  |  | 39.3141
2023-24
1 | 220 KV SS Narketpally | 1x100+3x160 | 4x160 | 13.33
2 | 220 KV SS Shivarampally | 2x100+2x160 | 1x100+3x160 | 4.1
3 | 220 KV SS Shamshabad | 2x50 | 1x50+1x80 | 2.6
| Sub Total |  |  | 20.03
| Grand Total |  |  | 214.5041
220 KV Substations : Capacitor Bank Details
Sl.No | Name of the substation at which Capacitor is proposed |  | Capacity of Capacitor in MVAR | Estimated cost (in Rs. Crores) including cost of erection
2019-20
1 | 220 KV SS Kamareddy |  | 14.4 | 0.7
2 | 220 KV SS Salivagu |  | 7.2 | 0.2
3 | 220 KV SS Nagaram |  | 7.2 | 0.2
4 | 220 KV SS Bheemghanpur |  | 7.2 | 0.2
| Total |  | 36 | 1.3
132 KV Substations Augmentation of Power Transformers
Sl. No. | Name of the substation at which augmentation of Power Transformer is proposed | Present capacity of Power Transformer (in MVA) | After Augmentation of Power Transformer capacity (in MVA) | Estimated cost (in Rs. Crores) including cost of erection
2019-20
1 | 132 KV SS Darmasagar | 1x31.5 | 1x50 | 2.5
2 | 132 KV SS Balanagar | 3x50 | 2x50+1x80 | 3
3 | 132 KV SS Jadcherla | 2x31.5 | 1x31.5+1x50 | 2.5
4 | 132 KV SS Kalwakurthy | 1x31.5+2x50 | 1x31.5+1x50+1x80 | 3
5 | 132 KV SS Thirumalaipally | 2x10/16+1x31.5 | 1x10/16+2x31.5 | 2
6 | 132 KV SS Makthal | 2x31.5+1x50 | 1x31.5+2x50 | 2.5
7 | 132 KV SS Amarchintha | 1x10/16+1x31.5 | 2x31.5 | 2
8 | 132 KV SS Mudhole | 2x10/16 | 1x10/16+1x31.5 | 2
9 | 132 KV SS Utnoor | 2x10/16 | 1x10/16+1x 31.5 | 2
10 | 132 KV SS Gangadhara | 1x16+1x31.5 | 2x31.5 | 2
11 | 132 KV SS Husnabad | 2x31.5+1x50 | 1x31.5+2x50 | 2.5
12 | 132 KV SS Huzurabad | 2x31.5 | 1x31.5+1x50 | 2.5
13 | 132 KV SS Pudur | 1x31.5+1x50 | 2x50 | 2.5
14 | 132 KV SS Yellareddypet | 1x25+2x31.5 | 3x31.5 | 2
15 | 132 KV SS Dharmaram | 2x31.5 | 1x31.5+1x50 | 2.5
16 | 132 KV SS Manakondoor | 1x31.5+1x50 | 2x50 | 2.5
17 | 132 KV SS Kataram | 1x31.5+1x50 | 1x31.5+2x50 | 3
18 | 132 KV SS RTS-B | 2x31.5 | 1x31.5+1x50 | 2.5
19 | 132 KV SS Choutuppal | 2x50 | 1x50+1x80 | 3
20 | 132 KV SS Wadapally | 1×15+ 1×31.5 | 2×31.5 | 2
21 | 132 KV SS Ramapuram | 1×16+1x31.5 | 2x50 | 6
22 | 132 KV SS Suryapet | 2x80 | 1x50+2x80 | 3
23 | 132 KV SS Kodada | 2x50 | 3x50 | 3
24 | 132 KV SS Munagala | 3x10/16 | 3x50 | 9
25 | 132 KV SWS Vepala Singaram | - | 2x31.5 | 4
26 | 132 KV SS Geesugonda | 2x31.5 | 1x31.5+1x50 | 2.5
27 | 132 KV SS Wardhannapet | 1x31.5+1x50 | 2x50 | 2.5
28 | 132 KV SS Ghanpur | 1x31.5+1x50 | 2x50 | 2.5
29 | 132 KV SS Musthyal | 2x50 | 1x31.5+2x50 | 2.5
30 | 132 KV SS Inavole | 2x16 | 2x31.5 | 2
31 | 132 KV SS Mulugu | 3x31.5 | 1x31.5+2x50 | 2.5
32 | 132 KV SS Kamalapur | 2x31.5 | 2x50 | 2.5
33 | 132 KV SS Manoharabad | 1x50+1x80 | 2x80 | 3
34 | 132 KV SS Bollaram | 3x31.5+1x50+1x80 | 1x31.5+3x50+1x80 | 6.12
35 | 132 KV SS Turkayamjal | 1x31.5+1x50 | 1x50+1x80 | 4
36 | 132 KV SS Mamidipally | 1x31.5+1x50 | 1x50+1x80 | 4
37 | 220 KV SS Bonguluru | 1x50 | 2x50 | 2.1
38 | 220 KV SS Shamshabad | 1×31.5+1×50+3×100 | 2×50+3×100 | 2.1
39 | 132 KV SS Nellikuduru | 1x16+1x31.5 | 2x31.5 | 2
40 | 132 KV SS Guduru | 1x16+1x31.5 | 2x31.5 | 2
41 | 132 KV SS Palakurthy | 2x50 | 3x50 | 5
42 | 132 KV SS Chityala | 2x50 | 3x50 | 5
43 | 132 KV SS Chelpur | 1x31.5+1x50 | 2x50 | 2
44 | 220 KV SS Nirmal | 1x31.5+1x50 | 1x31.5+2x50 | 2.5
45 | 132 KV SS Burugupally | 1x16+1x31.5 | 2x31.5 | 2
| Sub Total |  |  | 132.32
2020-21
1 | 132 KV SS Jadcherla | 1x31.5+1x50 | 2x50 | 2.5
2 | 132 KV SS Achampet | 2x50 | 1x50+1x80 | 3
3 | 132 KV SS Thirumalaipally | 1x10/16+2x31.5 | 3x31.5 | 2
4 | 132 KV SS Chinnamaroor | 2x31.5 | 1x31.5+1x50 | 2.5
5 | 132 KV SS Khila Ghanapur | 2x31.5 | 1x31.5+1x50 | 2.5
6 | 132 KV SS Makthal | 1x31.5+2x50 | 3x50 | 2.5
7 | 132 KV SS Ieeja | 3x31.5 | 2x31.5+1x50 | 2.5
8 | 132 KV SS Alampur | 2x31.5 | 1x31.5+1x 50 | 2.5
9 | 132 KV SS Ichoda | 3x10/16 | 2x10/16+1x31.5 | 2
10 | 132 KV SS Raikal | 1x16+1x31.5 | 2x31.5 | 2
11 | 132 KV SS Munugode | 1x10/16+31.5 | 2x31.5 | 2
12 | 132 KV SS Yerrabelly | 1x16+1x31.5 | 1x31.5+1x50 | 2.2
13 | 132 KV SS Kanagal | 2x50 | 1x50+1x80 | 3
14 | 220 KV SS Narketpally | 1x31.5+1x50 | 2x50 | 5
15 | 132 KV SS Aitipamula | 1x31.5+1x50 | 2x50 | 5
16 | 220 KV SS Bhongir | 2x50 | 1x50+1x80 | 6
17 | 132 KV SS Wadapally | 2×31.5 | 1×31.5+1×50 | 2.4
18 | 132 KV SS Haliya | 2×50 | 1×50+1×80 | 3
19 | 132 KV SS Nizamabad | 3x50 | 2x50 + 1x80 | 2.7
20 | 132 KV SS Nandipet | 2x50 | 1x50 + 1x80 | 2.7
21 | 132 KV SS Jakora | 2x50 | 1x50 + 1x80 | 2.7
22 | 132 KV SS Domakonda | 1 x 31.5 + 1x50 | 2x50 | 2.45
23 | 132 KV SS Nellikuduru | 2x31.5 | 1x31.5+1x50 | 2.5
24 | 132 KV SS Jangaon | 1x31.5+1x50 | 2x50 | 2.5
25 | 132 KV SS Nekkonda | 1x31.5+1x50 | 2x50 | 2.5
26 | 132 KV SS Inavole | 2x31.5 | 1x31.5+1x50 | 2.5
27 | 132 KV SS Mulugu | 1x31.5+2x50 | 3x50 | 2.5
28 | 132 KV SS Chegunta | 1x50+1x80 | 2x80 | 3
29 | 220 KV SS Nagole | 1x31.5+1x80 | 2x80 | 4
30 | 220 KV SS Ghanapur | 1x31.5+1x80+3x160 | 2x80+3x160 | 4
31 | 220 KV SS Fabcity | 2x50+2x100 | 1 x50+1x80+2x100 | 2.6
| Sub Total |  |  | 89.25
2021-22
1 | 132 KV SS Chinnamaroor | 1x31.5+1x50 | 2x50 | 2.5
2 | 132 KV SS Khila Ghanapur | 1x31.5+1x50 | 2x50 | 2.5
3 | 220 KV SS Singotam | 2x31.5 | 1x31.5+1x50 | 2.5
4 | 132 KV SS Marikal | 3x31.5 | 2x31.5+1x50 | 2.5
5 | 132 KV SS Adilabad | 3x31.5 | 2x31.5+1x50 | 2.5
6 | 220 KV SS Nirmal | 1x31.5+2x50 | 3x50 | 2.5
7 | 132 KV SS Asifabad | 2x10/16 | 2x16+1x31.5 | 2
8 | 132 KV SS Bellampally | 2x31.5 | 1x31.5+1x50 | 2.5
9 | 132 KV SS Chennur | 2x31.5 | 1x31.5+1x 50 | 2.5
10 | 132 KV SS Mancherial | 1x31.5+1x50 | 2x50 | 2.5
11 | 132 KV SS Luxettipet | 1x10/16+1x31.5 | 2x31.5 | 2
12 | 132 KV SS Nalgonda | 1x31.5+1x50+1x80 | 2x50+1x80 | 3
13 | 132 KV SS Ramannapet | 3x50 | 2x50+1x80 | 3
14 | 132 KV SS Bibinagar | 1x50+1x80 | 2x80 | 1.5
15 | 132 KV SS Kolanpaka | 2x50+1x80 | 1x50+2x80 | 3
16 | 132 KV SS Mothkur | 2x50 | 1×50+1×80 | 3
17 | 132 KV SS Dirsincherla | 2×50 | 1×50+1×80 | 3
18 | 132 KV SS Kondamallepally | 1x31.5+1x50+1x80 | 2x50+1x80 | 2.4
19 | 132 KV SS Suryapet | 1x50+2x80 | 3x80 | 5
20 | 132 KV SS Thungathurthy | 2x50 | 3x50 | 3
21 | 132 KV SS Mattampally | 2x50 | 3x50 | 3
22 | 132 KV SS Kamareddy | 1x31.5 +1x50 | 2x50 | 2.45
23 | 132 KV SS Dasnagar | 1x31.5 +1x50 | 2x50 | 2.4
24 | 132 KV SS Dornakal | 2x10/16 | 1x16+1x31.5 | 2
25 | 132 KV SS Narmetta | 2x31.5 | 1x31.5+1x50 | 2.5
26 | 132 KV SS Inavole | 1x31.5+1x50 | 2x50 | 2.5
27 | 132 KV SS Doulthbad | 2x10/16 | 1x10/16+1x31.5 | 2
28 | 132 KV SS Kandi | 3x50 | 3x80 | 9
29 | 132 KV SS Ibrahimpatnam | 2x50 | 1×50+1×80 | 2.6
| Sub Total |  |  | 81.85
2022-23
1 | 220 KV SS Singotam | 1x31.5+1x50 | 2x50 | 2.5
2 | 132 KV SS Sirpur Kagaznagar | 1x10/16+1x31.5 | 1x31.5+1x50 | 2.5
3 | 132 KV SS Munugode | 2x31.5 | 1x31.5+1x 50 | 3.5
4 | 132 KV SS Yerrabelly | 1x31.5+1x50 | 2x50 | 6
5 | 220 KV SS Narketpally | 2x50 | 1×50+1×80 | 5
6 | 132 KV SS Aitipamula | 2x50 | 1×50+1×80 | 5
7 | 132 KV SS Shaligowraram | 1×50+1×80 | 2x80 | 3
8 | 132 KV SS Choutuppal | 1x50+1x80 | 2x80 | 3
9 | 220 KV SS Bhongir | 1x50+1x80 | 2x80 | 3
10 | 132 KV SS Dirsincherla | 1×50+1x80 | 2×80 | 3
11 | 132 KV SS Madgulapally | 1×50+1×80 | 2×80 | 3
12 | 132 KV SS Guntipally | 1x10/16+2x31.5 | 3×31.5 | 2
13 | 132 KV SS Sirikonda | 1x31.5 +1x50 | 2x50 | 2.4
14 | 132 KV SS Nellikuduru | 1x31.5+1x50 | 2x50 | 2.5
15 | 220 KV SS Warangal | 1x50+2x80 | 3x80 | 3
16 | 132 KV SS Palamakula | 2x31.5 | 1x31.5+1x 50 | 2.04
17 | 132 KV SS Pashamailaram | 3x50 | 3x80 | 9
18 | 132 KV SS Sadasivapet | 2x31.5+1x80 | 1x31.5+2x80 | 3
19 | 132 KV SS Peddashankarampet | 2x31.5 | 1x 31.5+1x50 | 2.04
20 | 132 KV SS Mamidipally | 1x50+1x80 | 2x80 | 2.6
21 | 132 KV SS Takkalapally | 2x31.5 | 1x80+1x31.5 | 4
| Sub Total |  |  | 72.08
2023-24
1 | 132 KV SS Mudhole | 1x10/16+1x31.5 | 2x31.5 | 2
2 | 132 KV SS Nalgonda | 2×50+1×80 | 1×50+2×80 | 3
3 | 132 KV SS Kanagal | 1x50+1x80 | 2x80 | 3
4 | 132 KV SS Ramannapet | 2x50+1x80 | 1×50+2×80 | 6
5 | 132 KV SS Kolanpaka | 1×50+2×80 | 3x80 | 5
6 | 132 KV SS Mothkur | 1x50+1x80 | 2x80 | 3
7 | 132 KV SS Marriguda | 2×50 | 3×50 | 2.4
8 | 132 KV SS Wadapally | 1×31.5+1x50 | 1×31.5+1×80 | 3
9 | 132 KV SS Banswada | 1x31.5+1x50 | 2x50 | 2.4
10 | 132 KV SS Yellandu | 1x31.5+1x50 | 2x50 | 2.5
11 | 132 KV SS Tunikibollaram | 2x31.5 | 1x31.5+1x50 | 2.04
12 | 132 KV SS Singur | 2x31.5 | 2x50 | 4.08
13 | 132 KV SS Ramayampet | 2x31.5 | 1x31.5+1x50 | 2.04
14 | 132 KV SS Medak | 2x50 | 2x80 | 6
15 | 132 KV SS Gunrock | 1×50+2×80 | 2×50+2×80 | 4.51
16 | 132 KV SS Jubilee Hills | 1x10/16+1x50+2x80 | 2×50+2×80 | 4.0185
17 | 132 KV SS Vikarabad | 2x16 | 1x16+1x31.5 | 2.5
18 | 132 KV SS IDPL | 2x50 | 2x80 | 6
19 | 132 KV SS Chintal | 2x50 | 2x80 | 6
20 | 132 KV SS Medchal | 3x50 | 3x80 | 9
21 | 132 KV SS RC Puram | 2x10/16+3x50 | 2x10/16+2x50+1x80 | 3
22 | 220 KV SS Shivarampally | 2×50+3×80 | 1×50+4×80 | 2.6
| Sub Total |  |  | 84.0885
| Grand Total |  |  | 459.5885
132 KV Substations Capacitor Bank Details
Sl. No. | Name of the substation at which Capacitor is proposed |  | Capacity of Capacitor in MVAR | Estimated cost (Rs. Crores) including cost of erection
2019-2020
1 | 132 KV SS Pudur |  | 5 | 0.25
2 | 132 KV SS Munugode |  | 7.2 | 2
3 | 132 KV SS Yerrabelly |  | 7.2 | 2
4 | 132 KV SS Aitipamula |  | 10 | 1.2
5 | 132 KV SS Choutuppal |  | 10 | 1.2
6 | 132 KV SS Bibinagar |  | 1x10+1x5 | 2
7 | 132 KV SS Dirsincherla |  | 5 | 0.15
8 | 132 KV SS Wadapally |  | 5 | 0.15
9 | 132 KV SS Madgulapally |  | 5 | 0.15
10 | 132 KV SS Guntipally |  | 2×10 | 0.6
11 | 132 KV SS Marriguda |  | 7.5 | 0.2
12 | 132 KV SS Haliya |  | 7.2 | 0.2
13 | 132 KV SS Ramapuram |  | 2x7.5 | 2
14 | 132 KV SS Suryapet |  | 2x10 | 2.4
15 | 132 KV SS Kodada |  | 1x10 | 1.2
16 | 132 KV SS Thungathurthy |  | 1x10 | 1.2
17 | 132 KV SS Mattampally |  | 2x10 | 2.4
18 | 132 KV SS Munagala |  | 2x10 | 2.4
19 | 132 KV SS Vepala singaram |  | 2x7.5 | 2
20 | 132 KV SS Dasnagar |  | 7.2 | 0.25
21 | 220 KV SS Warangal |  | 14.4 | 0.4
22 | 132 KV SS Narsampet |  | 7.2 | 0.2
23 | 132 KV SS Geesugonda |  | 7.2 | 0.2
|  |  | Sub-total | 24.75
2020-21
1 | 132 KV SS Kanagal |  | 7.2 | 1
2 | 220 KV SS Bhongir |  | 10 | 0.4
3 | 132 KV SS Banswada |  | 7.2 | 0.25
4 | 132 KV SS Ayyagaripally |  | 7.2 | 0.2
5 | 132 KV SS Guduru |  | 7.2 | 0.2
6 | 220 KV SS Waddekothapally |  | 14.4 | 0.4
7 | 132 KV SS Waddepally |  | 7.2 | 0.2
|  |  | Sub-total | 2.65
2021-22
1 | 220 KV SS Narketpally |  | 7.2 | 1
2 | 132 KV SS Shaligowraram |  | 10 | 1.2
3 | 132 KV SS Ramannapet |  | 7.2 | 1
4 | 132 KV SS Bibinagar |  | 10 | 2.4
5 | 132 KV SS Mothkur |  | 7.2 | 1
6 | 132 KV SS Lingampet |  | 7.2 | 0.25
7 | 132 KV SS Armoor |  | 7.2 | 0.25
8 | 132 KV SS Sirikonda |  | 7.2 | 0.25
9 | 132 KV SS Dornakal |  | 7.2 | 0.2
10 | 132 KV SS Peddanagaram |  | 7.2 | 0.2
11 | 132 KV SS Wardhannapet |  | 7.2 | 0.2
12 | 132 KV SS Nellikuduru |  | 7.2 | 0.2
13 | 132 KV SS Jangaon |  | 7.2 | 0.2
14 | 132 KV SS Narmetta |  | 7.2 | 0.2
|  |  | Sub-total | 8.55
2022-23
1 | 132 KV SS Munugode |  | 7.2 | 1
2 | 132 KV SS Yerrabelly |  | 7.2 | 1
3 | 132 KV SS Aitipamula |  | 7.2 | 1
4 | 132 KV SS Morthad |  | 7.2 | 0.25
5 | 132 KV SS Ghanpur |  | 7.2 | 0.2
6 | 132 KV SS Chityala |  | 7.2 | 0.2
7 | 132 KV SS Mulugu |  | 7.2 | 0.2
8 | 132 KV SS Raghunathpally |  | 7.2 | 0.2
9 | 132 KV SS Palakurthy |  | 7.2 | 0.2
|  |  | Sub-total | 4.25
2023-24
1 | 132 KV SS Kanagal |  | 7.2 | 1
2 | 220 KV SS Narketpally |  | 7.2 | 1
3 | 132 KV SS Habsipur |  | 10 | 0.2988
4 | 132 KV SS Tunikibollaram |  | 10 | 0.2988
5 | 132 KV SS Palamakula |  | 10 | 0.2988
6 | 132 KV SS Angadikistapur |  | 5 | 0.15
7 | 132 KV SS Duddeda |  | 5 | 0.15
8 | 132 KV SS Doulthbad |  | 5 | 0.15
9 | 132 KV SS Chandulapur |  | 5 | 0.15
10 | 132 KV SS Sadasivapet |  | 5 | 0.15
11 | 132 KV SS Zaheerabad |  | 10 | 0.2988
12 | 132 KV SS Jogipet |  | 10 | 0.2988
13 | 132 KV SS Narayanakhed |  | 5 | 0.15
14 | 132 KV SS Peddashankarampet |  | 10 | 0.2988
15 | 132 KV SS Minpur |  | 30 | 0.7
16 | 132 KV SS Narsapur |  | 10 | 0.2988
17 | 132 KV SS Kandi |  | 10 | 0.2988
18 | 132 KV SS Kosigi |  | 7.2 | 0.2
19 | 132 KV SS Alwal |  | 7.2 | 0.2
20 | 132 KV SS Jadcherla |  | 7.2 | 0.2
21 | 132 KV SS Midjil |  | 7.2 | 0.2
22 | 132 KV SS Madugula |  | 7.2 | 0.2
23 | 132 KV SS Achampet |  | 7.2 | 0.2
24 | 132 KV SS Narayanpet |  | 7.2 | 0.2
25 | 132 KV SS Marikal |  | 7.2 | 0.2
26 | 132 KV SS Maddur |  | 7.2 | 0.2
27 | 132 KV SS Srirangapur |  | 7.2 | 0.2
28 | 132 KV SS Makthal |  | 7.2 | 0.2
29 | 132 KV SS Chinnamaroor |  | 7.2 | 0.2
30 | 132 KV SS Thirumalaipally |  | 7.2 | 0.2
31 | 132 KV SS Amarchintha |  | 7.2 | 0.2
32 | 132 KV SS Alampur |  | 7.2 | 0.2
33 | 132 KV SS Gadwal |  | 3x7.2 | 0.6
34 | 132 KV SS Burugupally |  | 10+5 | 0.8
35 | 132 KV SS Mudhole |  | 5 | 0.4
36 | 132 KV SS Ichoda |  | 7.2 | 0.4
37 | 132 KV SS Utnoor |  | 7.2 | 0.4
38 | 132 KV SS Khanpur |  | 7.2 | 0.4
39 | 132 KV SS Asifabad |  | 7.2 | 0.2
40 | 132 KV SS Chennur |  | 7.2 | 0.2
42 | 132 KV SS Luxettipet |  | 7.2 | 0.2
43 | 132 KV SS Sirpur Kagaznagar |  | 7.2 | 0.2
44 | 132 KV SS Thallada |  | 7.2 | 0.2
45 | 132 KV SS Bhadrachalam |  | 7.2 | 0.2
46 | 132 KV SS Vikarabad |  | 5 | 0.15
47 | 132 KV SS Inavole |  | 7.2 | 0.2
48 | 132 KV SS Dharmasagar |  | 7.2 | 0.2
|  |  | Sub Total | 13.7404
|  |  | Grand Total | 53.9404

## Sheet1
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## FUNDING-Tied-up 22032017
Funding to be tied up for Augmentation schemes
Sl. No. | Scheme code | Description of work | T.O.O.No & Date (With amounts) | T.O.O Amount (Rs. In Lakhs) | Unit | Remarks | Funding requested U.O Dt: | Loan from | Loan No. | Remarks/ Amount sanctioned |  | Existing PTRs Capacity (in MVA) | Proposed Enhancement of PTRs capacity (in MVA) | 10.02.2018 status
36 |  | 220KV SS Shivarampally | 23, Dt.28.01.2014 | 493 |  | Augmentation of PTR capacity
37 |  | 132KV SS Shapurnagar |  | 256 |  | Augmentation of PTR capacity
38 |  | 132Kv SS Parigi |  | 258 |  | Augmentation of PTR capacity
39 |  | 132KV SS Gunrock |  | 325 |  | Augmentation of PTR capacity
40 |  | 220KV SS Gachibowli |  | 409 |  | Augmentation of PTR capacity
41 |  | 132KV SS Rompicherla |  | 142 |  | Augmentation of PTR capacity
1 | AG15TOO040 | Augmentation of PTR capacity at 220KV SS Narketpally (160MVA) | 40, Dt.25.02.2015 (520 lakhs) | 520 | 5112, 3600 | Under 9 hrs. Agl. scheme | U.O No. 450 / 2015, 17.10.2015 |  |  |  |  | 1x160 + 2x100 | 2x160 + 1x100 | 2x160 + 2x100 |  | over
2 | AG15TOO040 | Augmentation of PTR capacity at 132KV SS Choutuppal (50MVA) | 40, Dt.25.02.2015 (228 lakhs) | 228 | 5112 | Under 9 hrs. Agl. scheme | U.O No. 450 / 2015, 17.10.2015 |  |  |  |  | 2x31.5 | 1x50 + 1x31.5 | 2x50 |  | over
3 | AG15TOO057 | Augmentation of PTR capacity at 132KV SS Kodada (2x50MVA) | 57, Dt.26.03.2015 (422 lakhs) | 422 | 5112 | Under 9 hrs. Agl. scheme | U.O No. 450 / 2015, 17.10.2015 |  |  |  |  | 2x31.5 | 2X50 | 2X50 |  | over
4 | AG15TOO057 | Augmentation of PTR capacity at 132KV SS Khammam (50MVA) | 57, Dt.26.03.2015 (201 lakhs) | 201 | 5121 | Under 9 hrs. Agl. scheme | U.O No. 450 / 2015, 17.10.2015 |  |  |  |  | 2X50+1X31.5 | 3x50 | 3X50+ 1X31.5 |  | over
| AG15TOO057 | Augmentation of PTR capacity at 132KV SS Waddepally (50MVA) | 57, Dt.26.03.2015 (229 lakhs) | 229 | Funding not required and as it is covered in the TOO 82, Dt:01.05.2015 | [6 empty] | 2X31.5 | 1x50+1x31.5 | 2X50 --- 1 No. 50 MVA i.e 3rd given to mustyal |  | over
5 | A-15-05.AG15TOO082 | Aug of PTRs for providing 9Hrs.Agl supply in METRO & RURAL Zones | 82,01.05.2015 (28303.46 Lakhs) | 28303.46 |  | Under 9 hrs. Agl. scheme | As per TOO | REC | 9497 | 25473.11 Lakhs |  |  |  | All Charged |  | over
6 | A-15-06.AG15TOO083 | Aug of PTRs for providing 9Hrs.Agl supply in WARANGAL Zone | 83,01.05.2015 (23375.28Lakhs) | 23375.28 |  | Under 9 hrs. Agl. scheme | As per TOO | REC | 9496 | 21037.75 Lakhs |  |  |  | All Charged |  | over
7 | A-15-07.AG15TOO114 | Augmentation of Transformer capacities at 220KV SS Narketpally, 220KV SS Konda Mallepally & 220KV SS Miryalaguda for extending 9 Hrs. Agl. supply during day time. | 114, Dt.02.07.2015 (1135.74 lakhs) | 378.58 | 5112 | Under 9 hrs. Agl. scheme | U.O No. 450 / 2015, 17.10.2015 | PFC | 37203015 / March 2017 | 10.14 Crores |  |  |  | All Charged |  | over
8 |  |  |  | 378.58 | 5112 | Under 9 hrs. Agl. scheme | [7 empty] | All Charged |  | over
9 |  |  |  | 378.58 | 5112 | Under 9 hrs. Agl. scheme | [7 empty] | All Charged |  | over
10 | AG15TOO115 | Augmentation of Transformer capacities at 220KV SS Dichpally for extending 9 Hrs. Agl. supply during day time. | 115, Dt.02.07.2015 (378.58 lakhs) | 378.58 | 5106 | Under 9 hrs. Agl. scheme | U.O No. 450 / 2015, 17.10.2015 | [6 empty] | All Charged |  | over
11 | A-15-04.AG15TOO071 | Augmentation of PTR capacity at 132KV SS Chintal (50MVA) | 71, Dt.15.04.2015 (201 lakhs) | 201 | 5108 | Augmentation of Transformer capacities in GHMC area | U.O No. 450 / 2015, 17.10.2015 | PFC | 37203015 / March 2017 | 3.70 Crores | 1X50+1X31.5 | 2x50 |  | 2X50 |  | over
12 | A-15-04.AG15TOO071 | Augmentation of PTR capacity at 132KV SS Jubilee Hills (31.5MVA) | 71, Dt.15.04.2015 (214 lakhs) | 214 | 5108 | Augmentation of Transformer capacities in GHMC area | U.O No. 450 / 2015, 17.10.2015 | PFC | 37203015 / March 2017 |  | 2x80 + 1x50 + 1x10/16MVA (132/11KV) | 2x80 + 1x50+ 1x31.5MVA (132/33KV) |  | 2x80+1x50+1x10/16 (132/11KV) | 2x80+2x50 | To be covered | Under 24 Hrs. again added
13 | A-15-02.AG15TOO028 | Augmentation of PTR capacity at 132KV SS Hussainsagar (80MVA) | 28, Dt.12.02.2015 (277 lakhs) | 277 | 5108 | Augmentation of Transformer capacities in GHMC area | U.O No. 450 / 2015, 17.10.2015 | PFC | 37203015 / March 2017 | 7.42Crores | 1X80+1X50 | 2x80 |  | 2x80 |  | over
14 | A-15-02.AG15TOO028 | Augmentation of PTR capacity at 132KV SS Chilakalguda (2x80MVA) | 28, Dt.12.02.2015 (554 lakhs) | 554 | 5108 | Augmentation of Transformer capacities in GHMC area | U.O No. 450 / 2015, 17.10.2015 | PFC | 37203015 / March 2017 |  | 2x50 | 2x80 |  | 80+50 |  | To be covered
15 | A-15-09.AG15TOO216 | Augmentation of PTR capacity at 132KV SS Khammam (3x50+1x31.5MVA) | 216, Dt.20.11.2015 (201 lakhs) | 201 | 5121 | Under 9 hrs. Agl. scheme | U.O No. 598 / 2016, 03.02.2016 | PFC | 37203015 / March 2017 | 1.79 Crores | 3x50 | 3x50 +1x31.5 |  | 3X50+ 1X31.5 |  | over
16 | A-16-02.AG16TOO024 | Augmentation of PTR capacity at 220KV SS Moulali (80MVA) | 24, Dt.16.02.2016 (515 lakhs) | 515 | 5108 | Augmentation of Transformer capacities in GHMC area | U.O No. 669 / 2016, 10.03.2016 | PFC | 37203015 / March 2017 | 10.27 Crores | 2X80+ 1X50 | 3x80+1x50 |  | 3x80+1x31.5 |  | To be covered |  | 463.5 | 51.5
17 | A-16-02.AG16TOO024 | Augmentation of PTR capacity at 220KV SS Sivarampally (80MVA) | 24, Dt.16.02.2016 (636 lakhs) | 636 | 5108 | Augmentation of Transformer capacities in GHMC area |  | PFC | 37203015 / March 2017 |  | 2x80+ 2x50 | 3x80+2x50 |  | 3x80+2x50 |  | over | Under 24 Hrs. again added | 572.4 | 63.6
18 | A-16-04.AG16TOO038 | Augmentation of PTR capacity at 132KV SS Madhapur (80MVA) | 38, Dt.01.03.2016 (473 lakhs) | 473 | 5108 | Augmentation of Transformer capacities in GHMC area |  | PFC | 37203015 / March 2017 | 4.22 Crores | 2X80 | 3x80 |  | 3x80 |  | over |  | 425.7 | 47.3
19 | A-16-06.TOOMS61 | 132KV SS Thunikibollaram | 61, 23.04.2016 | 364 |  | Augmentation of Transformer capacities | U.O No. 54 / 2016, 11.05.2016 | PFC | 37203015 / March 2017 | 7.99 Crores | 2X10/16 | 2x31.5 |  | 2x31.5 |  | over
20 | A-16-06.TOOMS61 | 400KV SS Gajwel | 61, 23.04.2016 | 531 |  | Augmentation of Transformer capacities |  | PFC | 37203015 / March 2017 |  | 1x160 + 2x100 | 2x160+1x100 |  | 2x160+1x100 |  | over
21 | A-15-24.AG15TOO033 | 132KV SS Gunrock | 33, 14.02.2015 (Revision to 23, 28.01.2014) | 451 |  | Augmentation of Transformer capacities in GHMC area | U.O No. 711 / 2016, 06.04.2016 | REC | 9518 | Balance funding required Rs.126 Lakhs | 2x80+1x50 | 2x80+2x50 |  | 2x80+1x50 |  | To be covered | Rs.325 lakhs funding tied up with REC
22 | A-15-25.AG15TOO108 | 220KV SS Gachibowli | 108, 23.06.2015 (Revision to 23, 28.01.2014) | 570 |  | Augmentation of Transformer capacities in GHMC area |  | REC | 9518 | Balance funding required Rs.161 Lakhs | 1x80+2x50 | 1x80+3x50 |  | 1x80+2x50 |  | To be covered | Rs.409 lakhs funding tied up with REC
23 | A-16-05.TOO97DT16072016 | 132KV SS Erragadda | 97, 16.07.2016 | 423 |  | Augmentation of Transformer capacities in GHMC area | U.O No. 218 / 2016, 27.07.2016 |  |  |  | 2X80+ 1X50+1x40 (132/66KV) | 3x80+1x40 (132/66KV) |  | 3x80+1x40 (132/66KV) |  | over
24 | A-16-10.TOO167DT08122016 | 220KV SS Gunrock | 167, 08.12.2016 | 865.45 |  | Augmentation of Transformer capacities in GHMC area | U.O No. 49 / 2017, 28.01.2017 |  |  |  | 2x160 | 3x160 |  | 2x160 |  | To be covered
25 | A-16-10.TOO167DT08122016 | 220KV SS Ghanapur | 167, 08.12.2016 | 540.47 |  | Augmentation of Transformer capacities in GHMC area |  |  |  |  | 2X160+1x100 | 3X160 |  | 2X160+1x100 |  | To be covered
26 | A-16-09.TOO169DT09122016 | 220KV SS Malyalapally | 169, 09.12.2016 | 538.12 |  | Augmentation of Transformer capacities |  |  |  |  | 1x160+1x100 | 2x160 |  | 1x160+1x100 |  | To be covered
27 | O-16-01.TOO4DT11012017 | Procurement of EHT SS equipment required for O&M and PTRs rolling stock | 4, 11.01.2017 | 3953 |  | Equipment | U.O No. 133 / 2017, 14.03.2017
28 | A-17-01 Budget kept in SAP as per the CMD note approval | Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Warangal Zone | 77, 20.05.2017 |  |  |  | U.O No. 460 / 2017, 13.06.2017 | [8 empty] | To be covered
|  | 132 KV SS Kusumanchi |  | 300.92 | [6 empty] | 2*50 | 3*50
|  | 132 KV SS Bhadrachalam |  | 167.29 | [6 empty] | 1*31.5+1*16 | 2*31.5
|  | 132 KV SS Yellandu |  | 212.52 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Thallada |  | 212.52 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 220 KV SS Warangal |  | 282.86 | [6 empty] | 1*80+2*50 | 2*80+1*50
|  | 132 KV SS Narmetta |  | 233.66 | [6 empty] | 1*31.5+1*16 | 1*50+1*31.5
|  | 132 KV SS Ghanpur |  | 205.38 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Jangaon |  | 273.88 | [6 empty] | 1*31.5+1*16 | 1*50+1*31.5
|  | 132 KV SS Mustyal |  | 248.48 | [6 empty] | 1*50+1*31.5 | 2*50
|  | 132 KV SS Manakondur |  | 247.93 | [6 empty] | 1*31.5+1*16 | 1*50+1*31.5
|  | 132 KV SS Chippalapally |  | 109.83 | [6 empty] | 2*16 | 1*31.5+1*16
|  | 132 KV SS Mallaram |  | 203.93 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Shanigaram |  | 349.92 | [6 empty] | 2*31.5 | 1*50+2*31.5
|  | 220/132 KV SS Kamareddy |  | 763.58 | [6 empty] | 2*100 | 1*160+2*100
|  | 220/132/33 KV SS Dichpally |  | 449.69 | [6 empty] | 2*160+2*100 | 3*160+1*100
|  | 132 KV SS Bodhan |  | 255.46 | [6 empty] | 1*31.5+1*16 | 1*50+1*31.5
|  | 132 KV SS Bheemgal |  | 276.26 | [6 empty] | 2*50 | 1*80+1*50
|  | 132 KV SS Sirikonda |  | 214.81 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Armoor |  | 219.62 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Morthad |  | 218.34 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Banswada |  | 211.14 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Nizamsagar |  | 236.97 | [6 empty] | 2*31.5 | 1*50+1*31.5
|  | 132 KV SS Bichkunda |  | 126.34 | [6 empty] | 1*31.5+1*16 | 2*31.5
|  | 220/132/33 KV SS Dichpally |  | 225.93 | [6 empty] | 1*50+1*31.5 | 2*50
|  | 220 KV SS Mandamarry (Bellampally) |  | 612.3 | [6 empty] | 2*100 | 3*100
|  | 132 KV SS Burugupally |  | 115.97 | [6 empty] | 2*16 | 1*31.5+1*16
|  | 132 KV Khanapur (*) |  | 247.96 | [6 empty] | 1*31.5+1*16 | 2*31.5
29 | A-17-02 | Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Metro and Rural Zones | 87, 02.06.2017 |  |  |  | U.O No. 460 / 2017, 13.06.2017 | [8 empty] | To be covered
|  | 132KV SS Jubilee Hills |  | 401.85 | [6 empty] | 2x80+1x50+1x10/16 (132/11KV) | 2x80+2x50 |  |  |  | 132KV SS Jubilee Hills (50 MVA in place of 10/16MVA 132/11KV)
|  | 132KV SS Asif nagar |  | 277.48 | [6 empty] | 1x80+1x50 | 2x80 |  |  |  | 132KV SS Asif nagar (80 MVA in place of 50MVA)
|  | 220KV SS Sivarampally |  | 409.16 | [6 empty] | 1x160+3X100 | 2x160+2x100 |  |  |  | 220KV SS Sivarampally (160 MVA in place of 100 MVA)
|  | 220KV SS Ghanapur |  | 395.47 | [6 empty] | 2x31.5 | 1x80+1x31.5 |  |  |  | 220KV SS Ghanapur (80MVA in place of 31.5MVA)
|  | 220KV SS Nagole |  | 299.45 | [6 empty] | 2x31.5 | 1x80+1x31.5 |  |  |  | 220KV SS Nagole (80MVA in place of 31.5MVA)
|  | 132KV SS Malkaram |  | 261.29 | [6 empty] | 1x80+1x50 | 2x80 |  |  |  | 132KV SS Malkaram (80MVA in place of 50MVA)
|  | 132 KV SS Turkayamjal |  | 210.06 | [6 empty] | 2x31.5 | 1x50+1x31.5 |  |  |  | 132 KV SS Turkayamjal (50MVA in place of 31.5MVA)
|  | 220KV SS Gachibowli |  | 462.71 | [6 empty] | 2x160+2x100 | 3x160+1x100 |  |  |  | 220KV SS Gachibowli (160MVA in place of 100MVA)
|  | 220KV SS Medchel |  | 429.68 | [6 empty] | 2x160+1x100 | 3x160 |  |  |  | 220KV SS Medchel (160MVA in place of 100MVA)
|  | 220KV SS Shapurnagar |  | 296.54 | [6 empty] | 2x80+1x50 | 3x80 |  |  |  | 220KV SS Shapurnagar (80 MVA in place of 50 MVA)
|  | 220KV SS Mahaboobnagar (Bhoothpur) |  | 429.68 | [6 empty] | 2x160+1x100 | 3x160 |  |  |  | 220KV SS Mahaboobnagar (Bhoothpur) (160 MVA in place of 100 MVA)
|  | 220KVSS Minpur |  | 429.68 | [6 empty] | 2x160+1x100 | 3x160 |  |  |  | 220KVSS Minpur(160MVA in place of 100MVA)
|  | 132KV SS Pashamailaram |  | 458.95 | [6 empty] | 1x50+2x31.5 | 3x50 |  |  |  | 132KV SS Pashamailaram (1Nos. 50MVA in place of 1Nos.31.5MVA) (I/II)
|  | 132KV SS Bollaram |  | 367.75 | [6 empty] | 1x50+4x31.5 | 1x80+1x50+3x31.5 |  |  |  | 132KV SS Bollaram (80MVA in place of 31.5MVA)
30 |  | Procurement of Battery sets of various capacities for various Substations of TSTRANSCO to maintain the Healthiness of the System – Administrative Approval -Regarding | 97, 24.06.2017 | 39.53 |  |  | U.O No. 583/17, Dt:31.07.2017 | [8 empty] | To be covered
31 |  | Replacement of aged / obsolete equipment & strengthening/improvement works in EHT sub-stations and Transmission lines under Renovation & Modernization Scheme during the FY: 2017-18, FY:2018-19 - Administrative approval - Regarding | 146, 07.10.2017 | 100.22 | [11 empty] | To be covered
32 |  | Procurement of Battery sets of various capacities for various Substations of TSTRANSCO to maintain the Healthiness of the System – Administrative Approval -Regarding | 172, Dt:29.11.2017 | 174.29 |  |  | U.O No. 831/17, Dt:29.11.2017 |  |  |  |  | at (i) 400KV Malkaram SS from 2X100MVA to 1X160MVA +1X100MVA and (ii) 220KV Gachibowli SS from 1x80+2x50 MVA to 2x80+2x50 instead of 1x80+2x50 MVA to 1x80+3x50 MVA (with 5 Nos. 33 KV Bays) |  |  |  | To be covered
33 |  | 400KV Malkaram SS | 56, Dt.16.03.2018. | 479.36 |  | Augmentation of PTR Capacities
34 |  | 220KV Gachibowli S |  | 620.17
35 |  | 132KV Manoharabad SS | 55, Dt.16.03.2018 | 362.84 |  | Augmentation of PTR capacity

## TOOs list from 2014
DE / SS TOOs list for Augmentations in Nizamabad Circle
Description of work | T.O.O.No & Date (With amounts) | Existing PTR Capacities | Augmentation Capacities | T.O.O Amount (Rs. In Lakhs) | Accounting Unit | Circle | Date of Charging |  |  | T.O.O Amount (Rs. In Lakhs) | Unit | Remarks | Date of Charging | District
220KV SS Shivarampally | 23, Dt.28.01.2014 | 4x100 | 1x160+3x100 | 493 | 3310 | Metro-East |  |  |  | 493 | 3310 | Augmentation of PTR capacity
132KV SS Shapurnagar | 23, Dt.28.01.2014 | 2x50+1x80 | 1x50+2x80 | 256 | 3300 | Metro-West |  |  |  | 256 | 3300 | Augmentation of PTR capacity
132Kv SS Parigi | 23, Dt.28.01.2014 | 2x31.5 | 1x31.5 +1x50 | 258 | 3300 | Metro-West |  |  |  | 258 | 3300 | Augmentation of PTR capacity
132KV SS Gunrock | 23, Dt.28.01.2014 | 2x80+1x50 | 2x80+2x50 | 325 | 5108 | Metro-Central |  |  |  | 325 | 5108 | Augmentation of PTR capacity
220KV SS Gachibowli | 23, Dt.28.01.2014 | 2x50+1x80 | 3x50+1x80 | 409 | 3300 | Metro-West |  |  |  | 409 | 3300 | Augmentation of PTR capacity
132KV SS Hussainsagar (80MVA) | 28, Dt.12.02.2015 (277 lakhs) | 1X80+1X50 | 2x80 | 277 | 5108 | Metro-Central |  |  |  | 277 | 5108 | Augmentation of Transformer capacities in GHMC area
Augmentation of PTR capacity at 132KV SS Chilakalguda (2x80MVA) | 28, Dt.12.02.2015 (554 lakhs) | 2x50 | 2x80 | 554 | 5108 | Metro-Central |  |  |  | 554 | 5108 | Augmentation of Transformer capacities in GHMC area
Augmentation of PTR capacity at 220KV SS Narketpally (160MVA) | 40, Dt.25.02.2015 (520 lakhs) | 1x160 + 2x100 | 2x160 + 1x100 | 520 | 5112 | Nalgonda |  |  |  | 520 | 5112, 3600 | Under 9 hrs. Agl. scheme
Augmentation of PTR capacity at 132KV SS Choutuppal (50MVA) | 40, Dt.25.02.2015 (228 lakhs) | 2x31.5 | 1x50 + 1x31.5 | 228 | 5112 | Nalgonda |  |  |  | 228 | 5112 | Under 9 hrs. Agl. scheme
Augmentation of PTR capacity at 132KV SS Kodada (2x50MVA) | 57, Dt.26.03.2015 (422 lakhs) | 2x31.5 | 2X50 | 422 | 5112 | Nalgonda |  |  |  | 422 | 5112 | Under 9 hrs. Agl. scheme
Augmentation of PTR capacity at 132KV SS Khammam (50MVA) | 57, Dt.26.03.2015 (201 lakhs) | 2X50+1X31.5 | 3x50 | 201 | 5121 | Khammam |  |  |  | 201 | 5121 | Under 9 hrs. Agl. scheme
Augmentation of PTR capacity at 132KV SS Waddepally (50MVA) | 57, Dt.26.03.2015 (229 lakhs) | 2X31.5 | 1x50+1x31.5 | 229 | Funding not required and as it is covered in the TOO 82, Dt:01.05.2015 |  |  |  |  | 229 | Funding not required and as it is covered in the TOO 82, Dt:01.05.2015
132KV SS Chintal (50MVA) | 71, Dt.15.04.2015 (201 lakhs) | 1X50+1X31.5 | 2x50 | 201 | 5108 | Metro-Central |  |  |  | 201 | 5108 | Augmentation of Transformer capacities in GHMC area
Augmentation of PTR capacity at 132KV SS Jubilee Hills (31.5MVA) | 71, Dt.15.04.2015 (214 lakhs) | 2x80 + 1x50 + 1x10/16MVA (132/11KV) | 2x80 + 1x50+ 1x31.5MVA (132/33KV) | 214 | 5108 | Metro-Central |  |  |  | 214 | 5108 | Augmentation of Transformer capacities in GHMC area
220/132KV SS Narketpally | 114, Dt.02.07.2015 (1135.74 lakhs) | 2x160 + 1x100 | 2x160 + 2x100 | 378.58 | 5112 | Nalgonda |  |  |  | 378.58 | 5112 | Under 9 hrs. Agl. scheme
220/132KV SS Konda Mallepally (K.M.Pally) | 114, Dt.02.07.2015 (1135.74 lakhs) | 3x100 | 4x100 | 378.58 | 5112 | Nalgonda |  |  |  | 378.58 | 5112 | Under 9 hrs. Agl. scheme
220/132KV SS Miryalaguda | 114, Dt.02.07.2015 (1135.74 lakhs) | 2x160 + 1x100 | 2x160 + 2x100 | 378.58 | 5112 | Nalgonda |  |  |  | 378.58 | 5112 | Under 9 hrs. Agl. scheme
Augmentation of Transformer capacities at 220KV SS Dichpally for extending 9 Hrs. Agl. supply during day time. | 115, Dt.02.07.2015 (378.58 lakhs) | 1x160 + 2x100 | 2x160 + 2x100 | 378.58 | 5106 | Nizamabad | 06.04.2016 |  |  | 378.58 | 5106 | Under 9 hrs. Agl. scheme | 06.04.2016 | Nizamabad
RMI Works for the FY 2016-17 | 182, 16.09.2015 | [8 empty] | 5308
Augmentation of PTR capacity at 132KV SS Khammam (3x50+1x31.5MVA) | 216, Dt.20.11.2015 (201 lakhs) | 3x50 | 3x50 +1x31.5 | 201 | 5121 | Khammam |  |  |  | 201 | 5121 | Under 9 hrs. Agl. scheme
Renovation and Up-gradation of protection system in EHT Sub-stations of Telangana - TSTRANSCO - PSDF Approaval - Regarding | 19, Dt:08.02.2016 | [8 empty] | 5997
Augmentation of PTR capacity at 220KV SS Moulali (80MVA) | 24, Dt.16.02.2016 (515 lakhs) | 2X80+ 1X50 | 3x80+1x50 | 515 | 5108 | Metro-Central |  |  |  | 515 | 5108 | Augmentation of Transformer capacities in GHMC area |  | 463.5 | 51.5
Augmentation of PTR capacity at 220KV SS Sivarampally (80MVA) | 24, Dt.16.02.2016 (636 lakhs) | 2x80+ 2x50 | 3x80+2x50 | 636 | 5108 | Metro-Central | Under 24 Hrs. again added |  |  | 636 | 5108 | Augmentation of Transformer capacities in GHMC area | Under 24 Hrs. again added | 572.4 | 63.6
Augmentation of PTR capacity at 132KV SS Madhapur (80MVA) | 38, Dt.01.03.2016 (473 lakhs) | 2X80 | 3x80 | 473 | 5108 | Metro-Central |  |  |  | 473 | 5108 | Augmentation of Transformer capacities in GHMC area |  | 425.7 | 47.3
132KV SS Thunikibollaram | 61, 23.04.2016 | 2X10/16 | 2x31.5 | 364 | 5102 | Sangareddy |  |  |  | 364 | 5102 | Augmentation of Transformer capacities
400KV SS Gajwel | 61, 23.04.2016 | 1x160 + 2x100 | 2x160+1x100 | 531 | 5102 | Sangareddy |  |  |  | 531 | 5102 | Augmentation of Transformer capacities
132KV SS Gunrock | 33, 14.02.2015 (Revision to 23, 28.01.2014) | 2x80+1x50MVA | 2x80+2x50MVA | 451 | 5108 | Metro-Central | 09.07.2018 |  |  | 451 | 5108 | Augmentation of Transformer capacities in GHMC area | 09.07.2018 | Rs.325 lakhs funding tied up with REC
220KV SS Gachibowli | 108, 23.06.2015 (Revision to 23, 28.01.2014) | 1x80+2x50 | 1x80+3x50 | 570 | 3300 | Metro-West |  |  |  | 570 | 3300 | Augmentation of Transformer capacities in GHMC area |  | Rs.409 lakhs funding tied up with REC
132KV SS Erragadda | 97, 16.07.2016 | 2X80+ 1X50+1x40 (132/66KV) | 3x80+1x40 (132/66KV) | 423 | 5108 | Metro-Central |  |  |  | 423 | 5108 | Augmentation of Transformer capacities in GHMC area
220KV SS Gunrock | 167, 08.12.2016 | 2x160 | 3x160 | 865.45 | 5108 | Metro-Central | 24.05.2018 |  |  | 865.45 | 5108 | Augmentation of Transformer capacities in GHMC area | 24.05.2018
220KV SS Ghanapur | 167, 08.12.2016 | 2X160+1x100 | 3X160 | 540.47 | 3310 | Metro-East |  |  |  | 540.47 | 3310 | Augmentation of Transformer capacities in GHMC area
220KV SS Malyalapally | 169, 09.12.2016 | 1x160+1x100 | 2x160 | 538.12 | 5111 | Karimnagar | -- |  |  | 538.12 | 5111 | Augmentation of Transformer capacities | --
RMI Works for the FY 2016-17 | 171, 14.12.2016 (amendment to T.O.O 182, Dt:16.09.2015) | [8 empty] | 5308
Procurement of EHT SS equipment required for O&M and PTRs rolling stock | 4, 11.01.2017 | [8 empty] | 3953 |  | Equipment
Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Warangal Zone | 77, 20.05.2017
132 KV SS Kusumanchi | 77, 20.05.2017 | 2x50 | 3x50 | 300.92 | 5121 | Khammam | 05.02.2018 |  |  | 300.92 | 5121 | 24 Hrs Agl. | 05.02.2018
132 KV SS Bhadrachalam | 77, 20.05.2017 | 1x31.5+1x16 | 2x31.5 | 167.29 | 5121 | Khammam | -- |  |  | 167.29 | 5121 | 24 Hrs Agl. | --
132 KV SS Yellandu | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 212.52 | 5121 | Khammam | 30.12.2017 |  |  | 212.52 | 5121 | 24 Hrs Agl. | 30.12.2017
132 KV SS Thallada | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 212.52 | 5121 | Khammam | 31.12.2017 |  |  | 212.52 | 5121 | 24 Hrs Agl. | 31.12.2017
220 KV SS Warangal | 77, 20.05.2017 | 1x80+2x50 | 2x80+1x50 | 282.86 | 5101 | Warangal | 24.12.2017 |  |  | 282.86 | 5101 | 24 Hrs Agl. | 24.12.2017
132 KV SS Narmetta | 77, 20.05.2017 | 1x31.5+1x16 | 2x31.5 | 233.66 | 5101 | Warangal | 18.01.2018 |  |  | 233.66 | 5101 | 24 Hrs Agl. | 18.01.2018
132 KV SS Ghanpur | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 205.38 | 5101 | Warangal | 26.11.2017 |  |  | 205.38 | 5101 | 24 Hrs Agl. | 26.11.2017
132 KV SS Jangaon | 77, 20.05.2017 | 1x31.5+1x16 | 1x50+1x31.5 | 273.88 | 5101 | Warangal | 05.12.2017 |  |  | 273.88 | 5101 | 24 Hrs Agl. | 05.12.2017
132 KV SS Mustyal | 77, 20.05.2017 | 1x50+1x31.5 | 2x50 | 248.48 | 5101 | Warangal | 31.01.2018 |  |  | 248.48 | 5101 | 24 Hrs Agl. | 31.01.2018
132 KV SS Manakondur | 77, 20.05.2017 | 1x31.5+1x16 | 1x50+1x31.5 | 247.93 | 5111 | Karimnagar | 08.12.2017 |  |  | 247.93 | 5111 | 24 Hrs Agl. | 08.12.2017
132 KV SS Chippalapally | 77, 20.05.2017 | 2x16 | 1x31.5+1x16 | 109.83 | 5111 | Karimnagar | 09.01.2018 |  |  | 109.83 | 5111 | 24 Hrs Agl. | 09.01.2018
132 KV SS Mallaram | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 203.93 | 5111 | Karimnagar | 09.01.2018 |  |  | 203.93 | 5111 | 24 Hrs Agl. | 09.01.2018
132 KV SS Shanigaram | 77, 20.05.2017 | 2x31.5 | 1x50+2x31.5 | 349.92 | 5111 | Karimnagar | 30.04.2018 |  |  | 349.92 | 5111 | 24 Hrs Agl. | 30.04.2018
220/132 KV SS Kamareddy | 77, 20.05.2017 | 2x100 | 1x160+2x100 | 763.58 | 5106 | Nizamabad | 16.12.2017 |  |  | 763.58 | 5106 | 24 Hrs Agl. | 16.12.2017 | Nizamabad
220/132/33 KV SS Dichpally | 77, 20.05.2017 | 2x160+2x100 | 3x160+1x100 | 449.69 | 5106 | Nizamabad | 07.12.2017 |  |  | 449.69 | 5106 | 24 Hrs Agl. | 07.12.2017 | Nizamabad
132 KV SS Bodhan | 77, 20.05.2017 | 1x31.5+1x16 | 1x50+1x31.5 | 255.46 | 5106 | Nizamabad | 12.12.2017 |  |  | 255.46 | 5106 | 24 Hrs Agl. | 12.12.2017 | Nizamabad
132 KV SS Bheemgal | 77, 20.05.2017 | 2x50 | 1x80+1x50 | 276.26 | 5106 | Nizamabad | 10.02.2018 |  |  | 276.26 | 5106 | 24 Hrs Agl. | 10.02.2018 | Nizamabad
132 KV SS Sirikonda | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 214.81 | 5106 | Nizamabad | 30.12.2017 |  |  | 214.81 | 5106 | 24 Hrs Agl. | 30.12.2017 | Nizamabad
132 KV SS Armoor | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 219.62 | 5106 | Nizamabad | 03.01.2018 |  |  | 219.62 | 5106 | 24 Hrs Agl. | 03.01.2018 | Nizamabad
132 KV SS Morthad | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 218.34 | 5106 | Nizamabad | 27.12.2017 |  |  | 218.34 | 5106 | 24 Hrs Agl. | 27.12.2017 | Nizamabad
132 KV SS Banswada | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 211.14 | 5106 | Nizamabad | 28.12.2017 |  |  | 211.14 | 5106 | 24 Hrs Agl. | 28.12.2017 | Nizamabad
132 KV SS Nizamsagar | 77, 20.05.2017 | 2x31.5 | 1x50+1x31.5 | 236.97 | 5106 | Nizamabad | 05.01.2018 |  |  | 236.97 | 5106 | 24 Hrs Agl. | 05.01.2018 | Nizamabad
132 KV SS Bichkunda | 77, 20.05.2017 | 1x31.5+1x16 | 2x31.5 | 126.34 | 5106 | Nizamabad | 08.09.2017 |  |  | 126.34 | 5106 | 24 Hrs Agl. | 08.09.2017 | Nizamabad
220/132/33 KV SS Dichpally | 77, 20.05.2017 | 1x50+1x31.5 | 2x50 | 225.93 | 5106 | Nizamabad | 30.12.2017 |  |  | 225.93 | 5106 | 24 Hrs Agl. | 30.12.2017 | Nizamabad
220 KV SS Mandamarry (Bellampally) | 77, 20.05.2017 | 2x100 | 3x100 | 612.3 | 5122 | Adilabad | 06.04.2018 |  |  | 612.3 | 5122 | 24 Hrs Agl. | 06.04.2018 | Adilabad
132 KV SS Burugupally | 77, 20.05.2017 | 2x16 | 1x31.5+1x16 | 115.97 | 5122 | Adilabad | 15.11.2017 |  |  | 115.97 | 5122 | 24 Hrs Agl. | 15.11.2017 | Adilabad
132 KV Khanapur (*) | 77, 20.05.2017 | 1x31.5+1x16 | 2x31.5 | 247.96 | 5122 | Adilabad | 21.04.2017 |  |  | 247.96 | 5122 | 24 Hrs Agl. | 21.04.2017 | Adilabad
Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Metro and Rural Zones | 87, 02.06.2017
132KV SS Jubilee Hills | 87, 02.06.2017 | 2x80+1x50+1x10/16 (132/11KV) | 2x80+2x50 | 401.85 | 5108 | Metro-Central | 18.06.2018 |  |  | 401.85 | 5108 |  | 18.06.2018
132KV SS Asif nagar | 87, 02.06.2017 | 1x80+1x50 | 2x80 | 277.48 | 5108 | Metro-Central | 27.01.2018 |  |  | 277.48 | 5108 |  | 27.01.2018
220KV SS Sivarampally | 87, 02.06.2017 | 1x160+3X100 | 2x160+2x100 | 409.16 | 3310 | Metro-East | 26.07.2018 |  |  | 409.16 | 3310 |  | 26.07.2018
220KV SS Ghanapur | 87, 02.06.2017 | 2x31.5 | 1x80+1x31.5 | 395.47 | 3310 | Metro-East | -- |  |  | 395.47 | 3310 |  | --
220KV SS Nagole | 87, 02.06.2017 | 2x31.5 | 1x80+1x31.5 | 299.45 | 3310 | Metro-East | 02.05.2018 |  |  | 299.45 | 3310 |  | 02.05.2018
132KV SS Malkaram | 87, 02.06.2017 | 1x80+1x50 | 2x80 | 261.29 | 3310 | Metro-East | 28.08.2018 |  |  | 261.29 | 3310 |  | 28.08.2018
132 KV SS Turkayamjal | 87, 02.06.2017 | 2x31.5 | 1x50+1x31.5 | 210.06 | 3310 | Metro-East | -- |  |  | 210.06 | 3310 |  | --
220KV SS Gachibowli | 87, 02.06.2017 | 2x160+2x100 | 3x160+1x100 | 462.71 | 3300 | Metro-West | 19.02.2018 |  |  | 462.71 | 3300 |  | 19.02.2018
220KV SS Medchel | 87, 02.06.2017 | 2x160+1x100 | 3x160 | 429.68 | 3300 | Metro-West | -- |  |  | 429.68 | 3300 |  | --
220KV SS Shapurnagar | 87, 02.06.2017 | 2x80+1x50 | 3x80 | 296.54 | 3300 | Metro-West | 14.04.2019 |  |  | 296.54 | 3300 |  | 14.04.2019
220KV SS Mahaboobnagar (Bhoothpur) | 87, 02.06.2017 | 2x160+1x100 | 3x160 | 429.68 | 5113 | Mahaboobnagar | 22.02.2018 |  |  | 429.68 | 5113 |  | 22.02.2018
220KVSS Minpur | 87, 02.06.2017 | 2x160+1x100 | 3x160 | 429.68 | 5102 | Sangareddy | 06.03.2018 |  |  | 429.68 | 5102 |  | 06.03.2018
132KV SS Pashamailaram | 87, 02.06.2017 | 1x50+2x31.5 | 3x50 | 458.95 | 5102 | Sangareddy | 16.07.2018 |  |  | 458.95 | 5102 |  | 16.07.2018
132KV SS Bollaram | 87, 02.06.2017 | 1x50+4x31.5 | 1x80+1x50+3x31.5 | 367.75 | 5102 | Sangareddy | 28.06.2018 |  |  | 367.75 | 5102 |  | 28.06.2018 |  |  |  | (Malkajgiri)
Procurement of Battery sets of various capacities for various Substations of TSTRANSCO to maintain the Healthiness of the System – Administrative Approval -Regarding | 97, 24.06.2017 | [8 empty] | 103
Replacement of aged / obsolete equipment & strengthening/improvement works in EHT sub-stations and Transmission lines under Renovation & Modernization Scheme during the FY: 2017-18, FY:2018-19 - Administrative approval - Regarding | 146, 07.10.2017 | [8 empty] | 10022 | [5 empty] | (Bhoothpur)
Procurement of Battery sets of various capacities for various Substations of TSTRANSCO to maintain the Healthiness of the System – Administrative Approval -Regarding | 172, Dt:29.11.2017 | [8 empty] | 174.29
400KV Malkaram SS | 56, Dt.16.03.2018. | 2X100 | 1x160+1x100 | 479.36 | 3310 | Metro-East | 06.07.2018 |  |  | 479.36 | 3310 | Augmentation of PTR Capacities | 06.07.2018
220KV Gachibowli S |  | 1x80+2x50 | 2x80+2x50 (with 5 Nos. 33 KV Bays) | 620.17 | 3300 | Metro-West | 15.04.2018 |  |  | 620.17 | 3300 |  | 15.04.2018
132KV Manoharabad SS | 55, Dt.16.03.2018 | 2X50 | 1x80 + 1x50 | 362.84 | 5102 | Sangareddy | 08.01.2018 |  |  | 362.84 | 5102 | Augmentation of PTR capacity | 08.01.2018
Procurement of EHT SS equipment required for O&M and PTRs rolling stock | 70, 03.04.2018 | [8 empty] | 2643.57 |  |  |  |  | TOTAL |  |  | 5129.75
220 KV Chadrayanagutta | 78, Dt:13.04.2018 | 2x160 + 2x100 | 4 x 160 | 825 | 3310 | Metro-East | 20.03.2018, 09.04.2018 |  |  | 825 | 3310 | Augmentation of PTR capacity | 20.03.2018, 09.04.2018
132 KV Yerrabally SS | T.O.O.No 152& Dt 18.07.2018 | 1x16 + 1x31.5 | 2x31.5 | 105.65 | 5122 | Adilabad | 05.03.2018 |  |  | 105.65 | 5122 |  | 05.03.2018
220 KV Waddekothapally SS | T.O.O.No 152& Dt 18.07.2018 | 2x50 | 2x50 + 1x31.5 | 279.25 | 5101 | Warangal |  |  |  | 279.25 | 5101
132 KV Ghanpur SS | T.O.O.No 152& Dt 18.07.2018 | 1x50 + 1x31.5 | 2x50 | 176.63 | 5101 | Warangal | 04.08.2018 |  |  | 176.63 | 5101 |  | 04.08.2018
132 KV Inavole SS | T.O.O.No 152& Dt 18.07.2018 | 2x16 | 1x16 + 1x31.5 | 106.78 | 5101 | Warangal | 08.08.2018 |  |  | 106.78 | 5101 |  | 08.08.2018
220 KV SS K.M Pally |  | 3x100 | 4x100 | 378.58 | 5112 | Nalgonda | 13.06.2016 |  |  | 378.58 | 5112 | 9 Hrs Agl. | 13.06.2016 | Nalgonda
220 KV SS Miryalaguda |  | 2x160+1x100 | 2x160+2x100 | 378.58 | 5112 | Nalgonda | 26.04.2016 |  |  | 378.58 | 5112 | 9 Hrs Agl. | 26.04.2016 | Nalgonda
220 KV SS Narketpally |  | 1x160+2x100 | 2x160+2x100 | 378.58 | 5112 | Nalgonda |  |  |  | 378.58 | 5112 | 9 Hrs Agl. |  | Nalgonda
220/132 KV SS Dichpally |  | 1x160+2x100 | 2x160+2x100 | 378.58 | 5106 | Nizamabad | 06.04.2016 |  |  | 378.58 | 5106 | 9 Hrs Agl. | 06.04.2016 | Nizamabad | Repeated
132 KV SS Khammam | TOO Ms. No.216, Dt:20.11.2015 | 2x50+1x31.5 | 3x50+1x31.5 (instead of 3x50) | 201 | 5121 | Khammam | 04.02.2016 |  |  |  | 5121 | 9 Hrs Agl. | 04.02.2016 | Khammam
220/132/33 KV SS Shamshabad | T.O.O Ms. No.82, Dt:01.05.2015 | 2x100 | 3x100 | 587.71 | 3310 | Metro-East | 12.03.2016 | 0 |  | 587.71 | 3310 | 9 Hrs Agl. | 12.03.2016 | Ranga Reddy-East
220/132/33 KV SS Tandur | T.O.O Ms. No.82, Dt:01.05.2015 | 2x100 | 3x100 | 587.71 | 3300 | Metro-West | 03.03.2016 | 0 |  | 587.71 | 3300 | 9 Hrs Agl. | 03.03.2016 | Ranga Reddy-West
220/132/33 KV SS Shamshabad | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 213.7 | 3310 | Metro-East | 24.12.2015 | 0 |  | 213.7 | 3310 | 9 Hrs Agl. | 24.12.2015 | Ranga Reddy-East
132 KV SS Dhamasagar | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 3x31.5 | 265.22 | 3300 | Metro-West | 12.03.2016 | 0 |  | 265.22 | 3300 | 9 Hrs Agl. | 12.03.2016 | Ranga Reddy-West
132 KV SS Puttapahad | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 3x31.5 | 265.22 | 3300 | Metro-West | 10.03.2016 | 0 |  | 265.22 | 3300 | 9 Hrs Agl. | 10.03.2016 | Ranga Reddy-West
132KV SS Parigi | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 3x50 | 273.03 | 3300 | Metro-West | 21.01.2016 | 273.03 |  | 546.06 | 3300 | 9 Hrs Agl. | 21.01.2016 | Ranga Reddy-West
132KV SS Parigi | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 3x50 | 273.03 | 3300 | Metro-West | 05.03.2016 | -273.03 |  |  | 3300 | 9 Hrs Agl. | 05.03.2016 | Ranga Reddy-West
132 KV SS Medchel | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50+1x31.5 | 3x50 | 209.37 | 3300 | Metro-West | 08.01.2016 | 0 |  | 209.37 | 3300 | 9 Hrs Agl. | 08.01.2016 | Ranga Reddy-West
132 KV SS Bandlaguda | T.O.O Ms. No.82, Dt:01.05.2015 | 2x80+1x50 | 3x80+1x50 | 363.66 | 3310 | Metro-East | 16.10.2015 | 0 |  | 363.66 | 3310 | 9 Hrs Agl. | 16.10.2015 | Ranga Reddy-East
132 KV SS Yacharam | T.O.O Ms. No.82, Dt:01.05.2015 | 1x10/16 (modified in stead of 2x10/16) | 2x31.5 | 138.465 | 3310 | Metro-East | 18.11.2015 | 138.465 |  | 276.93 | 3310 | 9 Hrs Agl. | 18.11.2015 | Ranga Reddy-East
132 KV SS Yacharam | T.O.O Ms. No.82, Dt:01.05.2015 | 1x10/16 (modified in stead of 2x10/16) | 2x31.5 | 138.465 | 3310 | Metro-East | 02.12.2015 | -138.465 |  |  | 3310 | 9 Hrs Agl. | 02.12.2015 | Ranga Reddy-East
220/132/33 KV SS Tandur | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 3x50 | 361.21 | 3300 | Metro-West | 29.04.2016 | 0 |  | 361.21 | 3300 | 9 Hrs Agl. | 29.04.2016 | Ranga Reddy-West
220/132/33 KV SS Malkaram | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 1x80+1x50 | 282.66 | 3310 | Metro-East | 25.01.2016 | 0 |  | 282.66 | 3310 | 9 Hrs Agl. | 25.01.2016 | Ranga Reddy-East
220/132/33 KV SS Minpur | T.O.O Ms. No.82, Dt:01.05.2015 | 3x100 | 2x160+1x100 | 510.195 | 5102 | Sangareddy | 18.02.2016 | 510.195 |  | 1020.39 | 5102 | 9 Hrs Agl. | 18.02.2016 | Medak
220/132/33 KV SS Minpur | T.O.O Ms. No.82, Dt:01.05.2015 | 3x100 | 2x160+1x100 | 510.195 | 5102 | Sangareddy | 14.05.2016 | -510.195 |  |  | 5102 | 9 Hrs Agl. | 14.05.2016 | Medak
220 KV SS Siddipet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x100 | 1x160+2x100 | 778.12 | 5102 | Sangareddy | 13.05.2016 | 0 |  | 778.12 | 5102 | 9 Hrs Agl. | 13.05.2016 | Medak
220 KV SS Sadasivpet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x100 | 1x160+1x100 | 483.73 | 5102 | Sangareddy | 18.03.2016 | 0 |  | 483.73 | 5102 | 9 Hrs Agl. | 18.03.2016 | Medak
220/132/33 KV SS Minpur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 224.9 | 5102 | Sangareddy | 05.02.2016 | 224.9 |  | 449.8 | 5102 | 9 Hrs Agl. | 05.02.2016 | Medak
220/132/33 KV SS Minpur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 224.9 | 5102 | Sangareddy | 02.04.2016 | -224.9 |  |  | 5102 | 9 Hrs Agl. | 02.04.2016 | Medak
132 KV SS Sadasivpet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5+1x10/16 | 1x80+2x31.5 | 418.41 | 5102 | Sangareddy | 11.03.2016 | 0 |  | 418.41 | 5102 | 9 Hrs Agl. | 11.03.2016 | Medak
132 KV SS Zaheerabad | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 2x80+ 1x50 (instead of 2 x 80) | 293.37 | 5102 | Sangareddy | 04.02.2016 | 293.37 |  | 586.74 | 5102 | 9 Hrs Agl. | 04.02.2016 | Medak
132 KV SS Zaheerabad | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 2x80+ 1x50(instead of 2 x 80) | 293.37 | 5102 | Sangareddy |  | -293.37 |  |  | 5102 | 9 Hrs Agl. |  | Medak
132 KV SS Jogipet | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5102 | Sangareddy | 13.02.2016 | 221.33 |  | 442.66 | 5102 | 9 Hrs Agl. | 13.02.2016 | Medak
132 KV SS Jogipet | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5102 | Sangareddy | 14.03.2016 | -221.33 |  |  | 5102 | 9 Hrs Agl. | 14.03.2016 | Medak
132 KV SS Medak | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x 31.5 | 2x50 | 151.56 | 5102 | Sangareddy | 06.02.2016 | 0 |  | 151.56 | 5102 | 9 Hrs Agl. | 06.02.2016 | Medak
132 KV SS Narayankhed | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 203.93 | 5102 | Sangareddy | 10.03.2016 | 203.93 |  | 407.86 | 5102 | 9 Hrs Agl. | 10.03.2016 | Medak
132 KV SS Narayankhed | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 203.93 | 5102 | Sangareddy | 04.04.2016 | -203.93 |  |  | 5102 | 9 Hrs Agl. | 04.04.2016 | Medak
132 KV SS Gummadidala | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 1x80+1x50 | 307.51 | 5102 | Sangareddy | 28.04.2016 | 0 |  | 307.51 | 5102 | 9 Hrs Agl. | 28.04.2016 | Medak
132 KV SS Kowdipally | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.495 | 5102 | Sangareddy | 03.02.2016 | 221.495 |  | 442.99 | 5102 | 9 Hrs Agl. | 03.02.2016 | Medak
132 KV SS Kowdipally | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.495 | 5102 | Sangareddy | 26.03.2016 | -221.495 |  |  | 5102 | 9 Hrs Agl. | 26.03.2016 | Medak
132 KV SS Narsapur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x 31.5 | 2x50 | 138.36 | 5102 | Sangareddy | 30.12.2015 | 0 |  | 138.36 | 5102 | 9 Hrs Agl. | 30.12.2015 | Medak
132 KV SS Singoor | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 139.87 | 5102 | Sangareddy | 07.01.2016 | 139.87 |  | 279.74 | 5102 | 9 Hrs Agl. | 07.01.2016 | Medak
132 KV SS Singoor | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 139.87 | 5102 | Sangareddy | 06.03.2016 | -139.87 |  |  | 5102 | 9 Hrs Agl. | 06.03.2016 | Medak
132 KV SS Peddashankarampet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 139.87 | 5102 | Sangareddy | 11.01.2016 | 139.87 |  | 279.74 | 5102 | 9 Hrs Agl. | 11.01.2016 | Medak
132 KV SS Peddashankarampet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 139.87 | 5102 | Sangareddy | 08.02.2016 | -139.87 |  |  | 5102 | 9 Hrs Agl. | 08.02.2016 | Medak
132 KV SS Tukkapur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 2x50 | 213.21 | 5102 | Sangareddy | 09.03.2016 | 0 |  | 213.21 | 5102 | 9 Hrs Agl. | 09.03.2016 | Medak
132 KV SS Gajwel | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 2x80 | 278.995 | 5102 | Sangareddy | 22.06.2015 | 278.995 |  | 557.99 | 5102 | 9 Hrs Agl. | 22.06.2015 | Medak
132 KV SS Gajwel | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 2x80 | 278.995 | 5102 | Sangareddy | 16.02.2016 | -278.995 |  |  | 5102 | 9 Hrs Agl. | 16.02.2016 | Medak
132 KV SS Chegunta | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 1x80+1x50 | 280.99 | 5102 | Sangareddy | 28.08.2015 | 0 |  | 280.99 | 5102 | 9 Hrs Agl. | 28.08.2015 | Medak
132 KV SS Habsipur | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 203.93 | 5102 | Sangareddy | 03.10.2015 | 203.93 |  | 407.86 | 5102 | 9 Hrs Agl. | 03.10.2015 | Medak
132 KV SS Habsipur | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 203.93 | 5102 | Sangareddy | 20.02.2016 | -203.93 |  |  | 5102 | 9 Hrs Agl. | 20.02.2016 | Medak
132 KV SS Ramayampet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 147.505 | 5102 | Sangareddy | 31.12.2015 | 147.505 |  | 295.01 | 5102 | 9 Hrs Agl. | 31.12.2015 | Medak
132 KV SS Ramayampet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 147.505 | 5102 | Sangareddy | 14.01.2016 | -147.505 |  |  | 5102 | 9 Hrs Agl. | 14.01.2016 | Medak
132 KV SS Palamakula | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 145.88 | 5102 | Sangareddy | 18.01.2016 | 145.88 |  | 291.76 | 5102 | 9 Hrs Agl. | 18.01.2016 | Medak
132 KV SS Palamakula | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 145.88 | 5102 | Sangareddy | 30.01.2016 | -145.88 |  |  | 5102 | 9 Hrs Agl. | 30.01.2016 | Medak
220/132/33 KV SS Miryalaguda | T.O.O Ms. No.82, Dt:01.05.2015 | 1x80+1x50 | 2x80 | 279.99 | 5112 | Nalgonda | 24.07.2015 | 0 |  | 279.99 | 5112 | 9 Hrs Agl. | 24.07.2015 | Nalgonda
220 KV SS Narketpally | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x15 | 1x50+1x31.5 (instead of 2x50) | 225.95 | 5112 | Nalgonda | 13.11.2015 | 225.95 | 225.95 | 451.9 | 5112 | 9 Hrs Agl. | 13.11.2015 | Nalgonda
132 KV SS Aitipamula | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 1x50+1x31.5 | 225.95 | 5112 | Nalgonda | 04.01.2016 | -225.95 |  |  | 5112 | 9 Hrs Agl. | 04.01.2016 | Nalgonda
220 KV SS Bhongiri | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 225.95 | 5112 | Nalgonda | 16.12.2015 | 225.95 |  | 451.9 | 5112 | 9 Hrs Agl. | 16.12.2015 | Nalgonda
220 KV SS Bhongiri | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 225.95 | 5112 | Nalgonda | 01.02.2016 | -225.95 |  |  | 5112 | 9 Hrs Agl. | 01.02.2016 | Nalgonda
132 KV SS Mattampally | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 211.055 | 5112 | Nalgonda | 27.11.2015 | 211.055 |  | 422.11 | 5112 | 9 Hrs Agl. | 27.11.2015 | Nalgonda
132 KV SS Mattampally | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 211.055 | 5112 | Nalgonda | 30.03.2016 | -211.055 |  |  | 5112 | 9 Hrs Agl. | 30.03.2016 | Nalgonda
132 KV SS Thungaturthy | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 211.055 | 5112 | Nalgonda | 25.09.2015 | 211.055 |  | 422.11 | 5112 | 9 Hrs Agl. | 25.09.2015 | Nalgonda
132 KV SS Thungaturthy | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 211.055 | 5112 | Nalgonda | 07.03.2016 | -211.055 |  |  | 5112 | 9 Hrs Agl. | 07.03.2016 | Nalgonda
132 KV SS Haliya | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 211.055 | 5112 | Nalgonda | 22.12.2015 | 211.055 |  | 422.11 | 5112 | 9 Hrs Agl. | 22.12.2015 | Nalgonda
132 KV SS Haliya | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 211.055 | 5112 | Nalgonda | 13.02.2016 | -211.055 |  |  | 5112 | 9 Hrs Agl. | 13.02.2016 | Nalgonda
132 KV SS K.M.Pally | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50+1x31.5 | 1x80+2x50 (instead of 2x80+1x31.5) | 554.57 | 5112 | Nalgonda | 11.03.2016 | 0 |  | 554.57 | 5112 | 9 Hrs Agl. | 11.03.2016 | Nalgonda
132 KV SS Disincherla | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 204.89 | 5112 | Nalgonda | 16.10.2015 | 204.89 |  | 409.78 | 5112 | 9 Hrs Agl. | 16.10.2015 | Nalgonda
132 KV SS Disincherla | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 204.89 | 5112 | Nalgonda | 04.03.2016 | -204.89 |  |  | 5112 | 9 Hrs Agl. | 04.03.2016 | Nalgonda
132 KV SS Guntipally | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5 + 1x10/16 | 2x31.5 + 1x10/16 | 254.42 | 5112 | Nalgonda | 10.05.2016 | 0 |  | 254.42 | 5112 | 9 Hrs Agl. | 10.05.2016 | Nalgonda
132 KV SS Nalgonda | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+2x31.5 | 1x80+1x50+2x31.5 (instead of 2x80+2x31.5) | 704.62 | 5112 | Nalgonda | 23.05.2016 | 0 |  | 704.62 | 5112 | 9 Hrs Agl. | 23.05.2016 | Nalgonda
132 KV SS Kolanpaka (Aleru) | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50+1x10/16 (132/ 11 KV) | 1x80+2x50 | 334.93 | 5112 | Nalgonda | 27.05.2016 | 0 |  | 334.93 | 5112 | 9 Hrs Agl. | 27.05.2016 | Nalgonda
132 KV SS Ramannapet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 3x50 (instead of 2x80) | 553.45 | 5112 | Nalgonda | 01.06.2016 | 0 |  | 553.45 | 5112 | 9 Hrs Agl. | 01.06.2016 | Nalgonda
132 KV SS Bibinagar | cost included in 43 and 44 in TOO 82 | 2x50 | 1x80+1x50 | 0 | 5112 | Nalgonda | 03.03.2016 | 0 |  | 0 | 5112 | 9 Hrs Agl. | 03.03.2016 | Nalgonda
132 KV SS Shali Gowraram | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 1x80+1x50 (instead of 2x50) | 207.71 | 5112 | Nalgonda | 12.01.2016 | 0 |  | 207.71 | 5112 | 9 Hrs Agl. | 12.01.2016 | Nalgonda
132 KV SS Choutuppal | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 2x50 | 179.21 | 5112 | Nalgonda | 15.12.2015 | 0 |  | 179.21 | 5112 | 9 Hrs Agl. | 15.12.2015 | Nalgonda
132 KV SS Madgulapally | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 1x80+1x50 (instead of 2x50) | 221.33 | 5112 | Nalgonda | 29.02.2016 | 221.33 |  | 442.66 | 5112 | 9 Hrs Agl. | 29.02.2016 | Nalgonda
132 KV SS Madgulapally | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 1x80+1x50 (instead of 2x50) | 221.33 | 5112 | Nalgonda | 04.04.2016 | 221.33 |  | 442.66 | 5112 | 9 Hrs Agl. | 04.04.2016 | Nalgonda
132 KV SS Mothkur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5112 | Nalgonda | 23.11.2015 | 221.33 |  | 442.66 | 5112 | 9 Hrs Agl. | 23.11.2015 | Nalgonda
132 KV SS Mothkur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5112 | Nalgonda | 05.02.2016 | -221.33 |  |  | 5112 | 9 Hrs Agl. | 05.02.2016 | Nalgonda
132 KV SS Marriguda | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5112 | Nalgonda | 05.11.2015 | 221.33 |  | 442.66 | 5112 | 9 Hrs Agl. | 05.11.2015 | Nalgonda
132 KV SS Marriguda | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5112 | Nalgonda | 28.04.2016 | -221.33 |  |  | 5112 | 9 Hrs Agl. | 28.04.2016 | Nalgonda
132 KV SS Kanagal | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5112 | Nalgonda | 21.01.2016 | 221.33 |  | 442.66 | 5112 | 9 Hrs Agl. | 21.01.2016 | Nalgonda
132 KV SS Kanagal | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 221.33 | 5112 | Nalgonda | 30.11.2015 | -221.33 |  |  | 5112 | 9 Hrs Agl. | 30.11.2015 | Nalgonda
220/132/33 KV SS Mahaboobnagar (Bhootpur) | T.O.O Ms. No.82, Dt:01.05.2015 | 1x160+2x100 | 2x160+1x100 | 506.21 | 5113 | Mahaboobnagar | 10.02.2016 | 0 |  | 506.21 | 5113 | 9 Hrs Agl. | 10.02.2016 | Mahaboobnagar
220 KV SS Kalwakurthy | T.O.O Ms. No.82, Dt:01.05.2015 | 3x100 | 2x160+1x100 | 508.89 | 5113 | Mahaboobnagar | 21.03.2016 | -508.89 |  |  | 5113 | 9 Hrs Agl. | 21.03.2016 | Mahaboobnagar
220 KV SS Kalwakurthy | T.O.O Ms. No.82, Dt:01.05.2015 | 3x100 | 2x160+1x100 | 508.89 | 5113 | Mahaboobnagar | 17.02.2016 | 508.89 |  | 1017.78 | 5113 | 9 Hrs Agl. | 17.02.2016 | Mahaboobnagar
220/132/33 KV SS Shadnagar | T.O.O Ms. No.82, Dt:01.05.2015 | 3x100 | 1x160+2x100 | 502.88 | 5113 | Mahaboobnagar | 02.12.2015 | 0 |  | 502.88 | 5113 | 9 Hrs Agl. | 02.12.2015 | Mahaboobnagar
220/132/33 KV SS Wanaparthy | T.O.O Ms. No.82, Dt:01.05.2015 | 1x160+1x100 | 2x160 | 502.88 | 5113 | Mahaboobnagar | 29.02.2016 | 0 |  | 502.88 | 5113 | 9 Hrs Agl. | 29.02.2016 | Mahaboobnagar
220 KV SS Jurala | T.O.O Ms. No.82, Dt:01.05.2015 | 2x100 | 3x100 | 585.31 | 5113 | Mahaboobnagar | 21.06.2016 | 0 |  | 585.31 | 5113 | 9 Hrs Agl. | 21.06.2016 | Mahaboobnagar
220/132/33 KV SS Shadnagar | T.O.O Ms. No.82, Dt:01.05.2015 | 1x80+1x50 | 1x80+1x50 + 1x31.5 | 260.89 | 5113 | Mahaboobnagar | 29.03.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 29.03.2016 | Mahaboobnagar
132 KV SS Mahaboobnagar | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50+1x10/16 | 1x80+2x50 (instead of 3x50) | 241.87 | 5113 | Mahaboobnagar | 14.04.2016 | 0 |  | 241.87 | 5113 | 9 Hrs Agl. | 14.04.2016 | Mahaboobnagar
220 KV SS Kalwakurthy | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+2x31.5 | 3x50 | 146.37 | 5113 | Mahaboobnagar | 16.11.2015 | 0 |  | 146.37 | 5113 | 9 Hrs Agl. | 16.11.2015 | Mahaboobnagar
132 KV SS Balanagar | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50+1x31.5 | 3x50 | 205.87 | 5113 | Mahaboobnagar | 20.01.2016 | 0 |  | 205.87 | 5113 | 9 Hrs Agl. | 20.01.2016 | Mahaboobnagar
132 KV SS Kothur | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50+1x31.5 | 3x50 | 210.87 | 5113 | Mahaboobnagar | 25.01.2016 | 0 |  | 210.87 | 5113 | 9 Hrs Agl. | 25.01.2016 | Mahaboobnagar
132 KV SS Amangal | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 1x50+2x31.5 | 260.89 | 5113 | Mahaboobnagar | 11.05.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 11.05.2016 | Mahaboobnagar
132 KV SS Nagarkurnool | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 1x50+2x31.5 | 260.89 | 5113 | Mahaboobnagar | 09.03.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 09.03.2016 | Mahaboobnagar
132 KV SS Maddur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 1x50+2x31.5 | 260.89 | 5113 | Mahaboobnagar | 24.03.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 24.03.2016 | Mahaboobnagar
132 KV SS Achampet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 199.3 | 5113 | Mahaboobnagar | 16.11.2015 | 199.3 |  | 398.6 | 5113 | 9 Hrs Agl. | 16.11.2015 | Mahaboobnagar
132 KV SS Achampet | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 2x50 | 199.3 | 5113 | Mahaboobnagar | 03.03.2016 | -199.3 |  |  | 5113 | 9 Hrs Agl. | 03.03.2016 | Mahaboobnagar
132 KV SS Marikal | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 3x31.5 | 260.89 | 5113 | Mahaboobnagar | 13.04.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 13.04.2016 | Mahaboobnagar
132 KV SS Makthal | T.O.O Ms. No.82, Dt:01.05.2015 | 1x50+1x31.5 | 1x50+2x31.5 | 260.89 | 5113 | Mahaboobnagar | 29.06.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 29.06.2016 | Mahaboobnagar
132 KV SS Kodangal | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 3x31.5 | 260.89 | 5113 | Mahaboobnagar | 31.03.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 31.03.2016 | Mahaboobnagar
132 KV SS Alampur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 139.21 | 5113 | Mahaboobnagar | 21.12.2015 | 0 |  | 139.21 | 5113 | 9 Hrs Agl. | 21.12.2015 | Mahaboobnagar
132 KV SS Peddadagada (Chinnamaroor) | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 138.465 | 5113 | Mahaboobnagar | 14.12.2015 | 138.465 |  | 276.93 | 5113 | 9 Hrs Agl. | 14.12.2015 | Mahaboobnagar
132 KV SS Peddadagada (Chinnamaroor) | T.O.O Ms. No.82, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 138.465 | 5113 | Mahaboobnagar | 28.12.2015 | -138.465 |  |  | 5113 | 9 Hrs Agl. | 28.12.2015 | Mahaboobnagar
132 KV SS Gadwal | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 1x80+ 2x50( instead of 2x80) | 276.835 | 5113 | Mahaboobnagar | 04.04.2016 | 276.835 |  | 553.67 | 5113 | 9 Hrs Agl. | 04.04.2016 | Mahaboobnagar
132 KV SS Gadwal | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 1x80+ 2x50( instead of 2x80) | 276.835 | 5113 | Mahaboobnagar | 04.04.2016 | -276.835 |  |  | 5113 | 9 Hrs Agl. | 04.04.2016 | Mahaboobnagar
132 KV SS Midjil | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 3x31.5 | 105.445 | 5113 | Mahaboobnagar | 23.12.2015 | 105.445 |  | 210.89 | 5113 | 9 Hrs Agl. | 23.12.2015 | Mahaboobnagar
132 KV SS Midjil | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 | 3x31.5 | 105.445 | 5113 | Mahaboobnagar | 01.03.2016 | -105.445 |  |  | 5113 | 9 Hrs Agl. | 01.03.2016 | Mahaboobnagar
132 KV SS Ieeza | T.O.O Ms. No.82, Dt:01.05.2015 | 2x31.5 | 3x31.5 | 260.89 | 5113 | Mahaboobnagar | 25.03.2016 | 0 |  | 260.89 | 5113 | 9 Hrs Agl. | 25.03.2016 | Mahaboobnagar
132 KV SS Wanaparthy | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 2x80 | 276.835 | 5113 | Mahaboobnagar | 13.02.2016 | 276.835 |  | 553.67 | 5113 | 9 Hrs Agl. | 13.02.2016 | Mahaboobnagar
132 KV SS Wanaparthy | T.O.O Ms. No.82, Dt:01.05.2015 | 2x50 | 2x80 | 276.835 | 5113 | Mahaboobnagar | 22.03.2016 | -276.835 |  |  | 5113 | 9 Hrs Agl. | 22.03.2016 | Mahaboobnagar
132 KV SS Jadcherla | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5 + 1x10/16 | 2x31.5 | 145.03 | 5113 | Mahaboobnagar | 04.12.2015 | 0 |  | 145.03 | 5113 | 9 Hrs Agl. | 04.12.2015 | Mahaboobnagar
132 KV SS Khila Ghanpur | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5 + 1x10/16 | 2x31.5 | 144.41 | 5113 | Mahaboobnagar | 26.11.2015 | 0 |  | 144.41 | 5113 | 9 Hrs Agl. | 26.11.2015 | Mahaboobnagar
132 KV SS Thirumalaipalli (LI) | T.O.O Ms. No.82, Dt:01.05.2015 | 1x31.5+1x10/16 (instead of 2x10/16) | 1x31.5+2x10/16 | 260.89 | 5113 | Mahaboobnagar | 26.03.2016 | 23190.79 |  | 260.89 | 5113 | 9 Hrs Agl. | 26.03.2016 | Mahaboobnagar
220/132/33 KV SS Shapurnagar | in force 82 T.O.O 489, 24-02-2011 | 2x160+1x100 | 3x160 | 500 | 3300 | Metro-West | 02.03.2016 | 0 |  | 500 | 3300 | 9 Hrs Agl. | 02.03.2016 | Ranga Reddy-West
220/132/33 KV SS Moulali | in force 82 T.O.O 489, 24-02-2011 | 2x160+1x100 | 3x160 | 500 | 3310 | Metro-East | 27.02.2016 | 0 |  | 500 | 3310 | 9 Hrs Agl. | 27.02.2016 | Ranga Reddy-East
220/132/33 KV SS Shapurnagar | in force 82 T.O.O 23, 28-01-2014 | 2x50+1x80 | 1x50+2x80 | 256 | 3300 | Metro-West | 06.04.2015 | 0 |  | 256 | 3300 | 9 Hrs Agl. | 06.04.2015 | Ranga Reddy-West
220/132/33 KV SS Shamshabad | in force 82 T.O.O 205, 08-10-2013 | 2x31.5 | 1x31.5+1x50 | 193 | 3310 | Metro-East | 13.01.2016 | 0 |  | 193 | 3310 | 9 Hrs Agl. | 13.01.2016 | Ranga Reddy-East
132 KV SS Pashamailaram | in force 82 T.O.O 205, 08-10-2013 | 1x50+1x31.5 | 1x50+2x31.5 | 232 | 5102 | Sangareddy | 19.11.2015 | 0 |  | 232 | 5102 | 9 Hrs Agl. | 19.11.2015 | Medak
132 KV SS RC Puram | in force 82 T.O.O 205, 08-10-2013 | 2x50+3x10/16 (132/11 KV) | 3x50+2x10/16 (instead of 3x50+3x10/16 (132/11 KV)) | 310 | 3300 | Metro-West | 10.04.2016 | 0 |  | 310 | 3300 | 9 Hrs Agl. | 10.04.2016 | Ranga Reddy-West
132 KV SS Bandlaguda | in force 82 T.O.O 110, 09-07-2013, | 1x80+2x50 | 2x80+1x50 | 267 | 3310 | Metro-East | 16.10.2015 | 0 |  | 267 | 3310 | 9 Hrs Agl. | 16.10.2015 | Ranga Reddy-East
132 KV SS Kandi | in force 82 T.O.O 418, 31-01-2012 | 2x50 | 3x50 | 301 | 5102 | Sangareddy | 12.08.2015 | 0 |  | 301 | 5102 | 9 Hrs Agl. | 12.08.2015 | Medak
132 KV SS Medak | in force 82 T.O.O 378, 17.01.2012, | 2x31.5 | 1x50+1x 31.5 | 194 | 5102 | Sangareddy | 11.04.2016 | 0 |  | 194 | 5102 | 9 Hrs Agl. | 11.04.2016 | Medak
132 KV SS Narsapur | in force 82 T.O.O 418, 31.01.2012 | 2x31.5 | 1x50+1x 31.5 | 190 | 5102 | Sangareddy | 04.03.2016 | 0 |  | 190 | 5102 | 9 Hrs Agl. | 04.03.2016 | Medak
132 KV SS Siddipet | in force 82 T.O.O 4, 30-06-2014 | 1x50 +2x31.5 +1x10/16 (132/11KV) | 1x50+3x31.5 | 150.94 | 5102 | Sangareddy | 16.03.2016 | 0 |  | 150.94 | 5102 | 9 Hrs Agl. | 16.03.2016 | Medak
220 KV SS Narketpally | in force 82 T.O.O 40, 25-02-2015 | 1x160+2x100 | 2x160+1x100 | 520 | 5112 | Nalgonda | 20.05.2016 | 0 |  | 520 | 5112 | 9 Hrs Agl. | 20.05.2016 | Nalgonda
132 KV SS Choutuppal | in force 82 T.O.O 40, 25-02-2015 | 2x31.5 | 1x50+1x31.5 | 228 | 5112 | Nalgonda | 29.02.2016 | 0 |  | 228 | 5112 | 9 Hrs Agl. | 29.02.2016 | Nalgonda
220 KV SS Bhongiri | in force 82 T.O.O 152, 13-08-2013 | 2x100 | 3x100 | 621 | 5112 | Nalgonda | 16.04.2016 | 0 |  | 621 | 5112 | 9 Hrs Agl. | 16.04.2016 | Nalgonda
132 KV SS Kodada | in force 82 T.O.O 152, 13-08-2013 | 2x31.5 | 2x50 | 211 | 5112 | Nalgonda | 24.08.2015 | 211 |  | 422 | 5112 | 9 Hrs Agl. | 24.08.2015 | Nalgonda
132 KV SS Kodada | in force 82 T.O.O 152, 13-08-2013 | 2x31.5 | 2x50 | 211 | 5112 | Nalgonda | 25.01.2016 | -211 |  |  | 5112 | 9 Hrs Agl. | 25.01.2016 | Nalgonda
220 KV SS Kalwakurthy | in force 82 T.O.O 489, 24-02-2011 | 3x31.5 | 2x50+1x31.5 | 440 | 5113 | Mahaboobnagar | 31.12.2015 | 0 |  | 440 | 5113 | 9 Hrs Agl. | 31.12.2015 | Mahaboobnagar
220 KV SS Budidampadu | T.O.O Ms. No.83, Dt:01.05.2015 | 2x100 | 2x160 | 502.13 | 5121 | Khammam | 10.03.2016 | 502.13 |  | 1004.26 | 5121 | 9 Hrs Agl. | 10.03.2016 | Khammam
220 KV SS Budidampadu | T.O.O Ms. No.83, Dt:01.05.2015 | 2x100 | 2x160 | 502.13 | 5121 | Khammam | 08.06.2016 | -502.13 |  |  | 5121 | 9 Hrs Agl. | 08.06.2016 | Khammam
220 KV SS Manuguru | T.O.O Ms. No.83, Dt:01.05.2015 | 2x100 | 2x160 | 502.13 | 5121 | Khammam | 12.02.2016 | 502.13 |  | 1004.26 | 5121 | 9 Hrs Agl. | 12.02.2016 | Khammam
220 KV SS Manuguru | T.O.O Ms. No.83, Dt:01.05.2015 | 2x100 | 2x160 | 502.13 | 5121 | Khammam | 31.03.2016 | -502.13 |  |  | 5121 | 9 Hrs Agl. | 31.03.2016 | Khammam
220 KV SS Seetharampatnam | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+1x31.5 | 2x50 | 204.71 | 5121 | Khammam | 02.12.2015 | 0 |  | 204.71 | 5121 | 9 Hrs Agl. | 02.12.2015 | Khammam
220 KV SS Manuguru | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x50 | 231.425 | 5121 | Khammam | 30.03.2016 | 231.425 |  | 462.85 | 5121 | 9 Hrs Agl. | 30.03.2016 | Khammam
220 KV SS Manuguru | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x50 | 231.425 | 5121 | Khammam |  | -231.425 |  |  | 5121 | 9 Hrs Agl. |  | Khammam
132 KV SS Aswaraopet | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5121 | Khammam | 24.12.2015 | 0 |  | 145.03 | 5121 | 9 Hrs Agl. | 24.12.2015 | Khammam
132 KV SS Penubally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 2x50 | 197.8 | 5121 | Khammam | 12.12.2015 | 197.8 |  | 395.6 | 5121 | 9 Hrs Agl. | 12.12.2015 | Khammam
132 KV SS Penubally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 2x50 | 197.8 | 5121 | Khammam | 18.03.2016 | -197.8 |  |  | 5121 | 9 Hrs Agl. | 18.03.2016 | Khammam
132 KV SS Madira | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 138.465 | 5121 | Khammam | 31.12.2015 | 138.465 |  | 276.93 | 5121 | 9 Hrs Agl. | 31.12.2015 | Khammam
132 KV SS Madira | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 138.465 | 5121 | Khammam | 23.02.2016 | -138.465 |  |  | 5121 | 9 Hrs Agl. | 23.02.2016 | Khammam
132 KV SS Kusumanchi | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 2x50 | 197.8 | 5121 | Khammam | 04.11.2015 | 197.8 |  | 395.6 | 5121 | 9 Hrs Agl. | 04.11.2015 | Khammam
132 KV SS Kusumanchi | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 2x50 | 197.8 | 5121 | Khammam | 19.02.2016 | -197.8 |  |  | 5121 | 9 Hrs Agl. | 19.02.2016 | Khammam
132 KV SS Yellandu | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5121 | Khammam | 18.01.2016 | 0 |  | 145.03 | 5121 | 9 Hrs Agl. | 18.01.2016 | Khammam
132 KV SS B.Gangaram | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 220.115 | 5121 | Khammam | 13.11.2015 | 220.115 |  | 440.23 | 5121 | 9 Hrs Agl. | 13.11.2015 | Khammam
132 KV SS B.Gangaram | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 220.115 | 5121 | Khammam | 02.01.2016 | -220.115 |  |  | 5121 | 9 Hrs Agl. | 02.01.2016 | Khammam
132 KV SS Tallada | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5121 | Khammam | 04.11.2015 | 0 |  | 145.03 | 5121 | 9 Hrs Agl. | 04.11.2015 | Khammam
220/132/33 KV SS Warangal | T.O.O Ms. No.83, Dt:01.05.2015 | 1x160+2x100 | 3x160 | 503.635 | 5101 | Warangal | 06.03.2016 | 503.635 |  | 1007.27 | 5101 | 9 Hrs Agl. | 06.03.2016 | Warangal
220/132/33 KV SS Warangal | T.O.O Ms. No.83, Dt:01.05.2015 | 1x160+2x100 | 3x160 | 503.635 | 5101 | Warangal | 30.05.2016 | -503.635 |  |  | 5101 | 9 Hrs Agl. | 30.05.2016 | Warangal
220/132/33 KV SS Waddekothapally | T.O.O Ms. No.83, Dt:01.05.2015 | 3x100 | 3x160 | 504.1333 | 5101 | Warangal | 24.11.2015 | 1008.2667 |  | 1512.4 | 5101 | 9 Hrs Agl. | 24.11.2015 | Warangal
220/132/33 KV SS Waddekothapally | T.O.O Ms. No.83, Dt:01.05.2015 | 3x100 | 3x160 | 504.1333 | 5101 | Warangal | 06.02.2016 | -504.1333 |  |  | 5101 | 9 Hrs Agl. | 06.02.2016 | Warangal
220/132/33 KV SS Waddekothapally | T.O.O Ms. No.83, Dt:01.05.2015 | 3x100 | 3x160 | 504.1333 | 5101 | Warangal | 25.04.2016 | -504.1333 |  |  | 5101 | 9 Hrs Agl. | 25.04.2016 | Warangal
132 KV SS Narsampet | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x31.5 | 263.39 | 5101 | Warangal | 01.02.2016 | 0 |  | 263.39 | 5101 | 9 Hrs Agl. | 01.02.2016 | Warangal
132 KV SS Pedda Nagaram | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 1x50+1x31.5 | 239.09 | 5101 | Warangal | 14.03.2016 | 0 |  | 239.09 | 5101 | 9 Hrs Agl. | 14.03.2016 | Warangal
132/33 KV SS Waddepally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x50 | 242.7 | 5101 | Warangal | 15.03.2016 | 485.4 |  | 728.1 | 5101 | 9 Hrs Agl. | 15.03.2016 | Warangal
132/33 KV SS Waddepally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x50 | 242.7 | 5101 | Warangal | 22.03.2016 | -242.7 |  |  | 5101 | 9 Hrs Agl. | 22.03.2016 | Warangal
132/33 KV SS Waddepally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x50 | 242.7 | 5101 | Warangal | 26.04.2016 | -242.7 |  |  | 5101 | 9 Hrs Agl. | 26.04.2016 | Warangal
132 KV SS Raghunathpally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x50 | 242.7 | 5101 | Warangal | 06.11.2015 | 485.4 |  | 728.1 | 5101 | 9 Hrs Agl. | 06.11.2015 | Warangal
132 KV SS Raghunathpally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x50 | 242.7 | 5101 | Warangal | 18.01.2016 | -242.7 |  |  | 5101 | 9 Hrs Agl. | 18.01.2016 | Warangal
132 KV SS Raghunathpally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x50 | 242.7 | 5101 | Warangal | 27.02.2016 | -242.7 |  |  | 5101 | 9 Hrs Agl. | 27.02.2016 | Warangal
132 KV SS Mulugu | T.O.O Ms. No.83, Dt:01.05.2015 | 3x10/16 | 3x31.5 | 143.04 | 5101 | Warangal | 07.04.2016 | 286.08 |  | 429.12 | 5101 | 9 Hrs Agl. | 07.04.2016 | Warangal
132 KV SS Mulugu | T.O.O Ms. No.83, Dt:01.05.2015 | 3x10/16 | 3x31.5 | 143.04 | 5101 | Warangal | 01.01.2016 | -143.04 |  |  | 5101 | 9 Hrs Agl. | 01.01.2016 | Warangal
132 KV SS Mulugu | T.O.O Ms. No.83, Dt:01.05.2015 | 3x10/16 | 3x31.5 | 143.04 | 5101 | Warangal | 13.11.2015 | -143.04 |  |  | 5101 | 9 Hrs Agl. | 13.11.2015 | Warangal
132 KV SS Kamalapur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 3x31.5 | 179.6067 | 5101 | Warangal | 28.03.2016 | 359.2133 |  | 538.82 | 5101 | 9 Hrs Agl. | 28.03.2016 | Warangal
132 KV SS Kamalapur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 3x31.5 | 179.6067 | 5101 | Warangal | 11.04.2016 | -179.6067 |  |  | 5101 | 9 Hrs Agl. | 11.04.2016 | Warangal
132 KV SS Kamalapur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 3x31.5 | 179.6067 | 5101 | Warangal | 14.07.2016 | -179.6067 |  |  | 5101 | 9 Hrs Agl. | 14.07.2016 | Warangal
132 KV SS Chityala | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x50 | 231.425 | 5101 | Warangal | 31.12.2015 | 231.425 |  | 462.85 | 5101 | 9 Hrs Agl. | 31.12.2015 | Warangal
132 KV SS Chityala | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x50 | 231.425 | 5101 | Warangal | 17.02.2016 | -231.425 |  |  | 5101 | 9 Hrs Agl. | 17.02.2016 | Warangal
220/132 KV SS Durshed | T.O.O Ms. No.83, Dt:01.05.2015 | 3x100 | 3x160 | 503.1333 | 5111 | Karimnagar | 30.12.2015 | 1006.2667 |  | 1509.4 | 5111 | 9 Hrs Agl. | 30.12.2015 | Karimnagar
220/132 KV SS Durshed | T.O.O Ms. No.83, Dt:01.05.2015 | 3x100 | 3x160 | 503.1333 | 5111 | Karimnagar | 23.02.2016 | -503.1333 |  |  | 5111 | 9 Hrs Agl. | 23.02.2016 | Karimnagar
220/132 KV SS Durshed | T.O.O Ms. No.83, Dt:01.05.2015 | 3x100 | 3x160 | 503.1333 | 5111 | Karimnagar | 14.03.2016 | -503.1333 |  |  | 5111 | 9 Hrs Agl. | 14.03.2016 | Karimnagar
220/132 KV SS Jagitial | T.O.O Ms. No.83, Dt:01.05.2015 | 2x100 | 3x100 | 590.32 | 5111 | Karimnagar | 19.03.2016 | 0 |  | 590.32 | 5111 | 9 Hrs Agl. | 19.03.2016 | Karimnagar
132 KV SS Suglampally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 1x50+2x31.5 | 339.82 | 5111 | Karimnagar | 17.03.2016 | 0 |  | 339.82 | 5111 | 9 Hrs Agl. | 17.03.2016 | Karimnagar
132 KV SS Karimnagar | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+1x31.5 | 1x50+1x31.5+1x10/16 (instead of 2 x 50) | 201.46 | 5111 | Karimnagar | 31.03.2016 | 0 |  | 201.46 | 5111 | 9 Hrs Agl. | 31.03.2016 | Karimnagar
132 KV SS Siricilla | T.O.O Ms. No.83, Dt:01.05.2015 | 2x50 | 1x80+2x50 | 430.94 | 5111 | Karimnagar | 22.02.2016 | 0 |  | 430.94 | 5111 | 9 Hrs Agl. | 22.02.2016 | Karimnagar
132 KV SS Mallaram | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5111 | Karimnagar | 24.02.2016 | 0 |  | 145.03 | 5111 | 9 Hrs Agl. | 24.02.2016 | Karimnagar
132 KV SS Yellareddypet | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x25 | 2x31.5+1x25 | 265.87 | 5111 | Karimnagar | 25.06.2016 | 0 |  | 265.87 | 5111 | 9 Hrs Agl. | 25.06.2016 | Karimnagar
132 KV SS Shanigaram | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 282.75 | 5111 | Karimnagar | 30.09.2015 | 0 |  | 282.75 | 5111 | 9 Hrs Agl. | 30.09.2015 | Karimnagar
132 KV SS Ellanthakunta | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5111 | Karimnagar | 29.02.2016 | 0 |  | 145.03 | 5111 | 9 Hrs Agl. | 29.02.2016 | Karimnagar
132 KV SS Mulkanoor | T.O.O Ms. No.83, Dt:01.05.2015 | 1x10/16 | 1x31.5+1x10/16 | 195.03 | 5111 | Karimnagar | 25.02.2016 | 0 |  | 195.03 | 5111 | 9 Hrs Agl. | 25.02.2016 | Karimnagar
132 KV SS Husnabad | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x31.5 | 263.39 | 5111 | Karimnagar | 16.03.2016 | 0 |  | 263.39 | 5111 | 9 Hrs Agl. | 16.03.2016 | Karimnagar
132 KV SS Water Works (Karimnagar) | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5 | 2x31.5 | 193.78 | 5111 | Karimnagar | 11.05.2015 | 0 |  | 193.78 | 5111 | 9 Hrs Agl. | 11.05.2015 | Karimnagar
132 KV SS Jagitial | T.O.O Ms. No.83, Dt:01.05.2015 | 2x50 | 3x50 | 271.67 | 5111 | Karimnagar | 08.12.2015 | 0 |  | 271.67 | 5111 | 9 Hrs Agl. | 08.12.2015 | Karimnagar
132 KV SS Korutla | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+1x31.5 | 2x50 | 201.46 | 5111 | Karimnagar | 12.01.2016 | 0 |  | 201.46 | 5111 | 9 Hrs Agl. | 12.01.2016 | Karimnagar
132 KV SS Godur | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5111 | Karimnagar | 19.11.2015 | 0 |  | 145.03 | 5111 | 9 Hrs Agl. | 19.11.2015 | Karimnagar
132 KV SS Dharmaram | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5 + 1x10/16 | 2x31.5 | 145.03 | 5111 | Karimnagar | 17.11.2015 | 0 |  | 145.03 | 5111 | 9 Hrs Agl. | 17.11.2015 | Karimnagar
132 KV SS Pudur | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5111 | Karimnagar | 26.11.2015 | 0 |  | 145.03 | 5111 | 9 Hrs Agl. | 26.11.2015 | Karimnagar
132 KV SS Dharmapuri | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 3x31.5 | 200.55 | 5111 | Karimnagar | 16.12.2015 | 200.55 |  | 401.1 | 5111 | 9 Hrs Agl. | 16.12.2015 | Karimnagar
132 KV SS Dharmapuri | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 3x31.5 | 200.55 | 5111 | Karimnagar | 28.06.2016 | -200.55 |  |  | 5111 | 9 Hrs Agl. | 28.06.2016 | Karimnagar
132 KV SS Kamalapur | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5111 | Karimnagar | 11.01.2016 | 0 |  | 145.03 | 5111 | 9 Hrs Agl. | 11.01.2016 | Karimnagar
132 KV SS Manthani | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 210.05 | 5111 | Karimnagar | 28.11.2015 | 210.05 |  | 420.1 | 5111 | 9 Hrs Agl. | 28.11.2015 | Karimnagar
132 KV SS Manthani | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x50 | 210.05 | 5111 | Karimnagar | 30.12.2015 | -210.05 |  |  | 5111 | 9 Hrs Agl. | 30.12.2015 | Karimnagar
132 KV SS Kataram | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 1x50+1x31.5 | 185.085 | 5111 | Karimnagar | 08.08.2015 | 185.085 |  | 370.17 | 5111 | 9 Hrs Agl. | 08.08.2015 | Karimnagar
132 KV SS Kataram | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 1x50+1x31.5 | 185.085 | 5111 | Karimnagar | 20.01.2016 | -185.085 |  |  | 5111 | 9 Hrs Agl. | 20.01.2016 | Karimnagar
132 KV SS Kalwasrirampur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 1x50+1x31.5 | 185.085 | 5111 | Karimnagar | 11.01.2016 | 185.085 |  | 370.17 | 5111 | 9 Hrs Agl. | 11.01.2016 | Karimnagar
132 KV SS Kalwasrirampur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 1x50+1x31.5 | 185.085 | 5111 | Karimnagar | 18.01.2016 | -185.085 |  |  | 5111 | 9 Hrs Agl. | 18.01.2016 | Karimnagar
220/132 KV SS Bheemgal | T.O.O Ms. No.83, Dt:01.05.2015 | 2x100 | 1x160+1x100 | 502.88 | 5106 | Nizamabad | 19.02.2016 | 0 |  | 502.88 | 5106 | 9 Hrs Agl. | 19.02.2016 | Nizamabad
220/132 KV SS Dichpally | T.O.O Ms. No.83, Dt:01.05.2015 | 1x160+2x100 | 2x160+1x100 | 502.88 | 5106 | Nizamabad | 06.04.2016 | 0 |  | 502.88 | 5106 | 9 Hrs Agl. | 06.04.2016 | Nizamabad
132 KV SS Bheemgal | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+1x31.5 | 2x50 | 201.46 | 5106 | Nizamabad | 12.01.2016 | 0 |  | 201.46 | 5106 | 9 Hrs Agl. | 12.01.2016 | Nizamabad
132 KV SS Sirikonda | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5106 | Nizamabad | 19.03.2016 | 0 |  | 145.03 | 5106 | 9 Hrs Agl. | 19.03.2016 | Nizamabad
132 KV SS Morthad | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5106 | Nizamabad | 19.11.2015 | 0 |  | 145.03 | 5106 | 9 Hrs Agl. | 19.11.2015 | Nizamabad
132 KV SS Bussapur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 1x50+1x31.5 | 212.46 | 5106 | Nizamabad | 31.03.2016 | 0 |  | 212.46 | 5106 | 9 Hrs Agl. | 31.03.2016 | Nizamabad
132 KV SS Dichpally | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 1x50+1x31.5 | 212.46 | 5106 | Nizamabad | 06.02.2016 | 0 |  | 212.46 | 5106 | 9 Hrs Agl. | 06.02.2016 | Nizamabad
132 KV SS Nizamabad. | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+2x31.5 | 3x50 | 214.59 | 5106 | Nizamabad | 10.11.2015 | 0 |  | 214.59 | 5106 | 9 Hrs Agl. | 10.11.2015 | Nizamabad | Total 429.18
132 KV SS Nizamabad. | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+2x31.5 | 3x50 | 214.59 | 5106 | Nizamabad | 17.02.2016 | 0 |  | 214.59 | 5106 | 9 Hrs Agl. | 17.02.2016 | Nizamabad
132 KV SS Renjal | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 1x50+1x31.5 | 212.46 | 5106 | Nizamabad | 17.12.2015 | 0 |  | 212.46 | 5106 | 9 Hrs Agl. | 17.12.2015 | Nizamabad
132 KV SS Nandipet | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+1x31.5 | 2x50 | 201.46 | 5106 | Nizamabad | 09.01.2016 | 0 |  | 201.46 | 5106 | 9 Hrs Agl. | 09.01.2016 | Nizamabad
132 KV SS Jakora | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+1x31.5 | 2x50 | 201.46 | 5106 | Nizamabad | 19.11.2015 | 0 |  | 201.46 | 5106 | 9 Hrs Agl. | 19.11.2015 | Nizamabad
132 KV SS Lingampet | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5106 | Nizamabad | 20.01.2016 | 0 |  | 145.03 | 5106 | 9 Hrs Agl. | 20.01.2016 | Nizamabad
132 KV SS Bhiknoor | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 1x31.5+1x10/16 | 145.03 | 5106 | Nizamabad | 04.03.2016 | 0 |  | 145.03 | 5106 | 9 Hrs Agl. | 04.03.2016 | Nizamabad
132/33 KV SS Reddypet | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 1x31.5+1x10/16 | 145.03 | 5106 | Nizamabad | 18.03.2016 | 0 |  | 145.03 | 5106 | 9 Hrs Agl. | 18.03.2016 | Nizamabad
132 KV SS Nizamsagar | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5106 | Nizamabad | 21.12.2015 | 0 |  | 145.03 | 5106 | 9 Hrs Agl. | 21.12.2015 | Nizamabad
132 KV SS Banswada | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x10/16 | 2x31.5 | 145.03 | 5106 | Nizamabad | 03.02.2016 | 0 |  | 145.03 | 5106 | 9 Hrs Agl. | 03.02.2016 | Nizamabad
220/132/33 KV SS Nirmal | T.O.O Ms. No.83, Dt:01.05.2015 | 2x100 | 3x100 | 590.32 | 5122 | Adilabad | 18.03.2016 | 0 |  | 590.32 | 5122 | 9 Hrs Agl. | 18.03.2016 | Adilabad
132/33 KV SS Nirmal | T.O.O Ms. No.83, Dt:01.05.2015 | 1x50+1x31.5 | 2x50+1x31.5 | 347.86 | 5122 | Adilabad | 29.02.2016 | 0 |  | 347.86 | 5122 | 9 Hrs Agl. | 29.02.2016 | Adilabad
132 KV SS Bhainsa | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 1x50+1x31.5 | 203.71 | 5122 | Adilabad | 22.01.2016 | 0 |  | 203.71 | 5122 | 9 Hrs Agl. | 22.01.2016 | Adilabad
132 KV SS Adilabad | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 3x31.5 (instead of 1x50+1x31.5) | 203.71 | 5122 | Adilabad |  | 0 |  | 203.71 | 5122 | 9 Hrs Agl. |  | Adilabad
132 KV SS Mancherial | T.O.O Ms. No.83, Dt:01.05.2015 | 2x31.5 | 1x50+1x31.5 | 203.71 | 5122 | Adilabad | 30.01.2016 | 0 |  | 203.71 | 5122 | 9 Hrs Agl. | 30.01.2016 | Adilabad
132 KV SS Bellampally | T.O.O Ms. No.83, Dt:01.05.2015 | 1x31.5+1x15 | 2x31.5 | 145.03 | 5122 | Adilabad | 04.03.2016 | 0 |  | 145.03 | 5122 | 9 Hrs Agl. | 04.03.2016 | Adilabad
132 KV SS Chennur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 141.375 | 5122 | Adilabad | 01.03.2016 | 141.375 | 141.375 | 282.75 | 5122 | 9 Hrs Agl. | 01.03.2016 | Adilabad
132 KV SS Chennur | T.O.O Ms. No.83, Dt:01.05.2015 | 2x10/16 | 2x31.5 | 141.375 | 5122 | Adilabad | 22.03.2016 | -141.375 |  |  | 5122 | 9 Hrs Agl. | 22.03.2016 | Adilabad
132 KV SS Khammam | Are in force-83 T.O.O 57, 26-03-2015 | 2x50+1x31.5 | 3x50+1x31.5 (instead of 3x50) | 201 | 5121 | Khammam |  | 201 |  | 402 | 5121 | 9 Hrs Agl. |  | Khammam
220/132/33 KV SS Warangal | Are in force-83 T.O.O 152, 13-08-2013 | 1x80 + 1x50 | 1x80 + 2x50 | 310 | 5101 | Warangal | 04.05.2016 | 0 |  | 310 | 5101 | 9 Hrs Agl. | 04.05.2016 | Warangal
132 KV SS Narsampet | Are in force-83 T.O.O 82, 20-06-2013, for 2nd31.5MVA | 1x31.5+1x10/16 | 2x31.5 | 142 | 5101 | Warangal | 26.03.2016 | 0 |  | 142 | 5101 | 9 Hrs Agl. | 26.03.2016 | Warangal
132 KV SS Pedda Nagaram | Are in force-83 T.O.O 110, 09.07.2013, for 1 No. 31.5MVA | 2x10/16 | 1x31.5+1x10/16 | 142 | 5101 | Warangal | 26.02.2016 | 0 |  | 142 | 5101 | 9 Hrs Agl. | 26.02.2016 | Warangal
132 KV SS Chelpur | Are in force-83 T.O.O 47, 04-06-2008 | 1x31.5+1x10/16 | 1x50+1x31.5 | 435 | 5101 | Warangal | 28.04.2016 | 0 |  | 435 | 5101 | 9 Hrs Agl. | 28.04.2016 | Warangal
132 KV SS Shanigaram | Are in force-83 T.O.O 82, 20-06-2013, for 1No.31.5MVA | 2x10/16 | 1x31.5+1x10/16 | 142 | 5111 | Karimnagar | 29.01.2016 | 0 |  | 142 | 5111 | 9 Hrs Agl. | 29.01.2016 | Karimnagar
132 KV SS Manakondur | Are in force-83 T.O.O 82, 20-06-2013 | 2x10/16 | 1x31.5+1x10/16 | 142 | 5111 | Karimnagar | 19.06.2015 | 0 |  | 142 | 5111 | 9 Hrs Agl. | 19.06.2015 | Karimnagar
132 KV SS Huzurabad | Are in force-83 T.O.O 84, 22-07-2008 | 1x31.5 + 1x10/16 | 2 x 31.5 | 218 | 5111 | Karimnagar | 25.02.2016 | 0 |  | 218 | 5111 | 9 Hrs Agl. | 25.02.2016 | Karimnagar
132 KV SS Jagitial | Are in force-83 T.O.O 84, 22-07-2008, for 2nd 50MVA | 1x50+1x31.5 | 2x50 | 397 | 5111 | Karimnagar | 31.03.2016 | 0 |  | 397 | 5111 | 9 Hrs Agl. | 31.03.2016 | Karimnagar
132 KV SS Dharmapuri | Are in force-83 T.O.O 84, 22-07-2008, for 1No.31.5MVA | 2x10/16 | 1x31.5+1x10/16 | 218 | 5111 | Karimnagar | 08.06.2015 | 0 |  | 218 | 5111 | 9 Hrs Agl. | 08.06.2015 | Karimnagar
132 KV SS Jammikunta | Are in force-83 T.O.O 84, 22-07-2008, for 1No.31.5MVA | 2x31.5 | 1x50+1x31.5 | 397 | 5111 | Karimnagar | 19.12.2015 | 0 |  | 397 | 5111 | 9 Hrs Agl. | 19.12.2015 | Karimnagar
132 KV SS RTS-B | Are in force-83 T.O.O 385, 07-03-2013 | 1x31.5+1x10/16 | 2x31.5 | 146 | 5111 | Karimnagar | 25.01.2016 | 0 |  | 146 | 5111 | 9 Hrs Agl. | 25.01.2016 | Karimnagar
132 KV SS Armoor | Are in force-83 T.O.O 110, 09-07-2013 | 1x31.5+1x10/16 | 2x31.5 | 142 | 5106 | Nizamabad | 05.01.2016 | 0 |  | 142 | 5106 | 9 Hrs Agl. | 05.01.2016 | Nizamabad
132 KV SS Bodhan | Are in force-83 T.O.O 110, 09-07-2013 | 2 x 10/16 | 1x31.5+1x10/16 | 142 | 5106 | Nizamabad | 04.05.2016 | 0 |  | 142 | 5106 | 9 Hrs Agl. | 04.05.2016 | Nizamabad
132 KV SS Bichkunda | Are in force-83 T.O.O 54, 21-05-2012 | 2 x 10/16 | 1x31.5+1x10/16 | 160 | 5106 | Nizamabad | 09.10.2015 | 0 |  | 160 | 5106 | 9 Hrs Agl. | 09.10.2015 | Nizamabad
132 KV SS Domakonda | Are in force-83 T.O.O 131, 01-10-2009 | 2 x 31.5 | 1x50+1x31.5 | 309 | 5106 | Nizamabad | 06.11.2015 | 0 |  | 309 | 5106 | 9 Hrs Agl. | 06.11.2015 | Nizamabad
220/132 KV SS Mandamarry (Bellampally) | Are in force-83 T.O.O 29, 03-05-2012 | 1x100 | 2 X 100 | 396 | 5122 | Adilabad | 07.09.2015 | 0 |  | 396 | 5122 | 9 Hrs Agl. | 07.09.2015 | Adilabad
132 KV SS Ichoda | Are in force-83 T.O.O 313, 18-01-2013 | 2x10/16 | 3x10/16 | 61 | 5122 | Adilabad | 26.03.2016 | 0 |  | 61 | 5122 | 9 Hrs Agl. | 26.03.2016 | Adilabad
132 KV SS Luxettipet | Are in force-83 T.O.O 110, 09-07-2013 | 2x10/16 | 1x31.5+1x10/16 | 142 | 5122 | Adilabad | 14.10.2015 | 0 |  | 142 | 5122 | 9 Hrs Agl. | 14.10.2015 | Adilabad
132/33 KV SS Sirpur Kagaznagar | Are in force-83 T.O.O 110, 09-07-2013 | 2x10/16 | 1x31.5+1x10/16 | 142 | 5122 | Adilabad | 06.03.2016 | 0 |  | 142 | 5122 | 9 Hrs Agl. | 06.03.2016 | Adilabad
220 KV SS Kosigi (Upcoming) | [7 empty] | 0 |  |  |  | 9 Hrs Agl.
220 KV SS Parigi | [11 empty] | 9 Hrs Agl.
220 KV SS Chandrayanagutta | [11 empty] | 9 Hrs Agl.
220 KV SS Huzurabad (Upcoming) | [11 empty] | 9 Hrs Agl.
220 KV SS Manthani (Up-coming) | [11 empty] | 9 Hrs Agl.
132 KV SS Adilabad (failed PTR ) | [11 empty] | 9 Hrs Agl.
132 KV SS Ghanapur | [11 empty] | 9 Hrs Agl.
132 KV SS Khanapur | [11 empty] | 9 Hrs Agl.
220 KV SS Sitapuram (Up-coming) | [11 empty] | 9 Hrs Agl.
220 KV SS Sitapuram (Up-coming) | [11 empty] | 9 Hrs Agl.
220 KV SS Fabcity | [11 empty] | 9 Hrs Agl.
132KV SS Mamidipally (UP-coming) | [11 empty] | 9 Hrs Agl.
| Total in Lakhs | [8 empty] | 88007.65 |  | 80.22 Crores

## Sheet2
24.73 | 8.12
0.02 | 0.06
0.11 | 0.12
0.003 | -0.05
0.08
0.49
24.863 | 8.82