## 2019-20.
1.1D ABSTRACT OF INVESTMENT PLAN ( FY 2019-20 ) OF CE/CONSTRUCTION
|  |  | Financial Year 2019-20 | [26 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Expenditure from 01.04.2019 to 25.10.2019 | Anticipated Expenditure from 26.10.2019 to 31.03.2020 | Investments proposed for the year |  |  |  | Cumulativ e Expenditure as on 31.03.2019 |  |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
[14 empty] | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt component of capex in year
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  |  | Loan Amount (Crores) | Interest Rate | Moratorium period | Repayment period | Loan source |  |  | Proposed investment in the year(Rs. Crores) | Proposed IDC | Proposed other expence | % Capatalisation | OPENING BALANCE | Actual investment | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 | TOO MS.NO.11 dt:07.03.2014 | S-10-17 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 KV Substation at N V Puram in Khammam District | System Improvement | 07.08.2016 | 31.03.2020 | 19.9462 | 0.59838 | 1.9946 | 1.2466 | 2.1442 | 25.93 |  |  | 10.55 |  |  |  | REC | 2.88 | 1.68 | 4.56 |  |  |  |  | 20.65 |  |  |  | 25.21
2 | T.O.O (CE-Construction) MS.No .82 Dated:18.04.2018 | S-11-11 | CRN.No.TST/TS132 kV SSt Donthanpalli/F-INVST-06/2013/Dt:08.10.2014 | 132 kV DC line from the proposed 220/132/33 kV SS Parigi to 132/33 kV SS Dharmasagar (132/33 kV Substation at Donthanpalli ) | System Improvement | 13.12.2016 | 31.03.2020 | 15.9462 | 0.47838 | 1.5946 | 0.99663 | 1.7142 | 20.73 |  |  | 19.2627 |  |  |  | REC | 0.65 | 4.767 | 5.417 |  |  |  |  | 3.14 |  |  |  | 8.557 |  |  |  |  | 39.5499
3 | TOO (CE-Construction) MS NO.83, Dt:21.06.2013 | S-11-16 | CRN.No.APT/TS/220/132 kV SS-Huzurnagar/F-INVST-01/2014/Dt:20.04.2013 | 220/132/33 kV substation at Huzurnagar in Nalgonda District | System Improvement | 31.10.2013 | 31.03.2020 | 45.75 | 1.37 | 5.49 | 2.86 | 4.92 | 60.39 |  |  | 62.65 |  |  |  | PFC | 1.11 | 5.628 | 6.738 |  |  |  |  | 12.04 |  |  |  | 18.778
4 | TOO (CE-Transmission) MS.NO.161 dt:26-08-2015 | S-11-28 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Nimmapalli with connected line in Karimnagar Dist | System Improvement | 23.03.2018 | 31.03.2020 | 18.4688 | 0.2546 | 1.97 | 0.0644 | 0.9122 | 21.67 |  |  | 17.73 |  |  |  | REC | 2.03 | 7.805 | 9.835 |  |  |  |  | 8.49 |  |  |  | 18.325
5 | TOO 61, Dt:25.05.2012 | S-12-09 | APT/TS/132/Yeddumailram/F-INVST-27/2013 | 132 KV DC/SC inter linking lines between substations 220 KV Yeddumailram-132 KV Pashmailaram | System Improvement | 01.12.2018 | 30.09.2020 | 9.086 | 0.0462 | 0.931 | 0.0012 | 0.1766 | 10.241 | [6 empty] | NABARD | 0 | 4.9 | 4.9 |  |  |  |  | 0.02 |  |  |  | 4.92
6 | TOO (CE-Construction-I) MS NO.117, Dt:30.05.2014 | S-13-03 | CRN.No. APT/TS/220 KVSS -Bonguluru/F.Invest-27/2014 | 220/132/33KV SS at Bonguloor in RR District | System Improvement | 01.06.2014 | 31.03.2020 | 56.8088 | 2.1343 | 6.34 | 0.04328 | 4.4136 | 69.74 | [6 empty] | NABARD | 3.38 | 22.29 | 25.67 |  |  |  |  | 19.35 |  |  |  | 45.02
7 | T.O.O (CE-Construction-I) Ms.No. 347 Dated: 13.02.2013 SI13KANDUK | S-13-11 | TST/TS/132 kV SS-Kandukuru/ F-INVST-05/2015 | 132 kV SS Kandukuru & connected lines | System Improvement | 09.09.2016 | 31.03.2020 | 21.4404 | 0.27755 | 2.275 | 0.0024 | 1.0296 | 25.025 |  |  | 20.0578 |  |  |  | REC | 0.88 | 15.6205 | 16.5005 |  |  |  |  | 1.83 |  |  |  | 18.3305
8 | T.O.O (CE-Construction-I) MS.No.08 Dated: 26.02.2014 | S-14-05 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd circuit stringing on 132kV DC/SC line from 220kV Durshed SS to 132kV Water Works SS and 2 Nos. 132 kV bays at 220kV Durshed and 132kV Water works in Karimnagar Town substations | System Improvement | 03.03.2018 | 31.03.2020 | 2.025 | 0.06075 | 0.24 | 0.1215 | 0.21769 | 2.6649 |  |  | 2.1825 |  |  |  | REC | 0 | 0.96246 | 0.96246 |  |  |  |  | 1.29 |  |  |  | 2.2525 |  |  |  |  | 0.4863
9 | TOO 22 Dt:10.09.2014 | S-14-12 | APT/TS/132 KV SS Kaithlapur/F-INVST-4/2014 | 132 KV substation Khaithalapur aong with connected lines | System Improvement | 05.07.2016 | 31.08.2020 | 63.5174 | 0.50461 | 5.0851 | 0.1489 | 1.8691 | 71.1251 |  |  | 59.09 |  |  |  | REC | 4.61 | 4 | 8.61 |  |  |  |  | 47.04 |  |  |  | 55.65
10 | TOO / CE/Trans/ MS No. 156 Dated 19.08.2015 | S-15-01 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing second source of supply to 132/33 kV Sub-Station, Lalgadi Malakpet in Shameerpet Mandal of Ranga Reddy District | System Improvement | 20.10.2015 | 31.03.2020 | 7.0327 | 0.0559 | 0.731 | 0.0212 | 0.2002 | 8.041 |  |  | 6.2 |  |  |  | PFC | 0.49 | 1 | 1.49 |  |  |  |  | 8.56 |  |  |  | 10.05
11 | T.O.O (CE-Transmisssion) MS.No. 159 Dated: 24.08.2015 SI15ASWARA | S-15-02 | TST/TS/ 132/33 kV Aswaraopet SS Up-Gradation to 220/132 kV / F-INVST- 7/2015 | Up-Gradation of 132/33 kV SS Aswaraopet to 220/132 kV SS | System Improvement | 18.01.2017 | 31.03.2020 | 50.2217 | 0.5249 | 4.65 | 0.1926 | 1.8808 | 57.47 |  |  | 42.55 |  |  |  | PFC | 0.18 | 7.59 | 7.77 |  |  |  |  | 2.7 |  |  |  | 10.47
12 | TOO / CE/Trans/ MS No. 140 Dated 30.07.2015 SI15JANGAP | S-15-04 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Sub-Station at Jangapally of Bejjanki Mandal in Karimnagar District. | System Improvement | 03.03.2018 | 31.12.2019 | 18.2773 | 0.3138 | 1.7415 | 0.0749 | 1.1242 | 21.5317 |  |  | 16.68 |  |  |  | PFC | 0.57 | 7.0642 | 7.6342 |  |  |  |  | 10.87 |  |  |  | 18.5042
13 | TOO (CE-Construction) MS NO.2, Dt:03.01.2015 | S-15-05 | CRN TST/TS/132 KVSS -Kondapur/F.Invst.06/2015 | erection of 132/33 kV Substation at Kondapur Village of Dhanwada Mandal in Mahaboobnagar District along with connected lines | System Improvement | 23.03.2017 | 31.03.2020 | 22.8844 | 0.3506 | 1.886 | - | 1.255 | 26.376 |  |  | 21.7104 |  |  |  | REC | 1.16 | 5.75 | 6.91 |  |  |  |  | 1.29 |  |  |  | 8.2 |  |  |  |  | 11.2455
14 | TOO / CE/Trans/ MS No. 210 Dated 6.11.2015 SI15L2CNKT | S-15-06 S-15-35 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing of alternate supply to 132 /33 kV SS Chennur and 132/33 kV SS Kataram from 220/132 kV SS, Manthani under the program for providing 9.00 Hrs Day Time Supply for Agriculture. | System Improvement | 07.02.2018 | 31.03.2020 | 11.9197 | 0.0421 | 1.213 | 0.0178 | 0.1504 | 13.343 |  |  | 10.917 |  |  |  | REC | 0.26 | 6.8481 | 7.1081 |  |  |  |  | 3.3 |  |  |  | 10.4081 |  |  |  |  | 10.7243
15 | TOO (CE-Construction-I) MS NO.55, Dt:25.03.2015 | S-15-31 | CRN.No.TST/TSAsifnagar SS alternatesource of supply/Invest.App.06/2015 | erection of 2nd circuit from 220kV Shivarampally SS to 132kV Asifnagar SS for providing 2nd source of supply to 132kV Asifnagar substation | System Improvement | 16.02.2018 | 31.03.2020 | 43.7987 | 0.4071 | 4.0454 | 0.2972 | 1.467 | 50.0154 |  |  | 41.3635 |  |  |  | REC | 1.42 | 10 | 11.42 |  |  |  |  | 19.53 |  |  |  | 30.95 |  |  |  |  | 37.8859
16 | TOO (CE-Transmission) MS.NO.231 dt:21-12-2015 | S-15-33 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Sarangapur in Adilabad District | System Improvement | 04.04.2018 | 31.01.2020 | 18.4173 | 0.3138 | 1.8685 | 0.0749 | 1.1242 | 21.7987 |  |  | 17.66 |  |  |  | REC | 1.74 | 3.63 | 5.37 |  |  |  |  | 10.59 |  |  |  | 15.96
17 | TOO (CE-Tr) MS NO.225, Dt:10.12.2015 | S-15-34 | CRN.No.TST/TS/Erection of 220 KV DC line Gajwel/Siddipet/Invest.App.04/17-2017-18 | 220 KV D/C Line from 400KV GAJWEL-SIDDIPET | System Improvement | 05.12.2017 | 31.12.2020 | 37.8541 | 0.0515 | 3.8117 | 0.0198 | 0.1846 | 41.9217 |  |  | 74.97 |  |  |  | REC | 5.8 | 8.4 | 14.2 |  |  |  |  | 26.31 |  |  |  | 40.51
18 | T.O.O (CE-Transmission) Ms.No.195 Dated:14.10.2015 | S-15-36 | TST/TS /132/33 kV SS Aipoor , Nalgonda /F-INVST- 01/2016-17 | 132/33 kV SS at Aipoor in Nalgonda district | System Improvement | 05.01.2017 | 31.03.2022 | 19.6933 | 0.3366 | 2.13 | 0.0841 | 1.2057 | 23.4497 |  |  | 18.9106 |  |  |  | REC | 0 | 0.1 | 0.1 |  |  |  |  | 0.15 |  |  |  | 0.25
19 | T.O.O (CE-Construction) MS. No. 137 Dated: 29.07.2015 | S-15-37 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection 132 kV line from 220 kV Jurala Sub-Station to 132 kV Ieeza Sub-Station under the program of providing 9.00 Hrs agricultural supply during day time | System Improvement | 12.03.2018 | 31.03.2020 | 16.3816 | 0.0318 | 1.64 | 0.0128 | 0.1138 | 18.18 |  |  | 30.5565 |  |  |  | REC | 2.78 | 2.31 | 5.09 |  |  |  |  | 12.1 |  |  |  | 17.19 |  |  |  |  | 12.9314
20 | TOO / CE/Trans/ MS No. 158 Dated 22.08.2015 | S-15-38 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132 kV lines for making LILO of (i) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Jangaon and (ii) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Kolanpak | System Improvement | 10.03.2017 | 31.03.2020 | 8.1522 | 0.0457 | 0.838 | 0.0186 | 0.1635 | 9.218 |  |  | 7.02 |  |  |  | PFC | 0.08 | 4.6186 | 4.6986 |  |  |  |  | 2.54 |  |  |  | 7.2386 |  |  |  |  | 4.3482
21 | TOO / CE/Trans/ MS No.62 Dated 25.04.2016 | S-16-08 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at existing 220/11 kV LI Sub-Station, Bheemghanpur Warangal District. | System Improvement | 05.05.2017 | 31.03.2020 | 4.775 | 0.14325 | 0.573 | 0.29844 | 0.51331 | 6.303 |  |  | 16.31 |  |  |  | PFC | 0 | 0.2891 | 0.2891 |  |  |  |  | 5.82 |  |  |  | 6.1091 |  |  |  |  | 5.9978
22 | TOO / CE/Trans/ MS No.76 Dated 25.05.2016 | S-16-11 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Bachannapet in Warangal District | System Improvement | 20.04.2017 | 31.03.2020 | 18.1064 | 0.2639 | 1.938 | 0.0642 | 0.9455 | 21.318 |  |  | 16.71 |  |  |  | PFC | 2.06 | 3.03 | 5.09 |  |  |  | 5.82 | 6.36 |  |  |  | 11.45
23 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | S-16-12 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Kotagiri with connected line & Bay in Nizamabad District | System Improvement | 06.06.2018 | 31.03.2020 | 13.8496 | 0.2419 | 1.505 | 0.0842 | 0.8743 | 16.555 |  |  | 12.98 |  |  |  | PFC | 1.34 | 10 | 11.34 |  |  |  |  | 0.68 |  |  |  | 12.02 |  |  |  |  | 6
24 | TOO No.72 Dt:13.05.2016 | S-16-14 | TST/TS/ 220132/33 kV / Substation, Borampet RR District/ INVST- No. 07/16 - 2016-17 | 220/132/33 kV Substation at Borampet in Ranga Reddy district | System Improvement | 28.11.2016 | 31.03.2021 | 196.487 | 3.3449 | 20.3712 | 0.3778 | 11.9859 | 232.5668 |  |  | 182.98 |  |  |  | PFC | 7.83 | 30 | 37.83 |  |  |  |  | 48.9 |  |  |  | 86.73
25 | TOO (CE-Transmission) MS NO.173, Dt:15.12.2016 | S-16-16 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 220/33 kV Sub-Station, at Domalapenta Village of Nagarkurnool District (erstwhile Mahaboobnagar District) | System Improvement | 05.03.2018 | 30.11.2019 | 12.5539 | 0.318 | 1.42 | 0.1885 | 1.1396 | 15.62 |  |  | 12.4108 |  |  |  | PFC | 2.39 | 4.13 | 6.52 |  |  |  |  | 7.33 |  |  |  | 13.85
26 | T.O.O (CE-Transmission) Ms. No. 26, Dated: 27.02.2017. | S-17-01 | CRN TS/TST/220/33 KV, GIS, Chanchaguda/Invest.Approval No.7/17-2017-18 | Erection of 220/33 kV Sub-Station at Chanchalguda | System Improvement | 28.02.2018 | 31.03.2020 | 78.651 | 2.2842 | 8.192 | - | 8.1849 | 97.3121 |  |  | 80.208 |  |  |  | REC | 7.76 | 35.1765 | 42.9365 |  |  |  |  | 37.3 |  |  |  | 80.2365
27 | T.O.O (CE-Transmission) Ms. No. 29, Dated: 27.02.2017. | S-17-06 | CRN TS/TST/132/33 KV, GIS, Petlaburz invest.Approval No.5/17-2017-18 | 132/33 kV Substation at PTO, Petlaburz, Hyderabad District | System Improvement | 02.03.2018 | 31.03.2021 | 35.4257 | 0.9818 | 3.993 | 0.0045 | 3.5183 | 43.9233 |  |  | 35.93 |  |  |  | REC | 0 | 7 | 7 |  |  |  |  | 20.09 |  |  |  | 27.09
28 | T.O.O (CE-Transmission) Ms. No.84, Dated: 27.05.2017 | S-17-09 | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | 220/132/33 kV Substation at Toopran(meenaji pet) in Medak District along with connected lines | System Improvement | 27.01.2016 | 31.03.2021 | 60.8 | 1.824 | 6.08 | 3.8 | 6.536 | 79.04 |  |  | 68.43 |  |  |  | REC | 4.92 | 10 | 14.92 |  |  |  |  | 39.87 |  |  |  | 54.79
29 | T.O.O (CE-Transmission) Ms. No. 88, Dated: 02.06.2017. | s-17-10 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132kV DC line from proposed 220/132kV SS Madugula to existing 132/33 kV Takkalapally (Yacharam) SS | System Improvement | 01.04.2019 | 31.03.2021 | 9.81 | 0.2943 | 0.981 | 0.5886 | 1.0546 | 12.7285 |  |  | 10.6 |  |  |  | REC | 0.03 | 2 | 2.03 |  |  |  |  | 0 |  |  |  | 2.03
30 | TOO (CE-construction) MS.NO.86 dt:29-05-2017 | S-17-12 | CRN TST/TS/132/33KV, Choppadandi, SS /Invest,Approval No.20/18-2017-18 | 132/33 kV SS with connected line at Choppadandi in Karimnagar Dist. | System Improvement | 06.06.2018 | 31.03.2020 | 21.1755 | 0.3375 | 2.5135 | 0.1282 | 1.2093 | 25.364 |  |  | 19.97 |  |  |  | PFC | 0 | 17.7408 | 17.7408 |  |  |  |  | 0.02 |  |  |  | 17.7608
31 | TOO (CE_Transmission)Ms.No.69 Dt:09.05.2017 | S-17-13 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Yadagirigutta Temple with connected line Town of Yadadri (erstwhile Nalgonda) .District | System Improvement | 01.10.2018 | 31.03.2020 | 13.9285 | 0.2154 | 1.6566 | 0.1312 | 0.7851 | 16.7168 |  |  | 13.16 |  |  |  | PFC | 2.47 | 6.4168 | 8.8868 |  |  |  |  | 5.08 |  |  |  | 13.9668
32 | T.O.O (CE-Construction) Ms. No.170 Dt;16.11.2017 | S-17-14 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing of 33 kV Features at upcoming 220/132 KV Sub-Station, Mahabubabad in Mahabubabad District | System Improvement | 31.10.2018 | 31.08.2020 | 6.6281 | 0.1807 | 0.854 | 1.0839 | 0.6473 | 9.394 |  |  | 7.44 |  |  |  | REC | 0 | 2.8 | 2.8 |  |  |  |  | 0.35 |  |  |  | 3.15
33 | T.O.O (CE-Construction) Ms. No. 124, Dated: 19.08.2017 | S-17-15 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Chinna Shankarampet in Medak District | System Improvement | 01.04.2018 | 31.03.2020 | 13.3134 | 0.2482 | 1.76 | 1.4891 | 0.8893 | 17.7 |  |  | 13.96 |  |  |  | REC | 0.18 | 11.83 | 12.01 |  |  |  |  | 0.62 |  |  |  | 12.63
34 | T.O.O (CE-Transmission) Ms. No. 70, Dated 09.05.2017 | S-17-18 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | feeding 132/33 kV SS Ghanpur through Ring Mains | System Improvement | 23.10.2018 | 31.03.2020 | 4.83 | 0.1449 | 0.483 | 0.2898 | 0.51923 | 6.2669 |  |  | 5.07 |  |  |  | PFC | 1.12 | 1.7688 | 2.8888 |  |  |  |  | 2.62 |  |  |  | 5.5088
35 | TOO (CE-construction) MS.NO.13 dt:20-01-2018 | S-17-19 | CRN No. TST/TS/Erection of 132/33 KV SS at Pitlam in Khammam Dist. Approval/No.04/2018-19 | 132/33 kV SS at Pitlam in Nizamabad District (13, dt.20.1.18 | System Improvement | 31.10.2018 | 31.03.2022 | 29.5454 | 0.2846 | 3.24 | 1.7077 | 1.0198 | 35.7975 |  |  | 31.8 |  |  |  | REC | 0 | 0.1 | 0.1 |  |  |  |  | 0.05 |  |  |  | 0.15
36 | T.O.O (CE-Construction) MS.No .294 Dated:29.01.2019 | S-18-02 | CRN No: TST/TS/Erecion of 220/132 kV Substation at Ammavaripet, Kazipet(M) in Warangal Urban District.F. Approval/ No.13/18/2018-19 | erection of 220/132 kV Sub-Station at Ammavaripetin Warangal-Urban District | System Improvement | 31.10.2018 | 30.06.2021 | 84.9 | 2.547 | 15.02 | 15.282 | 9.1267 | 126.8757 |  |  | 87.24 |  |  |  | PFC | 0.26 | 20 | 20.26 |  |  |  |  | 0.24 |  |  |  | 20.5
37 | TOO (CE Construction) MS NO.193, Dt:30.08.2018 | S-18-04 | CRN No. TST/TS/Erection of 132/33 KV Sub station at Nagaram in suryapet District. Approval/No.14/18/2018-19, Dt:12.12.2018 | 132/33 KV SS Nagaram,Nalgonda District | System Improvement | 01.04.2019 | 31.03.2022 | 26.2586 | 0.2904 | 4.64 | 1.7427 | 1.0407 | 33.9724 | [6 empty] | PFC | 0.48 | 0.5 | 0.98 |  |  |  |  | 0 |  |  |  | 0.98
38 | TOO (CE_Construction-1)Ms.No.217 Dt:25.09.2018 |  | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 KV features at 132 KV Railway Traction Switching Station, Kothagudem, Kothagudem Bhadradri District | System Improvement | 01.04.2019 | 31.03.2021 | 6.9998 | 0.1909 | 0.9 | 1.1453 | 0.684 | 9.92 | [6 empty] | To be tied up | 0 | 1 | 1 |  |  |  |  | 0 |  |  |  | 1
39 | T.O.O (CE-Construction) Ms. No.254, Dt:26.11.18 | -- | Proceedings No: 28/APERC/Secy/Dir(Engg)/E-725/2013, dated.06.05.2013 | 132/33kV SS at Padmanagar in Karimnagar District | System Improvement | 01.04.2019 | 31.03.2021 | 16.075 | 0.48225 | 1.929 | 1.0047 | 1.7281 | 21.219 | [7 empty] | 0 | 7 | 7 |  |  |  | 0 | 0 |  |  |  | 7
40 | T.O.O (CE-Construction) MS. No. 402 Dated: 08.07.2019 |  |  | 132/33 kV Gas Insulated Sub-Station (GIS) at Manikonda in Ranga Reddy District along with connected line with 132 KV XLPE UG cable | System Improvement | 31.09.2019 | 30.03.2021 | 83.0853 | 2.4926 | 7.4777 | 5.1928 | 8.9317 | 107.18 | [7 empty] | 0 | 10 | 10 |  |  |  |  | 0 |  |  |  | 10
41 | T.O.O (CE-Construction) MS. No. 401 Dated: 08.07.2019 | P-19-01 |  | 400/220 kV, 1X315 MVA ICT at Bhadradri Thermal Power Station (BTPS) switch yard, Manuguru, TSGENCO and erection of 220 KV DC line from 220/132/33 KV Manuguru SS to 400 KV BTPS switch yard | System Improvement | 31.09.2019 | 30.03.2021 | 51.5969 | 1.5479 | 4.6437 | 3.2248 | 5.5467 | 66.56 | [7 empty] | 0.58 | 27.958 | 28.538 |  |  |  |  | 0 |  |  |  | 28.538
42 | TOO (CE-Transmission) MS.NO.27 dt:27-02-2017 | S-17-04 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Administrative approval for erection of 132/33 KVSS Gachibowli in Ranga Reddy District. | System Improvement | 01.04.2019 | 31.03.2021 | 16.7357 | 0.3993 | 1.872 | 0.1636 | 1.4307 | 20.6013 |  |  | 16.52 |  |  |  | REC | 0 | 10 | 10 |  |  |  |  | 0 |  |  |  | 10
43 | TOO (CE-Transmission) MS.NO.28 dt:27-02-2017 | S-17-05 | CRN TS/TST/132/33 KV, GIS, Seetharambagh/Invest.Approval No.6/17-2017-18 | 132/33 KV Gas Insulated Sub-station (GIS) at Seetharambagh with connected UG cable & bay in Hyderabad District and connectivity from Asifnagar SS. | System Improvement | 01.04.2019 | 31.03.2022 | 56.3096 | 1.5947 | 6.362 | 0.0104 | 5.7146 | 69.9913 |  |  | 57.27 |  |  |  | REC | 0 | 2 | 2 |  |  |  |  | 0 |  |  |  | 2
44 | TOO (CE-Transmission) MS.NO.30 dt:27-02-2017 | S-17-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 KV IDA Mallapur Sub-station with connected line in Medchal-Malkajgiri District. | System Improvement | 01.04.2019 | 31.03.2022 | 17.2144 | 0.4116 | 1.905 | 0.1724 | 1.2523 | 20.9557 |  |  | 16.81 |  |  |  | REC | 0 | 1 | 1 |  |  |  |  | 0 |  |  |  | 1
45 | TOO (CE-Transmission) MS.NO.31 dt:27-02-2017 | S-17-03 | CRN TS/TST/132/33 KV, Moulali-ZTS SS, Investment Approval No.17/17, 2017-18 | 132/33 KV Sub-station at Moulali ZTS with connected UG cable & bay in Medchal-Malkajgiri District | System Improvement | 01.04.2019 | 31.03.2021 | 44.124 | 1.2338 | 4.9779 | 0.1599 | 4.2615 | 54.7571 |  |  | 44.47 |  |  |  | REC | 0.01 | 27 | 27.01 |  |  |  |  | 0 |  |  |  | 27.01
46 | TOO (CE-construction) MS.NO.177 dt:30-11-2017 | S-17-20 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132 KV DC/SC line from 220KVSS Chegur (Kothur) to existing 132KVSS Kothur | System Improvement | 01.04.2019 | 31.03.2020 | 5.2691 | 0.0423 | 0.5678 | 0.2169 | 0.1516 | 6.2477 |  |  | 5.11 |  |  |  | REC | 3.44 | 2.8 | 6.24 |  |  |  |  | 0 |  |  |  | 6.24
47 | TOO (CE-construction) MS.NO.149 dt:09-10-2017 | S-17-16 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd CKT (30KM) on 132KV DC/SC line from existing 220/132KV SS Waddekothapally to existing 132/33KV SS Peddanagaram with Panther ACSR Conductor with connected bays | System Improvement | 01.04.2019 | 31.03.2021 | 6.7387 | 0.0316 | 0.7019 | 0.1328 | 0.1167 | 7.7217 |  |  | 6.32 |  |  |  | REC | 0 | 5 | 5 |  |  |  |  | 0 |  |  |  | 5
48 | TOO / CE/Trans/ MS No. 31 Dated 18.02.2016 | S-16-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 33 kV Features at existing 132 kV Switching Station, Kodandapur in Nalgonda District. | System Improvement | 01.04.2019 | 31.03.2020 | 7.371 | 0.313 | 0.89 | 0.0945 | 1.1215 | 9.79 |  |  | 8.01 |  |  |  | REC | 0.03 | 1 | 1.03 |  |  |  |  | 0 |  |  |  | 1.03
49 | T.O.O (CE-Construction-I)MS.No. 186 Dated: 11.09.2013 2) T.O.O (CE-Construction) Ms. No. 103 Dated:11.07.2017 | S-13-15 S-17-23 | CRN TST/TS/220/ Switching Station/Mahaboobnagar/132 KV Features /Invest,Approval No.14/17-2017-18 | erection of 132 kV features at 220 kV Thimmajipet Switching Station in Mahaboobnagar District and extending connectivity to 132 kV Jadcherla Sub-Station from Thimmajipet | System Improvement | 01.04.2019 | 31.03.2021 | 24.43 | 0.733 | 2.443 | 1.4858 | 2.6262 | 31.718 |  |  | 26.39 |  |  |  | REC | 0 | 3.5 | 3.5 |  |  |  |  | 0 |  |  |  | 3.5
50 | T.O.O (CE-Construction) MS.No .341 Dated:02.04.2019 |  | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at upcoming 220/132 KV Sub-Station, Ammavaripet in Kazipet (M), Warangal Urban (District)- | System Improvement | 01.04.2019 | 31.03.2021 | 6.2791 | 0.18837 | 0.56512 | 0.39244 | 0.675 | 8.1 | [6 empty] | To be tied up | 0 | 1.4 | 1.4 |  |  |  |  | 0 |  |  |  | 1.4
51 | TOO (CE-construction) MS.NO.245 dt:29-09-2011 | S-07-03 |  | Erragadda and O.U GIS &Cables scheme | System Improvement | 27.12.2011 | 31.03.2020 | 437.7 | 13.131 | 43.77 | 26.262 | 47.0527 | 567.9157 |  |  | 415 |  |  |  | PFC | 0.32 | 8.5 | 8.82 |  |  |  |  | 0 |  |  |  | 8.82
52 | T.O.O (CE-Construction-1) Ms. No. 07 Dated: 18.12.2013 SI10NIM132 | S-07-04 |  | TWIN CITIES TRANSMISSION SYSTEM & 132 kV SS NIMS & connected lines & erection of 220/132 kV substations at Gunrock, Imlibun (GIS) & Hayatnagar and 132 kV GIS Substations at Moosarambagh, Miralam Filter bed, Patigadda, Balkampet and with connected Under Ground XLPE Cables – Under Modernization and Strengthening of Hyderabad Metropolitan area | System Improvement | 01.08.2014 | 31.03.2020 | 76.8437 | 2.3009 | 8.825 | 0.6132 | 8.4922 | 97.075 |  |  | 85.36 |  |  |  | JICA | 1.16 | 15.5 | 16.66 |  |  |  |  | 0 |  |  |  | 16.66
| TOO (CE-Construction) MS NO.379, Dt:17.01.2012 |  |  |  |  | 01.08.2014 | 31.03.2020 | 11.75 | 0.3525 | 1.175 | 0.705 | 1.2631 | 15.2456 |  |  | 11.4 | [15 empty] | 0
53 | T.O.O (CE-Construction) Ms. No.261 Dated: 09 .02.2009 | S-08-02 | CRN.No./TST/TS/132 KV Amarachinta//F.Invst./ App./08/2011 | 132/33 kV substation at Amarchinta in Mahaboobnagar district | System Improvement | 13.12.2010 | 31.03.2020 | 12.9583 | 0.38875 | 1.2958 | 0.7775 | 1.393 | 16.8134 |  |  | 15.55 |  |  |  | Uco Bank | 0.41 | 1 | 1.41 |  |  |  |  | 0 |  |  |  | 1.41
54 | T.O.O. (CE-Transmission) Ms. No. 140 Dated. 13.10.2016 (Revised) | S-08-08 | CRN.No./TST/TS/220-132 KV GIS-Hyd/F.Invst./99/2019, Dt:20.02.2009 | 132/33 KV Narayanaguda GIS Sub-station | System Improvement | 31.05.2013 | 31.03.2020 | 130.1917 | 3.9057 | 13.0192 | 7.8115 | 13.9956 | 168.9237 |  |  | 31.19 |  |  |  | PFC | 6.47 | 1.5 | 7.97 |  |  |  |  | 0 |  |  |  | 7.97
55 | T.O.O (CE-Construction) Ms. No. 290 Dt: 16.10.2010 | S-08-14 | APT/TS/220/33 KV-Singotam x Roads//F-INVST-20/2011 | Erection of 220/33 kV SS at Singotam ‘X’ Roads, instead of erection of 132/33 kV substation at Singotam ‘X’ Roads, Kollapur Mandal in Mahabubnagar district along with connected lines | System Improvement | 12.02.2011 | 31.03.2020 | 17.64 | 0.5292 | 2.12 | 1.1025 | 1.8963 | 23.288 | [6 empty] | Syndicate Bank | 0.22 | 0.5 | 0.72 |  |  |  |  | 0 |  |  |  | 0.72
56 | T.O.O (CE-Construction) Ms. No. 267 Dated: 6.10.2010 | S-10-02 | CRN.No.APT/TS/132 KVSS/ Asifabad/Invest.24/12 | 132/33 kV Substation at Asifabad in Adilabad district along with connected 132 kV & 33 kV lines | System Improvement | 29.11.2012 | 31.03.2020 | 16.7833 | 0.5035 | 1.6783 | 1.007 | 1.8042 | 21.7763 |  |  | 18.0042 |  |  |  | REC | 0.6 | 9 | 9.6 |  |  |  |  | 0 |  |  |  | 9.6
57 | T.O.O (CE-Construction) Ms. No. 99 Dated: 18.06.2010 | S-10-06 | CRN.No.TST/TS/132 KV SS Borabatla/F.INVT-24/2011, dt:21.03.2011 | 132/33 kV Substation at Borapatla in Medak district along with connecting 132 kV and 33 kV lines | System Improvement | 20.08.2011 | 31.03.2020 | 12.8306 | 0.38492 | 1.2831 | 0.76984 | 1.3793 | 16.6477 |  |  | 36.75 |  |  |  | NABARD | 0.25 | 1 | 1.25 |  |  |  |  | 0 |  |  |  | 1.25
58 | T.O.O (CE-Construction) MS. No. 247 Dated: 25.09.2010 | S-10-09 | APT/TS/132 kV SS -Geesukonda/ F-INVST -20/2012 | Erection of 132/33 kV Substation at Geesukonda in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 30.10.2010 | 31.03.2020 | 10.24 | 0.3072 | 1.22 | 0.64 | 1.1008 | 13.508 |  |  | 10.44 |  |  |  | REC | 0.02 | 0.5 | 0.52 |  |  |  |  | 0 |  |  |  | 0.52
59 | T.O.O (CE-Construction) Ms. No. 262 Dated: 04.10.2010 | S-10-16 | CRN.No.TST/TS/132 KV SS Narmetta/F.INVT-36/2013, dt:07.11.2012 | 132/33 kV Substation at Narmetta in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 07.08.2014 | 31.03.2020 | 15.5667 | 0.467 | 1.5567 | 0.934 | 1.6734 | 20.1977 |  |  | 15.9792 |  |  |  | REC | 0.11 | 0.5 | 0.61 |  |  |  |  | 0 |  |  |  | 0.61
60 | T.O.O (CE-Construction) Ms. No.3 Dated: 27.06.2014 SI11KAMANP | S-11-18 | APT/TS/132 kV SS -Kamanpur/ F-INVST -19/2013 | 132kv SS Kamanpur & connected lines | System Improvement | 16.07.2014 | 31.03.2020 | 20.952 | 0.60551 | 2.232 | - | 0.76253 | 24.552 |  |  | 15.5276 |  |  |  | PFC | 0.18 | 3 | 3.18 |  |  |  |  | 0 |  |  |  | 3.18
61 | T.O.O (CE-Construction-I) Ms. No. 297 Dated: 21.11.2011 SI11KATHLA | S-11-19 | APT/TS/132kV SS- Kathlapur/ F-INVST-09/2014 | 132kV SS Kathlapur & connected lines | System Improvement | 10.12.2015 | 31.03.2020 | 13.1651 | 0.2088 | 1.415 | 0.0012 | 0.77489 | 15.565 |  |  | 14.15 |  |  |  | TMB | 0.03 | 4.5 | 4.53 |  |  |  |  | 0 |  |  |  | 4.53
62 | T.O.O (CE-Construction-I) Ms. No. 184 Dated: 11.08.2011 SI11MUNUGO | S-11-25 S-11-26 | APT/TS/132kV SS-Munugodu/F-INVST-08/2014 | 132kV SS Munugodu & connected lines | System Improvement | 13.06.2016 | 31.03.2020 | 17.3109 | 0.2455 | 1.847 | 0.0016 | 0.912 | 20.317 |  |  | 16.137 |  |  |  | REC | 0.06 | 1.67 | 1.73 |  |  |  |  | 0 |  |  |  | 1.73
63 | T.O.O (CE-Construction-I) Ms. No.8 Dated: 6.04.2011 | S-11-27 | CRN.No.TST/TS/132 KVSS/Nellikoduru/F.Invest. 07/2014 | 132/33 kV Substation at Nellikuduru in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 21.07.2016 | 31.03.2020 | 17.675 | 0.53025 | 1.7675 | 1.0605 | 1.9001 | 22.9333 |  |  | 17.847 |  |  |  | REC | 0.16 | 2 | 2.16 |  |  |  |  | 0 |  |  |  | 2.16
64 | TOO (CE-Construction-I) MS NO.180, Dt:09.08.2011 | S-11-30 | APT/TS/220/132 kV SS -Parigi/F-INVST - 1/2013 | erection of 220/132 kV substation at Parigi in Ranga Reddy district | System Improvement | 19.10.2013 | 31.03.2020 | 57.5115 | 0.6051 | 6.035 | - | 2.2334 | 66.385 |  |  | 54.3164 |  |  |  | REC | 0.12 | 2 | 2.12 |  |  |  |  | 0 |  |  |  | 2.12
65 | T.O.O (CE-Transmission) Ms. No. 78 Dated: 14.06.2016. (Revised) | S-11-37 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Shad Nagar (V) Hamlet of Wattipally in Medak District | System Improvement | 09.09.2015 | 31.03.2020 | 15.8917 | 0.47675 | 1.5892 | 0.9535 | 1.7084 | 20.6194 |  |  | 57.195 |  |  |  | REC | 0.11 | 2 | 2.11 |  |  |  |  | 0 |  |  |  | 2.11
66 | T.O.O (CE-Construction-I) Ms. No. 173 Dated: 03.09.2012 SI11YELDUR | S-11-38 | APT/TS/132 kV SS -Yeldurthy/F-INVST - 7/2013 | 132 kV SS Yeldurthy & connected lines | System Improvement | 12.08.2016 | 31.03.2020 | 19.225 | 0.5767 | 0.1922 | 1.1535 | 2.0667 | 23.2141 |  |  | 17.27 |  |  |  | NABARD | 0.1 | 1 | 1.1 |  |  |  |  | 0 |  |  |  | 1.1
67 | T.O.O (CE-Construction-I) MS. No.376 Dated: 13.01.2012 | S-12-01 | APT/TS/220KV-SS-Kosgi/F-INVST-50/2013 | 220 kV features at proposed 132/33 kV Kosigi SS in Mahaboobnagar district | System Improvement | 07.08.2014 | 31.03.2020 | 43.5417 | 1.3062 | 4.3542 | 2.6125 | 4.6807 | 56.4953 |  |  | 46.5728 |  |  |  | REC | 0.07 | 0.3 | 0.37 |  |  |  |  | 0 |  |  |  | 0.37
68 | T.O.O (CE-Construction-I) Ms. No. 460 Dated: 24.02.2012 | S-12-04 | CRN.No.TST/TS/132 KV SS-Inavolu/F-INVST-15/2014/Dt:24.05.2013 | 132/33 kV Substation at Inavole in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 10.11.2016 | 31.03.2020 | 20.09 | 0.6027 | 2.009 | 1.2054 | 2.1597 | 26.0668 |  |  | 20.79 |  |  |  | PFC | 0.02 | 1 | 1.02 |  |  |  |  | 0 |  |  |  | 1.02
69 | T.O.O (CE-Construction) Ms.No.27 Dated: 12 .02.2015 SI12MDPALL | S-12-10 | TST/TS/132kV / MD Pally, Kattedan /F-INVST- 03/2016 | 132 kV SS MD Pally (Kattedan) & connected lines | System Improvement | 05.08.2015 | 31.03.2020 | 52.6715 | 0.7587 | 5.79 | 1.7015 | 2.7683 | 63.69 |  |  | 33.864 |  |  |  | PFC | 0.08 | 0.2 | 0.28 |  |  |  |  | 0 |  |  |  | 0.28
70 | T.O.O (CE-Construction) Ms. No.127 Dated: 17.07.2015 SI12MUNAGA | S-12-11 | TST/TS/132/33kV SS Munagala / F-INVST- 13/2015 | 132kV SS Munagala(V&M) & connected lines | System Improvement | 20.06.2016 | 31.03.2020 | 33.8827 | 0.3453 | 3.554 | 0.0749 | 1.2371 | 39.094 |  |  | 30.947 |  |  |  | REC | 0.07 | 0.2 | 0.27 |  |  |  |  | 0 |  |  |  | 0.27
71 | T.O.O (CE-Construction) MS.No .109 Dated:17.05.2018 (Revised) | S-13-06 | TST/TS/132kV SS/ Dommarapochampalli /F-INVST- 04/2015 | 132KV Dommarapochampally & connected lines | System Improvement | 24.12.2016 | 31.03.2020 | 35.9609 | 0.4336 | 4.031 | 2.3413 | 1.5742 | 44.341 |  |  | 32.3488 |  |  |  | REC | 0.4 | 2.96 | 3.36 |  |  |  |  | 0 |  |  |  | 3.36
72 | T.O.O (CE-Transmission) Ms.No.193 Dated:07.10.2015 (Revised) | S-13-10 | TST/TS/132kV / Kachapur SS/F-INVST- 17/2016 | 132/33kV SS Kachapur & connected lines | System Improvement | 22.09.2015 | 31.03.2020 | 19.9182 | 0.3337 | 1.8946 | 0.0827 | 1.1954 | 23.4246 |  |  | 21.53 |  |  |  | REC | 0.51 | 2 | 2.51 |  |  |  |  | 0 |  |  |  | 2.51
73 | T.O.O (CE-Construction) MS.No. 144 Dated:03.08.2015 | S-13-14 | CRN.No./TST/TS/220/132KV Substation /Sircilla /F.Invst./ App./08/2015 | 220/132 kV SS at Sircilla in Karimnagar District | System Improvement | 22.12.2015 | 31.03.2020 | 72.7583 | 2.1827 | 7.2758 | 4.3655 | 7.8215 | 94.4039 |  |  | 59.9992 |  |  |  | REC | 0.18 | 18.8 | 18.98 |  |  |  |  | 0 |  |  |  | 18.98
74 | T.O.O (CE-Construction) Ms. No. 02 `Dated: 04.02.2015. | S-15-03 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Chandulapur Village of Chinnakodur Mandal in Medak District along with connected lines | System Improvement | 27.04.2016 | 31.03.2020 | 15.2083 | 0.45625 | 1.5208 | 0.9125 | 1.6349 | 19.7328 |  |  | 30.5565 |  |  |  | REC | 0.01 | 1 | 1.01 |  |  |  |  | 0 |  |  |  | 1.01
75 | T.O.O (CE-Construction) Ms. No. 128 Dated: 17.07 2015. | S-15-10 | CRN.No.TST/TS/132/33 KVSS/Narayanpet, Mahabubnagar/Invest.Apprl.No.5/16,2016-17 | 132/33 kV Substation at Narayanpet in Mahaboobnagar District along with connected 132 kV & 33 kV lines | System Improvement | 21.09.2016 | 31.03.2020 | 17.6917 | 0.53075 | 1.7692 | 1.0615 | 1.9019 | 22.9549 |  |  | 34.9754 |  |  |  | REC | 0.56 | 0.1 | 0.66 |  |  |  |  | 0 |  |  |  | 0.66
76 | T.O.O (CE-Transmission) MS.No. 164 Dated: 06.11.2017 (Revised) | S-15-11 | TST/TS/ 220 kV 2nd circuit / RSS to Nirmal SS and RSS to Jagityal SS / F-INVST- 15/2015 | 220 kV 2nd circuit stringing on 220 kV RSS - Jagityal and 220 kV RSS - Nirmal | System Improvement | 27.11.2015 | 31.03.2020 | 65.6314 | 0.0511 | 6.614 | 0.2699 | 0.1876 | 72.754 |  |  | 38.06 |  |  |  | PFC | 0.01 | 2 | 2.01 |  |  |  |  | 0 |  |  |  | 2.01
77 | T.O.O (CE-Transmission) MS.No. 167 Dated: 04.09.2015 SI15L2SHAH | S-15-30 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd Circuit stringing on proposed 132 kV DC/SC line from the under construction 400/220/132 kV SS Suryapet to 132/33 kV Shah Ali Gowraram under the program for providing 9.00 Hrs agricultural supply during day time. | System Improvement | 05.04.2016 | 31.03.2020 | 5.9166 | 0.0248 | 0.604 | 0.01 | 0.0886 | 6.644 |  |  | 4.95 |  |  |  | REC | 0.47 | 0.1 | 0.57 |  |  |  |  | 0 |  |  |  | 0.57
78 | T.O.O (CE-Transmisssion) MS.No. 211 Dated: 07.11.2015 | S-15-32 | TST/TS/ 220 kV Pedagopati SS / Investment approval No. 19/16-2016 | Erection of 220/132/33 kV SS at Pedagopati in Khammam district | System Improvement | 27.02.2017 | 31.03.2020 | 120.2411 | 0.8479 | 10.9507 | 0.3131 | 3.0383 | 135.3911 |  |  | 121.2483 |  |  |  | REC | 0.62 | 3 | 3.62 |  |  |  |  | 0 |  |  |  | 3.62
79 | T.O.O (CE-Transmission) Ms. No.49 Dated: 06.04.2016. | S-16-09 | CRN.No.TST/TS/220/132/33 KV SS, Regonda,Warangal,Dist./Invest.Appl.No.8/17,2016-17 | 132/33 kV Sub-Station at Regonda in Warangal District. | System Improvement | 07.02.2018 | 31.03.2020 | 20.5138 | 0.334 | 1.9457 | 0.0652 | 1.1968 | 24.0555 |  |  | 19.07 |  |  |  | PFC | 0.12 | 0.55 | 0.67 |  |  |  |  | 0 |  |  |  | 0.67
80 | T.O.O (CE-Transmission) Ms. No. 82 Dated: 23.05.2017 | S-17-11 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at existing 132/11 kV LI Sub-Station, CH. Kondur in Nizamabad District | System Improvement | 16.04.2018 | 31.03.2020 | 3.5 | 0.105 | 0.35 | 0.21 | 0.37625 | 4.5412 |  |  | 3.6708 |  |  |  | PFC | 0.22 | 0.1 | 0.32 |  |  |  |  | 0 |  |  |  | 0.32
81 | TOO (CE-construction) MS.NO.14 dt:20-01-2018 | S-17-21 | CRN No. TST/TS/Erection of 132/33 KV SS at Pammy in Khammam Dist. Approval/No.03/2018-19 | 132/33kV SS at Pammy in Khammam District (14, dt.20.1.18) | System Improvement | 01.04.2019 | 31.03.2022 | 18.4685 | 0.3015 | 1.73 | 1.8088 | 1.0804 | 23.3892 | [6 empty] | To be tied up | 0.01 | 0.03 | 0.04 |  |  |  |  | 0 |  |  |  | 0.04
82 | TOO (CE-construction) MS.NO.43 dt:06-03-2018 | S-18-01 | CRN No.TST/TS/Erection of 132/33 KV Substation at Peechara in Wranagal District. Approval No. 05/2018-19 | 132/33 kV SS at Peechara in Warangal Dist. | System Improvement | 01.04.2019 | 31.03.2022 | 36.3068 | 0.3432 | 4.42 | 2.0594 | 1.2299 | 44.3593 |  |  | 39.1 |  |  |  | REC | 0.03 | 0.1 | 0.13 |  |  |  |  | 0 |  |  |  | 0.13
83 | T. O. O. (CE/Transmission) MS. No.171 Dated:07.09.2015 | P-15-05 |  | 400/220KV 315MVA PTR in place of failed 400/132KV 200MVA PTR at NTPC Ramagundam and connected 220KV line & Bay Works | System Improvement | 01.04.2016 | 31.03.2020 | 25.6666 | 0.77 | 2.5667 | 1.54 | 2.7592 | 33.3024 |  |  | 25.26 |  |  |  | PFC | 0.13 | 0.5 | 0.63 |  |  |  |  | 0 |  |  |  | 0.63
84 | T.O.O (CE-Construction) MS. No. 350 Dated: 27.11.2010 | P-10-03 |  | 132kV LILO line from 132 KV Makthal – Gadwal 2nd circuit line for the proposed 220 kV Substation Jurala along with bays in Mahabubnagar district | System Improvement | 12.03.2018 | 31.03.2020 | 6.3416 | 0.19025 | 0.63416 | 0.3805 | 0.68172 | 8.2282 |  |  | 3.52 |  |  |  | Bank of Baroda | 0.63 | 0.2 | 0.83 |  |  |  |  | 5.82 |  |  |  | 6.65
[7 empty] | Total | 2999.4335 | 67.2419 | 313.9656 | 111.7636 | 236.5179 | 3728.9225 |  |  | 2674.739 |  |  |  |  | 79.38 | 474.7138 | 554.0938 |  |  |  | 859 | 392.94 |  |  |  | 947.0338 |  |  |  |  | -328.4
Chief Engineer
Construction

## 2020-21
1.1D ABSTRACT OF INVESTMENT PLAN ( FY 2020-21 ) OF CE/CONSTRUCTION
|  |  | Financial Year 2020-21 | [24 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year FY 2020-21 |  |  |  | Investments incurred in the year | Total Investments incurred up to previous year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
Internal Accrual Component of capex in year
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crores) | Proposed IDC | Proposed other expence | % Capatalisation | OPENING BALANCE | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 | TOO 61, Dt:25.05.2012 | S-12-09 | APT/TS/132/Yeddumailram/F-INVST-27/2013 | 132 KV DC/SC inter linking lines between substations 220 KV Yeddumailram-132 KV Pashmailaram | System Improvement | 01.12.2018 | 30.09.2020 | 9.086 | 0.0462 | 0.931 | 0.0012 | 0.1766 | 10.241 | [6 empty] | NABARD | 2.0936 |  |  |  |  | 4.92 |  |  |  | 7.0137
2 | TOO 22 Dt:10.09.2014 | S-14-12 | APT/TS/132 KV SS Kaithlapur/F-INVST-4/2014 | 132 KV substation Khaithalapur aong with connected lines | System Improvement | 05.07.2016 | 31.08.2020 | 63.5174 | 0.50461 | 5.0851 | 0.1489 | 1.8691 | 71.1251 |  |  | 59.09 |  |  |  | REC | 2.6553 |  |  |  |  | 65.65 |  |  |  | 68.3053
3 | TOO (CE-Tr) MS NO.225, Dt:10.12.2015 | S-15-34 | CRN.No.TST/TS/Erection of 220 KV DC line Gajwel/Siddipet/Invest.App.04/17-2017-18 | 220 KV D/C Line from 400KV GAJWEL-SIDDIPET | System Improvement | 05.12.2017 | 31.12.2020 | 37.8541 | 0.0515 | 3.8117 | 0.0198 | 0.1846 | 41.9217 |  |  | 74.97 |  |  |  | REC | 2.3476 |  |  |  |  | 40.51 |  |  |  | 42.8576
4 | T.O.O (CE-Transmission) Ms.No.195 Dated:14.10.2015 | S-15-36 | TST/TS /132/33 kV SS Aipoor , Nalgonda /F-INVST- 01/2016-17 | 132/33 kV SS at Aipoor in Nalgonda district | System Improvement | 05.01.2017 | 31.03.2022 | 19.6933 | 0.3366 | 2.13 | 0.0841 | 1.2057 | 23.4497 |  |  | 18.9106 |  |  |  | REC | 5 |  |  |  |  | 0.25 |  |  |  | 5.25
5 | TOO (CE-Transmission) MS.NO.176 dt:22-12-2016 | S-16-13 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS with connected line at Tallapet in Adilabad District. | System Improvement | 01.04.2020 | 31.03.2022 | 15.585 | 0.3984 | 1.46 | 0.1786 | 0.4276 | 18.0496 |  |  | 0.1463 |  |  |  | REC | 6.7 |  |  |  |  | 0 |  |  |  | 6.7
6 | T.O.O (CE-Transmission) Ms. No. 29, Dated: 27.02.2017. | S-17-06 | CRN TS/TST/132/33 KV, GIS, Petlaburz invest.Approval No.5/17-2017-18 | 132/33 kV Substation at PTO, Petlaburz, Hyderabad District | System Improvement | 02.03.2018 | 31.03.2021 | 35.4257 | 0.9818 | 3.993 | 0.0045 | 3.5183 | 43.9233 |  |  | 35.93 |  |  |  | REC | 31.2 |  |  |  |  | 27.09 |  |  |  | 58.29
7 | T.O.O (CE-Transmission) Ms. No. 88, Dated: 02.06.2017. | S-17-10 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132kV DC line from proposed 220/132kV SS Madugula to existing 132/33 kV Takkalapally (Yacharam) SS | System Improvement | 01.04.2019 | 31.03.2021 | 9.81 | 0.2943 | 0.981 | 0.5886 | 1.0546 | 12.7285 |  |  | 10.6 |  |  |  | REC | 3.0745 |  |  |  |  | 2.03 |  |  |  | 5.1045
8 | T.O.O (CE-Construction) Ms. No.170 Dt;16.11.2017 | S-17-14 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing of 33 kV Features at upcoming 220/132 KV Sub-Station, Mahabubabad in Mahabubabad District | System Improvement | 31.10.2018 | 31.08.2020 | 6.6281 | 0.1807 | 0.854 | 1.0839 | 0.6473 | 9.394 |  |  | 7.44 |  |  |  | REC | 1.95 |  |  |  |  | 3.15 |  |  |  | 5.1
9 | TOO (CE-construction) MS.NO.13 dt:20-01-2018 | S-17-19 | CRN No. TST/TS/Erection of 132/33 KV SS at Pitlam in Khammam Dist. Approval/No.04/2018-19 | 132/33 kV SS at Pitlam in Nizamabad District (13, dt.20.1.18 | System Improvement | 31.10.2018 | 31.03.2022 | 29.5454 | 0.2846 | 3.24 | 1.7077 | 1.0198 | 35.7975 |  |  | 31.8 |  |  |  | REC | 5 |  |  |  |  | 0.15 |  |  |  | 5.15
10 | T.O.O (CE-Transmission) Ms. No. 75, Dated: 19.05.2017 | S-17-22 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Puttandoddi (V), Itikyal (M), Mahaboobnagar District | System Improvement | 01.04.2020 | 31.03.2022 | 11.46 | 0.3438 | 1.146 | 0.6876 | 1.232 | 14.8694 |  |  | 12.03 |  |  |  | PFC | 5 |  |  |  |  | 0 |  |  |  | 5
11 | TOO (CE-construction) MS.NO.43 dt:06-03-2018 | S-18-01 | CRN No.TST/TS/Erection of 132/33 KV Substation at Peechara in Wranagal District. Approval No. 05/2018-19 | 132/33 kV SS at Peechara in Warangal Dist. | System Improvement | 01.04.2020 | 31.03.2022 | 36.3068 | 0.3432 | 4.42 | 2.0594 | 1.2299 | 44.3593 |  |  | 39.1 |  |  |  | REC | 10 |  |  |  |  | 0.13 |  |  |  | 10.13
12 | T.O.O (CE-Construction) MS.No .294 Dated:29.01.2019 | S-18-02 | CRN No: TST/TS/Erecion of 220/132 kV Substation at Ammavaripet, Kazipet(M) in Warangal Urban District.F. Approval/ No.13/18/2018-19 | erection of 220/132 kV Sub-Station at Ammavaripet in Warangal-Urban District | System Improvement | 31.10.2018 | 30.06.2021 | 84.9 | 2.547 | 15.02 | 15.282 | 9.1267 | 126.8757 |  |  | 87.24 |  |  |  | PFC | 39 |  |  |  |  | 20.5 |  |  |  | 59.5
13 | TOO (CE Construction) MS NO.193, Dt:30.08.2018 | S-18-04 | CRN No. TST/TS/Erection of 132/33 KV Sub station at Nagaram in suryapet District. Approval/No.14/18/2018-19, Dt:12.12.2018 | 132/33 KV SS Nagaram,Nalgonda District | System Improvement | 01.04.2019 | 31.03.2022 | 26.2586 | 0.2904 | 4.64 | 1.7427 | 1.0407 | 33.9724 |  |  | 25.17 |  |  |  | PFC | 5 |  |  |  |  | 0.98 |  |  |  | 5.98
14 | - | - | New scheme | 220kV Substation Mucherla with connected line and bay at Pharma City-I, | System Improvement | 01.04.2020 | 31.03.2022 | 90.1 | 2.703 | 9.01 | 5.406 | 9.6857 | 116.9047 |  | - |  | - | - | - | - | 29.25 |  |  |  |  | 0 |  |  |  | 29.25
15 | - | - | New scheme | 220kV Substation Mucherla with connected line and bay at Pharma City-II, | System Improvement | 01.04.2020 | 31.03.2022 | 90.1 | 2.703 | 9.01 | 5.406 | 9.6857 | 116.9047 | [6 empty] | - | 32.5 |  |  |  |  | 0 |  |  |  | 32.5
16 | - | - | New scheme | 132kV Substation with connectd line at Pharma City-I | System Improvement | 01.04.2020 | 31.03.2022 | 49 | 1.47 | 4.9 | 2.94 | 5.2975 | 63.6075 | [6 empty] | - | 16.25 |  |  |  |  | 0 |  |  |  | 16.25
17 | - | - | New scheme | 132kV Substation with connectd line at Pharma City-II | System Improvement | 01.04.2020 | 31.03.2022 | 49 | 1.47 | 4.9 | 2.94 | 5.2975 | 63.6075 | [6 empty] | - | 13 |  |  |  |  | 0 |  |  |  | 13
18 | - | - | New scheme | 220/132/33 kV SS at Gopanpalli | System Improvement | 01.04.2020 | 31.03.2022 | 75 | 2.25 | 7.5 | 4.5 | 8.0625 | 97.3125 | [6 empty] | - | 26 |  |  |  |  | 0 |  |  |  | 26
19 | TOO (CE-construction) MS.NO.44 dt:06-03-2018 |  | CRN No.TST/TS/Erection of 132 KV DC/SC line from existing 132/33 KV Zaheerabad Substation to the existing 132/33 KV Narayankhed substation in Medak District. Approval No. 06/2018-19 | 132 KV DC/SC line (60 km) from existing 132/33 KV Zaheerabad SS to existing 132/33 kV SS Narayankhed including bay. | System Improvement | 01.04.2020 | 31.03.2021 | 54.4039 | 0.0478 | 5.48 | 0.2474 | 0.1713 | 60.3504 | [6 empty] | TO be Tied UP | 32.5 |  |  |  |  | 0 |  |  |  | 32.5
20 | TOO (CE-construction) MS.NO.12 dt:20-04-2018 |  | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132 kV LILO of existing 132 kV Maddur – Makthal DC/SC line to existing newly charged 132/33 kV Narayanpet Sub-Station including bay in Mahaboobnagar District – to meet N -1 Contingency (TOO No.12 20.04.2018) | System Improvement | 01.04.2020 | 31.03.2021 | 4.8449 | 0.0451 | 0.5142 | 0.1168 | 0.1532 | 5.6742 | [6 empty] | TO be Tied UP | 3.6855 |  |  |  |  | 0 |  |  |  | 3.6855
21 | TOO (CE-construction) MS.NO.27 dt:12-02-2018 | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Stringing of 2nd Ckt on existing 132KV DC/SC line from 220/132/33KV Boothpur to 132/33KV SS marikal including bay in Mahaboobnagar District (TOO No.27 12.02.2018) | System Improvement | 01.04.2020 | 31.03.2021 | 11.5907 | 0.0324 | 1.195 | 0.2197 | 0.1069 | 13.1447 |  |  | 0.1052 |  |  |  | REC | 6.5 |  |  |  |  | 0 |  |  |  | 6.5
22 | TOO (CE-construction) MS.NO.375 dt:03-06-2019 | - | - | 132 KV SS Patancheru in Medak District | System Improvement | 01.04.2020 | 31.03.2022 | 18.3178 | 0.54953 | 1.6486 | 1.1449 | 1.9692 | 23.63 | [7 empty] | 15 |  |  |  |  | 0 |  |  |  | 15
23 | TOO (CE-construction) MS.NO.260 dt:30-11-2018 | - | - | Up gradation of existing 132/33 KV RC Puram SS to 220/132/33 KV SS in Ranga Reddy District | System Improvement | 01.04.2020 | 31.03.2022 | 132.2946 | 3.9688 | 11.9065 | 8.2684 | 14.2217 | 170.66 | [7 empty] | 65 |  |  |  |  | 0 |  |  |  | 65
24 | TOO (CE-construction) MS.NO.14 dt:20-01-2018 | S-17-21 | CRN No. TST/TS/Erection of 132/33 KV SS at Pammy in Khammam Dist. Approval/No.03/2018-19 | 132/33kV SS at Pammy in Khammam District (14, dt.20.1.18) | System Improvement | 01.04.2020 | 31.03.2022 | 18.4685 | 0.3015 | 1.73 | 1.8088 | 1.0804 | 23.3892 | [6 empty] | To be tied up | 5 |  |  |  |  | 0.04 |  |  |  | 5.04
25 | - | - | New scheme | Erection of 33 KV feeder bays at 220 KV Medchal SS. | System Improvement | 01.04.2020 | 31.03.2021 | 15 | 0.45 | 1.5 | 0.9 | 1.6125 | 19.4625 | [7 empty] | 6.5 |  |  |  |  | 0 |  |  |  | 6.5
26 | TOO (CE-construction) MS.NO.11 dt:20-04-2018 |  | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | connecting the existing 132 kV Shapurnagar – Bhongir – Aleru line to 400/220/132 kV Malkaram SS and 400/220/132 kV Ghanapur SS (UG cable) | System Improvement | 01.04.2020 | 31.03.2022 | 14.8245 | 0.3325 | 1.56 | 2.0152 | 1.1834 | 19.9156 | [7 empty] | 5 |  |  |  |  | 0 |  |  |  | 5
27 | T.O.O (CE-Construction) Ms. No.254, Dt:26.11.18 | -- | Proceedings No: 28/APERC/Secy/Dir(Engg)/E-725/2013, dated.06.05.2013 | 132/33kV SS at Padmanagar in Karimnagar District | System Improvement | 01.04.2019 | 31.03.2021 | 16.075 | 0.48225 | 1.929 | 1.0047 | 1.7281 | 21.219 | [7 empty] | 11.7 |  |  |  |  | 7 |  |  |  | 18.7
28 | T.O.O (CE-Construction) MS. No. 402 Dated: 08.07.2019 |  |  | 132/33 kV Gas Insulated Sub-Station (GIS) at Manikonda in Ranga Reddy District along with connected line with 132 KV XLPE UG cable | System Improvement | 31.09.2019 | 30.03.2021 | 83.0853 | 2.4926 | 7.4777 | 5.1928 | 8.9317 | 107.18 | [7 empty] | 40 |  |  |  |  | 10 |  |  |  | 50
29 | T.O.O (CE-Construction) MS. No. 401 Dated: 08.07.2019 | P-19-01 |  | 400/220 kV, 1X315 MVA ICT at Bhadradri Thermal Power Station (BTPS) switch yard, Manuguru, TSGENCO and erection of 220 KV DC line from 220/132/33 KV Manuguru SS to 400 KV BTPS switch yard | System Improvement | 31.09.2019 | 30.03.2021 | 51.5969 | 1.5479 | 4.6437 | 3.2248 | 5.5467 | 66.56 | [7 empty] | 19.5 |  |  |  |  | 28.54 |  |  |  | 48.04
30 | TOO (CE-Transmission) MS.NO.45 dt:31-03-2016 | S-16-15 | CRN.No. TST/TS/220/132/33 KVSS,Kachavani Singaram, R.R.Dist.Inves.Appl./No.9/17,2016-17 | Erection of 220/132/33 kV Substation at Kachavani Singaram in Ghatkesar Mandal of Ranga Reddy District along with connected lines | System Improvement | 01.04.2020 | 31.03.2022 | 40.9618 | 1.0324 | 4.9724 | 0.3462 | 3.6996 | 51.0124 |  |  | 40.32 |  |  |  | REC | 10 |  |  |  |  | 0 |  |  |  | 10
31 | TOO (CE-Transmission) MS.NO.27 dt:27-02-2017 | S-17-04 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Administrative approval for erection of 132/33 KVSS Gachibowli in Ranga Reddy District. | System Improvement | 01.04.2019 | 31.03.2021 | 16.7357 | 0.3993 | 1.872 | 0.1636 | 1.4307 | 20.6013 |  |  | 16.52 |  |  |  | REC | 6 |  |  |  |  | 10 |  |  |  | 16
32 | TOO (CE-Transmission) MS.NO.28 dt:27-02-2017 | S-17-05 | CRN TS/TST/132/33 KV, GIS, Seetharambagh/Invest.Approval No.6/17-2017-18 | 132/33 KV Gas Insulated Sub-station (GIS) at Seetharambagh with connected UG cable & bay in Hyderabad District and connectivity from Asifnagar SS. | System Improvement | 01.04.2019 | 31.03.2022 | 56.3096 | 1.5947 | 6.362 | 0.0104 | 5.7146 | 69.9913 |  |  | 57.27 |  |  |  | REC | 30 |  |  |  |  | 2 |  |  |  | 32
33 | TOO (CE-Transmission) MS.NO.30 dt:27-02-2017 | S-17-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 KV IDA Mallapur Sub-station with connected line in Medchal-Malkajgiri District. | System Improvement | 01.04.2019 | 31.03.2022 | 17.2144 | 0.4116 | 1.905 | 0.1724 | 1.2523 | 20.9557 |  |  | 16.81 |  |  |  | REC | 8 |  |  |  |  | 1 |  |  |  | 9
34 | TOO (CE-Transmission) MS.NO.31 dt:27-02-2017 | S-17-03 | CRN TS/TST/132/33 KV, Moulali-ZTS SS, Investment Approval No.17/17, 2017-18 | 132/33 KV Sub-station at Moulali ZTS with connected UG cable & bay in Medchal-Malkajgiri District | System Improvement | 01.04.2019 | 31.03.2021 | 44.124 | 1.2338 | 4.9779 | 0.1599 | 4.2615 | 54.7571 |  |  | 44.47 |  |  |  | REC | 17.1 |  |  |  |  | 27.01 |  |  |  | 44.11
35 | TOO (CE-Transmission) MS.NO.32 dt:27-02-2017 | S-17-02 | CRN TS/TST/132/33 KV, GIS, R.P.Nilayam/Invest.Approval No. 8/17 - 2017-18 | 132/33 KV AIS/GIS at R.P. Nilayam with connected line in Medchal-Malkajgiri District. | System Improvement | 01.04.2020 | 31.03.2022 | 42.59 | 1.1891 | 4.8029 | 0.1529 | 4.0976 | 52.8325 |  |  | 42.89 |  |  |  | REC | 20 |  |  |  |  | 0 |  |  |  | 20
36 | TOO (CE-Transmission) MS.NO.162 dt:26-08-2015 | S-15-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132 kV 2nd Circuit (9 KM) from 132/33 kV SS Domakonda to 132/33 kV SS Biknur | System Improvement | 01.04.2020 | 31.03.2022 | 7.371 | 0.313 | 0.89 | 0.0945 | 1.1215 | 9.79 |  |  | - |  |  |  | PFC | 3 |  |  |  |  | 0 |  |  |  | 3
37 | TOO (CE-construction) MS.NO.149 dt:09-10-2017 | S-17-16 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd CKT (30KM) on 132KV DC/SC line from existing 220/132KV SS Waddekothapally to existing 132/33KV SS Peddanagaram with Panther ACSR Conductor with connected bays | System Improvement | 01.04.2019 | 31.03.2021 | 6.7387 | 0.0316 | 0.7019 | 0.1328 | 0.1167 | 7.7217 |  |  | 6.32 |  |  |  | REC | 2 |  |  |  |  | 5 |  |  |  | 7
38 | T.O.O (CE-Construction-I)MS.No. 186 Dated: 11.09.2013 2) T.O.O (CE-Construction) Ms. No. 103 Dated:11.07.2017 | S-13-15 S-17-23 | CRN TST/TS/220/ Switching Station/Mahaboobnagar/132 KV Features /Invest,Approval No.14/17-2017-18 | erection of 132 kV features at 220 kV Thimmajipet Switching Station in Mahaboobnagar District and extending connectivity to 132 kV Jadcherla Sub-Station from Thimmajipet | System Improvement | 01.04.2019 | 31.03.2021 | 24.43 | 0.733 | 2.443 | 1.4858 | 2.6262 | 31.718 |  |  | 26.39 |  |  |  | REC | 13 |  |  |  |  | 3.5 |  |  |  | 16.5
39 | T.O.O (CE-Construction) MS.No .341 Dated:02.04.2019 |  | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at upcoming 220/132 KV Sub-Station, Ammavaripet in Kazipet (M), Warangal Urban (District)- | System Improvement | 01.04.2019 | 31.03.2021 | 6.2791 | 0.18837 | 0.56512 | 0.39244 | 0.675 | 8.1 | [7 empty] | 3.965 |  |  |  |  | 1.4 |  |  |  | 5.365
40 | T.O.O (CE-Transmission) Ms. No.84, Dated: 27.05.2017 | S-17-09 | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | 220/132/33 kV Substation at Toopran(meenaji pet) in Medak District along with connected lines | System Improvement | 27.01.2016 | 31.03.2021 | 60.8 | 1.824 | 6.08 | 3.8 | 6.536 | 79.04 |  |  | 68.43 |  |  |  | REC | 9.75 |  |  |  | 44.79 | 54.79 |  |  |  | 64.54
41 | TOO No.72 Dt:13.05.2016 | S-16-14 | TST/TS/ 220132/33 kV / Substation, Borampet RR District/ INVST- No. 07/16 - 2016-17 | 220/132/33 kV Substation at Borampet in Ranga Reddy district | System Improvement | 28.11.2016 | 31.03.2021 | 196.487 | 3.3449 | 20.3712 | 0.3778 | 11.9859 | 232.5668 |  |  | 182.98 |  |  |  | PFC | 78 |  |  |  | 56.88 | 86.73 |  |  |  | 164.73
42 | TOO (CE-construction) MS.NO.65 dt:23-03-2018 | S-17-24 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132 KV 2nd circuit stringing (28 km) from 132/33 KV SSAmangal to 132/33 KV Keshampet SS with bays | System Improvement | 01.04.2020 | 31.03.2022 | 8.3207 | 0.0324 | 0.868 | 0.2197 | 0.1069 | 9.5477 | [6 empty] | REC | 0.5 |  |  |  |  | 0 |  |  |  | 0.5
43 | TOO (CE_Construction-1)Ms.No.217 Dt:25.09.2018 |  | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 KV features at 132 KV Railway Traction Switching Station, Kothagudem, Kothagudem Bhadradri District | System Improvement | 01.04.2019 | 31.03.2021 | 6.9998 | 0.1909 | 0.9 | 1.1453 | 0.684 | 9.92 | [6 empty] | To be tied up | 5.98 |  |  |  |  | 1 |  |  |  | 6.98
[7 empty] | Total | 1695.1342 | 39.9686 | 180.3279 | 77.5782 | 141.7752 | 2134.7842 |  |  | 904.9321 |  |  |  |  | 653.7016 |  |  |  | 0 | 403.37 |  |  |  | 1057.0716 |  |  |  |  | -328.4
CHIEF ENGINEER
CONSTRUCTION

## 2021-22
1.1D ABSTRACT OF INVESTMENT PLAN ( FY 2021-22 ) OF CE/CONSTRUCTION
|  |  | Financial Year 2021-22 | [24 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year FY 2021-22 |  |  |  | Total Investments incurred up to previous year |  |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
[14 empty] | Internal Accrual Component of capex in year |  | Debt component of capex in year
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crores.) | Proposed IDC | Proposed other expence | % Capatalisation | OPENING BALANCE | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 | TOO (CE-Transmission) MS.NO.162 dt:26-08-2015 | S-15-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132 kV 2nd Circuit (9 KM) from 132/33 kV SS Domakonda to 132/33 kV SS Biknur | System Improvement | 01.04.2020 | 31.03.2022 | 7.371 | 0.313 | 0.89 | 0.0945 | 1.1215 | 9.79 |  |  | - |  |  |  | PFC | 5 |  |  |  |  | 3 |  |  |  | 8
2 | T.O.O (CE-Transmission) Ms.No.195 Dated:14.10.2015 | S-15-36 | TST/TS /132/33 kV SS Aipoor , Nalgonda /F-INVST- 01/2016-17 | 132/33 kV SS at Aipoor in Nalgonda district | System Improvement | 05.01.2017 | 31.03.2022 | 19.6933 | 0.3366 | 2.13 | 0.0841 | 1.2057 | 23.4497 |  |  | 18.9106 |  |  |  | REC | 14 |  |  |  |  | 5.25 |  |  |  | 19.25
3 | TOO (CE-Transmission) MS.NO.176 dt:22-12-2016 | S-16-13 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS with connected line at Tallapet in Adilabad District. | System Improvement | 01.04.2020 | 31.03.2022 | 15.585 | 0.3984 | 1.46 | 0.1786 | 0.4276 | 18.0496 |  |  | 0.1463 |  |  |  | REC | 5 |  |  |  |  | 6.7 |  |  |  | 11.7
4 | TOO (CE-Transmission) MS.NO.45 dt:31-03-2016 | S-16-15 | CRN.No. TST/TS/220/132/33 KVSS,Kachavani Singaram, R.R.Dist.Inves.Appl./No.9/17,2016-17 | Erection of 220/132/33 kV Substation at Kachavani Singaram in Ghatkesar Mandal of Ranga Reddy District along with connected lines | System Improvement | 01.04.2020 | 31.03.2022 | 40.9618 | 1.0324 | 4.9724 | 0.3462 | 3.6996 | 51.0124 |  |  | 40.32 |  |  |  | REC | 30 |  |  |  |  | 10 |  |  |  | 40
5 | TOO (CE-Transmission) MS.NO.32 dt:27-02-2017 | S-17-02 | CRN TS/TST/132/33 KV, GIS, R.P.Nilayam/Invest.Approval No. 8/17 - 2017-18 | 132/33 KV AIS/GIS at R.P. Nilayam with connected line in Medchal-Malkajgiri District. | System Improvement | 01.04.2020 | 31.03.2022 | 42.59 | 1.1891 | 4.8029 | 0.1529 | 4.0976 | 52.8325 |  |  | 42.89 |  |  |  | REC | 25 |  |  |  |  | 20 |  |  |  | 45
6 | TOO (CE-Transmission) MS.NO.28 dt:27-02-2017 | S-17-05 | CRN TS/TST/132/33 KV, GIS, Seetharambagh/Invest.Approval No.6/17-2017-18 | 132/33 KV Gas Insulated Sub-station (GIS) at Seetharambagh with connected UG cable & bay in Hyderabad District and connectivity from Asifnagar SS. | System Improvement | 01.04.2019 | 31.03.2022 | 56.3096 | 1.5947 | 6.362 | 0.0104 | 5.7146 | 69.9913 |  |  | 57.27 |  |  |  | REC | 32 |  |  |  |  | 32 |  |  |  | 64
7 | TOO (CE-Transmission) MS.NO.30 dt:27-02-2017 | S-17-07 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 KV IDA Mallapur Sub-station with connected line in Medchal-Malkajgiri District. | System Improvement | 01.04.2019 | 31.03.2022 | 17.2144 | 0.4116 | 1.905 | 0.1724 | 1.2523 | 20.9557 |  |  | 16.81 |  |  |  | REC | 8 |  |  |  |  | 9 |  |  |  | 17
8 | TOO (CE-construction) MS.NO.13 dt:20-01-2018 | S-17-19 | CRN No. TST/TS/Erection of 132/33 KV SS at Pitlam in Khammam Dist. Approval/No.04/2018-19 | 132/33 kV SS at Pitlam in Nizamabad District (13, dt.20.1.18 | System Improvement | 31.10.2018 | 31.03.2022 | 29.5454 | 0.2846 | 3.24 | 1.7077 | 1.0198 | 35.7975 |  |  | 31.8 |  |  |  | REC | 23 |  |  |  |  | 5.15 |  |  |  | 28.15
9 | TOO (CE-construction) MS.NO.14 dt:20-01-2018 | S-17-21 | CRN No. TST/TS/Erection of 132/33 KV SS at Pammy in Khammam Dist. Approval/No.03/2018-19 | 132/33kV SS at Pammy in Khammam District (14, dt.20.1.18) | System Improvement | 01.04.2020 | 31.03.2022 | 18.4685 | 0.3015 | 1.73 | 1.8088 | 1.0804 | 23.3892 | [6 empty] | To be tied up | 13 |  |  |  |  | 5.04 |  |  |  | 18.04
10 | T.O.O (CE-Transmission) Ms. No. 75, Dated: 19.05.2017 | S-17-22 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Puttandoddi (V), Itikyal (M), Mahaboobnagar District | System Improvement | 01.04.2020 | 31.03.2022 | 11.46 | 0.3438 | 1.146 | 0.6876 | 1.232 | 14.8694 |  |  | 12.03 |  |  |  | PFC | 7 |  |  |  |  | 5 |  |  |  | 12
11 | TOO (CE-construction) MS.NO.65 dt:23-03-2018 | S-17-24 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132 KV 2nd circuit stringing (28 km) from 132/33 KV SSAmangal to 132/33 KV Keshampet SS with bays | System Improvement | 01.04.2020 | 31.03.2022 | 8.3207 | 0.0324 | 0.868 | 0.2197 | 0.1069 | 9.5477 | [6 empty] | REC | 7.8 |  |  |  |  | 0.5 |  |  |  | 8.3
12 | TOO (CE-construction) MS.NO.43 dt:06-03-2018 | S-18-01 | CRN No.TST/TS/Erection of 132/33 KV Substation at Peechara in Wranagal District. Approval No. 05/2018-19 | 132/33 kV SS at Peechara in Warangal Dist. | System Improvement | 01.04.2020 | 31.03.2022 | 36.3068 | 0.3432 | 4.42 | 2.0594 | 1.2299 | 44.3593 |  |  | 39.1 |  |  |  | REC | 25 |  |  |  |  | 10.13 |  |  |  | 35.13
13 | T.O.O (CE-Construction) MS.No .95 Dated:02.05.2018 | S-18-02 |  | Erection of 220/132 kV Sub-Station at Ammavaripet in Warangal-Urban District | System Improvement | 31.10.2018 | 30.06.2021 | 84.9 | 2.547 | 15.02 | 15.282 | 9.1267 | 126.8757 |  |  | 54.83 |  |  |  | PFC | 40 |  |  |  |  | 59.5 |  |  |  | 99.5
14 | TOO (CE Construction) MS NO.193, Dt:30.08.2018 | S-18-04 | CRN No. TST/TS/Erection of 132/33 KV Sub station at Nagaram in suryapet District. Approval/No.14/18/2018-19, Dt:12.12.2018 | 132/33 KV SS Nagaram,Nalgonda District | System Improvement | 01.04.2019 | 31.03.2022 | 26.2586 | 0.2904 | 4.64 | 1.7427 | 1.0407 | 33.9724 |  |  | 25.17 |  |  |  | PFC | 20 |  |  |  |  | 5.98 |  |  |  | 25.98
15 | -- | -- | New scheme | Up-gradation of existing 132/33kV Asifabad to 220/132/33 kv SS | System Improvement | 01.04.2021 | 31.03.2023 | 50 | 1.5 | 5 | 3 | 5.375 | 64.875 | [7 empty] | 30 |  |  |  | 14.94 | 0 |  |  |  | 30
16 | -- | -- | New scheme | 132/33kV SS with connected line at Dhantanpur in Karimnagar District | System Improvement | 01.04.2021 | 31.03.2023 | 35.26 | 1.0578 | 3.526 | 2.1156 | 3.7904 | 45.7499 | [6 empty] | - | 10 |  |  |  |  | 0 |  |  |  | 10
17 | -- | -- | New scheme | 132/33 kV Ramasagar Karimnagar District | System Improvement | 01.04.2021 | 31.03.2023 | 28.26 | 0.8478 | 2.826 | 1.6956 | 3.0379 | 36.6673 | [6 empty] | - | 10 |  |  |  |  | 0 |  |  |  | 10
18 | -- | -- | New scheme | 132/33 KV Bommalaramaram SS Nalgonda Dist | System Improvement | 01.04.2021 | 31.03.2023 | 41.22 | 1.2366 | 4.122 | 2.4732 | 4.4311 | 53.483 | [6 empty] | - | 10 |  |  |  |  | 0 |  |  |  | 10
19 | -- | -- | New scheme | 132/33 KV SS Kajjarla, Adilabad District | System Improvement | 01.04.2021 | 31.03.2023 | 20.7 | 0.621 | 2.07 | 1.242 | 2.2252 | 26.8583 | [6 empty] | - | 10 |  |  |  |  | 0 |  |  |  | 10
20 | -- | -- | New scheme | 132/33 KV SS Raparthy, Medak District | System Improvement | 01.04.2021 | 31.03.2023 | 31.2 | 0.936 | 3.12 | 1.872 | 3.354 | 40.482 | [6 empty] | - | 10 |  |  |  |  | 0 |  |  |  | 10
21 | -- | -- | New scheme | Erection of 220 KV DC line from 400/220/132 KV Narsapur SS to 220/132/33 KV SS Minpur in Medak District | System Improvement | 01.04.2021 | 31.03.2022 | 75.37 | 2.2611 | 7.537 | 4.5222 | 8.1023 | 97.7926 | [7 empty] | 52 |  |  |  |  | 0 |  |  |  | 52
22 | -- | -- | New scheme | 220kV Substation with connected line and bay at Pharma City-I, Mucherla | System Improvement | 01.04.2020 | 31.03.2022 | 90.1 | 2.703 | 9.01 | 5.406 | 9.6858 | 116.9048 | [7 empty] | 40 |  |  |  |  | 29.35 |  |  |  | 69.35
23 | -- | -- | New scheme | 220kV Substation Mucherla with connected line and bay at Pharma City-II, | System Improvement | 01.04.2020 | 31.03.2022 | 90.1 | 2.703 | 9.01 | 5.406 | 9.6858 | 116.9048 | [7 empty] | 40 |  |  |  |  | 32.5 |  |  |  | 72.5
24 | -- | -- | New scheme | 220/132/33 kV SS at Gopanpalli | System Improvement | 01.04.2020 | 31.03.2022 | 75 | 2.25 | 7.5 | 4.5 | 8.0625 | 97.3125 | [7 empty] | 40 |  |  |  |  | 26 |  |  |  | 66
25 | TOO (CE-construction) MS.NO.260 dt:30-11-2018 | - | - | Up gradation of existing 132/33 KV RC Puram SS to 220/132/33 KV SS in Ranga Reddy District | System Improvement | 01.04.2020 | 31.03.2022 | 132.2946 | 3.9688 | 11.9065 | 8.2684 | 14.2217 | 170.66 | [7 empty] | 72 |  |  |  |  | 65 |  |  |  | 137
26 | - | - | New scheme | 132kV Substation with connectd line at Pharma City-I | System Improvement | 01.04.2020 | 31.03.2022 | 49 | 1.47 | 4.9 | 2.94 | 5.2975 | 63.6075 | [7 empty] | 15 |  |  |  |  | 16.25 |  |  |  | 31.25
27 | - | - | New scheme | 132kV Substation with connectd line at Pharma City-II | System Improvement | 01.04.2020 | 31.03.2022 | 49 | 1.47 | 4.9 | 2.94 | 5.2975 | 63.6075 | [7 empty] | 15 |  |  |  |  | 13 |  |  |  | 28
28 | TOO (CE-construction) MS.NO.11 dt:20-04-2018 |  | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | connecting the existing 132 kV Shapurnagar – Bhongir – Aleru line to 400/220/132 kV Malkaram SS and 400/220/132 kV Ghanapur SS (UG cable) | System Improvement | 01.04.2020 | 31.03.2022 | 14.8245 | 0.3325 | 1.56 | 2.0152 | 1.1834 | 19.9156 | [7 empty] | 9 |  |  |  |  | 5 |  |  |  | 14
29 | TOO (CE-construction) MS.NO.375 dt:03-06-2019 | - | - | 132 KV SS Patancheru in Medak District | System Improvement | 01.04.2020 | 31.03.2022 | 18.3178 | 0.54953 | 1.6486 | 1.1449 | 1.9692 | 23.63 | [7 empty] | 5 |  |  |  |  | 15 |  |  |  | 20
[7 empty] | Total | 1215.632 | 33.3259 | 132.2224 | 74.0881 | 118.0746 | 1573.343 | [7 empty] | 622.8 |  |  |  | 14.94 | 379.35 |  |  |  | 1002.15 |  |  |  |  | -328.4
CHIEF ENGINEER
CONSTRUCTION

## 2022-23
1.1D ABSTRACT OF INVESTMENT PLAN ( FY 2022-23 ) OF CE/CONSTRUCTION
|  |  | Financial Year 2022-23 | [24 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year FY 2022-23 |  |  |  | Total Investments incurred up to previous year | [8 empty] | Remarks
[14 empty] | Internal Accrual Component of capex in year |  | Debt component of capex in year |  |  |  |  | Annual
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crores.) | Proposed IDC | Proposed other expence | % Capatalisation | OPENING BALANCE | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 | -- | -- | New scheme | 220/33 kV GISS at Knowledge Park, T-Hub, Hyderabad | System Improvement | 01.04.2022 | 31.03.2024 | 280 | 8.4 | 28 | 16.8 | 30.1 | 363.3 | [6 empty] | -- | 150 |  |  |  | 859 | 0 |  |  |  | 150
2 | -- | -- | New scheme | 220/132 kV SS with connected line and bay at Venkatapur Warangal District. | System Improvement | 01.04.2022 | 31.03.2024 | 107.6 | 3.228 | 10.76 | 6.456 | 11.567 | 139.611 | [6 empty] | -- | 80 |  |  |  | 14.94 | 0 |  |  |  | 80
3 | -- | -- | New scheme | 220 KV DC line from 220/11 KV Gudipalligattu LIS to 220 KV Nagarkurnool SS including bays. | System Improvement | 01.04.2022 | 31.03.2024 | 25.5 | 0.765 | 2.55 | 1.53 | 2.7412 | 33.0862 | [6 empty] | -- | 25 |  |  |  | 23.41 | 0 |  |  |  | 25
4 | -- | -- | New scheme | 132/33 kV SS with connected line at Somaram Warangal District | System Improvement | 01.04.2022 | 31.03.2024 | 51.2 | 1.536 | 5.12 | 3.072 | 5.504 | 66.432 | [6 empty] | -- | 20 |  |  |  |  | 0 |  |  |  | 20
5 | -- | -- | New scheme | 132/33 KV SS Devarakonda, Nalgonda Didtrict | System Improvement | 01.04.2022 | 31.03.2024 | 27.62 | 0.8286 | 2.762 | 1.6572 | 2.9691 | 35.837 | [6 empty] | -- | 20 |  |  |  |  | 0 |  |  |  | 20
6 | -- | -- | New scheme | 132/33 KV SS with connected line & bay at Wankidi, Adilabad District | System Improvement | 01.04.2022 | 31.03.2024 | 42.26 | 1.2678 | 4.226 | 2.5356 | 4.543 | 54.8323 | [6 empty] | -- | 32 |  |  |  |  | 0 |  |  |  | 32
7 |  | -- | New scheme | 132 KV LILO (6 km) of 132 KV Mulugu-Chelpur-Kamalapur line on multy circuit towers to proposed 220/132 KV SS Venkatapur | System Improvement | 01.04.2022 | 31.03.2023 | 10.2 | 0.306 | 1.02 | 0.612 | 1.0965 | 13.2345 | [6 empty] | -- | 13.23 |  |  |  |  | 0 |  |  |  | 13.23
8 | -- | -- | New scheme | 132 KV DC/SC line (37 km) from 220/132 KV SS Nagarkurnool to 132/33 KV Achampet SS | System Improvement | 01.04.2022 | 31.03.2023 | 25.9 | 0.777 | 2.59 | 1.554 | 2.7843 | 33.6052 | [6 empty] | -- | 25 |  |  |  |  | 0 |  |  |  | 25
9 | -- | -- | New scheme | 132 KV sub stations at Nandigama & Chowderguda in shadnagar Rangareddy District | System Improvement | 01.04.2022 | 31.03.2024 | 30 | 0.9 | 3 | 1.8 | 3.225 | 38.925 | [7 empty] | 20 |  |  |  |  | 0 |  |  |  | 20
10 | -- | -- | New scheme | 132/33 KV SS with connected line & bay at Chada, Nalgonda District | System Improvement | 01.04.2022 | 31.03.2024 | 38.76 | 1.1628 | 3.876 | 2.3256 | 4.1667 | 50.2911 | [6 empty] | -- | 30 |  |  |  |  | 0 |  |  |  | 30
11 | -- | -- | New scheme | Substations proposed to meet the unforseen load demand due to industrial development, commercial, residencial loads & power system requirement | System Improvement | 01.04.2022 | 31.03.2023 | 0 | [12 empty] | 90 | [8 empty] | 90
12 | -- | -- | New scheme | Up-gradation of existing 132/33kV Asifabad to 220/132/33 kv SS | System Improvement | 01.04.2021 | 31.03.2023 | 50 | 1.5 | 5 | 3 | 5.375 | 64.875 | [7 empty] | 10 |  |  |  | 14.94 | 30 |  |  |  | 40
13 | -- | -- | New scheme | 132/33kV SS with connected line at Dhantanpur in Karimnagar District | System Improvement | 01.04.2021 | 31.03.2023 | 35.26 | 1.0578 | 3.526 | 2.1156 | 3.7904 | 45.7499 | [6 empty] | - | 5 |  |  |  |  | 10 |  |  |  | 15
14 | -- | -- | New scheme | 132/33 kV Ramasagar Karimnagar District | System Improvement | 01.04.2021 | 31.03.2023 | 28.26 | 0.8478 | 2.826 | 1.6956 | 3.0379 | 36.6673 | [6 empty] | - | 5 |  |  |  |  | 10 |  |  |  | 15
15 | -- | -- | New scheme | 132/33 KV Bommalaramaram SS Nalgonda Dist | System Improvement | 01.04.2021 | 31.03.2023 | 41.22 | 1.2366 | 4.122 | 2.4732 | 4.4311 | 53.483 | [6 empty] | - | 5 |  |  |  |  | 10 |  |  |  | 15
16 | -- | -- | New scheme | 132/33 KV SS Kajjarla, Adilabad District | System Improvement | 01.04.2021 | 31.03.2023 | 20.7 | 0.621 | 2.07 | 1.242 | 2.2252 | 26.8583 | [6 empty] | - | 5 |  |  |  |  | 10 |  |  |  | 15
17 | -- | -- | New scheme | 132/33 KV SS Raparthy, Medak District | System Improvement | 01.04.2021 | 31.03.2023 | 31.2 | 0.936 | 3.12 | 1.872 | 3.354 | 40.482 | [6 empty] | - | 5 |  |  |  |  | 10 |  |  |  | 15
[7 empty] | Total | 845.68 | 25.3704 | 84.568 | 50.7408 | 90.9106 | 1097.2698 | [7 empty] | 540.23 |  |  |  | 897.35 |  |  |  |  | 620.23 |  |  |  |  | -328.4
CHIEF ENGINEER
CONSTRUCTION

## 2023-24
1.1D ABSTRACT OF INVESTMENT PLAN ( FY 2023-24 ) OF CE/CONSTRUCTION
|  |  | Financial Year 2023-24 | [24 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year FY 2023-24 |  |  |  | Total Investments incurred up to previous year |  |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
[14 empty] | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt component of capex in year |  |  |  |  | Annual
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.lCrores) |  |  | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crores.) | Proposed IDC | Proposed other expence | % Capatalisation | OPENING BALANCE | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 |  |  | New scheme | 220/33 kV GISS at Knowledge Park, T-Hub, Hyderabad | System Improvement | 01.04.2022 | 31.03.2024 | 280 | 8.4 | 28 | 16.8 | 30.1 | 363.3 | [6 empty] | -- | 150 |  |  |  |  | 150 |  |  |  | 300
2 | -- | -- | New scheme | 220 KV features at 132/33 KV SS kandukur | System Improvement | 01.04.2023 | 31.03.2025 | 80 | 2.4 | 8 | 4.8 | 8.6 | 103.8 | [6 empty] | - | 40 |  |  |  |  | 0 |  |  |  | 40
3 | -- | -- | New scheme | 220 KV SS Abdullapurmet | System Improvement | 01.04.2023 | 31.03.2025 | 98 | 2.94 | 9.8 | 5.88 | 10.535 | 127.155 | [6 empty] | - | 40 |  |  |  |  | 0 |  |  |  | 40
4 | -- | -- | New scheme | 132/33 KV SS with connected line & bays at pangal,Mahabubnagar Dist. | System Improvement | 01.04.2023 | 31.03.2025 | 28.96 | 0.8688 | 2.896 | 1.7376 | 3.1132 | 37.5756 | [7 empty] | 25 |  |  |  |  | 0 |  |  |  | 25
5 | -- | -- | New scheme | 132/33 KV SS with connected line at Vanamvarikistapuram, Khammam Dist. | System Improvement | 01.04.2023 | 31.03.2025 | 25.1 | 0.753 | 2.51 | 1.506 | 2.6986 | 32.5676 | [7 empty] | 25 |  |  |  |  | 0 |  |  |  | 25
6 | -- | -- | New scheme | 132/33 KV SS with connected line & bay at Aziznagar, Rangareddy District. | System Improvement | 01.04.2023 | 31.03.2025 | 35.87 | 1.0761 | 3.587 | 2.1522 | 3.856 | 46.5413 | [6 empty] | - | 30 |  |  |  |  | 0 |  |  |  | 30
7 | -- | -- | New scheme | 33 KV features atb 220/11 KV Vemnur in Karimnagar Dist | System Improvement | 01.04.2023 | 31.03.2025 | 35 | 1.05 | 3.5 | 2.1 | 3.7625 | 45.4125 | [7 empty] | 35 |  |  |  |  | 0 |  |  |  | 35
8 | -- | -- | New scheme | 220/132 kV SS with connected line and bay at Venkatapur Warangal District. | System Improvement | 01.04.2022 | 31.03.2024 | 107.6 | 3.228 | 10.76 | 6.456 | 11.567 | 139.611 | [6 empty] | -- | 40 |  |  |  | 14.94 | 80 |  |  |  | 120
9 | -- | -- | New scheme | 220 KV DC line from 220/11 KV Gudipalligattu LIS to 220 KV Nagarkurnool SS including bays. | System Improvement | 01.04.2022 | 31.03.2024 | 25.5 | 0.765 | 2.55 | 1.53 | 2.7412 | 33.0862 | [6 empty] | -- | 15 |  |  |  | 23.41 | 25 |  |  |  | 40
10 | -- | -- | New scheme | 132/33 kV SS with connected line at Somaram Warangal District | System Improvement | 01.04.2022 | 31.03.2024 | 51.2 | 1.536 | 5.12 | 3.072 | 5.504 | 66.432 | [6 empty] | -- | 10 |  |  |  |  | 20 |  |  |  | 30
11 | -- | -- | New scheme | 132/33 KV SS Devarakonda, Nalgonda Didtrict | System Improvement | 01.04.2022 | 31.03.2024 | 27.62 | 0.8286 | 2.762 | 1.6572 | 2.9691 | 35.837 | [6 empty] | -- | 5 |  |  |  |  | 20 |  |  |  | 25
12 | -- | -- | New scheme | 132/33 KV SS with connected line & bay at Wankidi, Adilabad District | System Improvement | 01.04.2022 | 31.03.2024 | 42.26 | 1.2678 | 4.226 | 2.5356 | 4.543 | 54.8323 | [6 empty] | -- | 13 |  |  |  |  | 32 |  |  |  | 45
13 | -- | -- | New scheme | 132 KV sub stations at Nandigama & Chowderguda in shadnagar Rangareddy District | System Improvement | 01.04.2022 | 31.03.2024 | 30 | 0.9 | 3 | 1.8 | 3.225 | 38.925 | [7 empty] | 10 |  |  |  |  | 20 |  |  |  | 30
14 | -- | -- | New scheme | 132/33 KV SS with connected line & bay at Chada, Nalgonda District | System Improvement | 01.04.2022 | 31.03.2024 | 38.76 | 1.1628 | 3.876 | 2.3256 | 4.1667 | 50.2911 | [6 empty] | -- | 10 |  |  |  |  | 30 |  |  |  | 40
` |  |  |  | Substations proposed to meet the unforseen load demand due to industrial development, commercial, residencial loads & power system requirement | System Improvement | 01.04.2023 | 31.03.2024 | [13 empty] | 80 |  |  |  |  | 0 |  |  |  | 80
[7 empty] | Total | 905.87 | 27.1761 | 90.587 | 54.3522 | 97.3813 | 1175.3666 | [7 empty] | 528 |  |  |  | 0 | 377 |  |  |  | 905 |  |  |  |  | -328.4
CHIEF ENGINEER
CONSTRUCTION