## 2018-19
Format 1.1(d) ABSTRACT OF INVESTMENT PLAN ( FY 2018-19) OF (400kV Schemes)
(Amount Rs. in Crs)
Base Year 2018-19
Sl No. | Project Code | Project Title |  |  | Expenditure as on 31.03.2018 | Opening Balance as on 31.03.2018 | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
|  |  | Expenciture as on 31.03.2018) | Budget (as on 05.03.2018) |  |  |  |  | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
1 | APT/TS/SCCL(Jaipur)-Evacuation-400kV Quad D/C /F-INVST-42/2013 | Jaipur Power Transmission Scheme P-10-01 | 149.252 | 86.33 | 577.83 | 0.2 | Mar'2013 | Mar' 2021 | 686.42 | 20.59 | 61.59 |  | 73.79 | 842.39 | [11 empty] | 4.85 |  |  |  | 5.05
2 | APT/TS/400kV Suryapet/F-INVST-28/2014 | Suryapet Power Transmission Scheme (S-14-02) | 649.2424 | 790.09 | 943.11 | 28 | Jul'2013 | Mar' 2021 | 1426.53 | 42.796 | 144.8 |  | 153.35 | 1767.476 | [11 empty] | 9.13 |  |  |  | 37.13
3 | Lr.No.APERC/Secy/DD(Trans)/F:E-700-8/2014 dated 06.08.2014 | Reactor Scheme -II (S-14-01) | 46.6751 | 23.49 | 46.68 | 0 | Sep'2016 | Mar' 2020 | 80.737 |  |  |  |  | 80.737 | [11 empty] | 2.92 |  |  |  | 2.92
4 | TST / TS / 400kV Dindi Substation /Trans. improvement scheme /Invest. Appoval No.16/15, Dt.02.01.2016 | Dindi System Improvement Scheme (P-15-01) | 126.0068 | 72.8 | 116.44 | 18.52 | Nov' 2015 | Mar' 2021 | 251.97 | 7.56 | 27.08 |  | 34.92 | 321.53 | [11 empty] | 24.04 |  |  |  | 42.56
5 | TST / TS / KTPS VII STAGE (1x800MW)/POWER TRANSMISSION/INVEST. APPROVAL/Revised approval 17/17 , 2017-18, dec'2017 | KTPS 1x800Mw, VII stage Power Evacuation scheme (P-15-04,S-15-24,S-16-05) | 378.6576 | 364.93 | 396.75 | 388.59 | Jul'2015 | Mar'2022 | 1150.3092 | 34.17 | 105.61 |  | 122.43 | 1412.5192 | [11 empty] | 509.39 |  |  |  | 897.98
6 | TST/TS/765kV Wardha –Hyderabad Link Transmission scheme-Erection of 400kV Sub stations at Maheshwaram and Manikonda with connected Transmission network investment proposal revised approval NO 16/17-2017-18 Dt.19.12.2017 | 765kV Wardha –Hyderabad Link Transmission scheme (S-15-13) | 447.2782 | 279.52 | 454.88 | 229.39 | Nov' 2015 | Mar'2021 | 1037.6982 | 30.82 | 100.08 |  | 110.45 | 1279.0482 | [11 empty] | 309.04 |  |  |  | 538.43
7 | TST/TS/315 MVA PTR,Augmentation/DICHPALLY,VELTOOR,Gajwel/revised APPROVAL NO 03/17,2017-18 dated 04.05.2017 | Augmentation Scheme(A-15-11,A-15-10) | 45.3393 | 26.67 | 53.9 | 18.2 | Feb'2016 | Mar' 2020 | 95.5909 |  |  |  |  | 95.5909 | [11 empty] | 1.22 |  |  |  | 19.42 |  |  | 100
8 | TST/TS/Bhadradri (4X270) MW Thermal power Transmission/ Investment Approval NO17/15, Dt.02.01.2016 | Bhadradri Thermal Power Transmission Scheme 4 X 270 MW (P-15-03,S-12-23,S-15-20,S-15-21,S-15-22,S-15-25) | 617.0321 | 516.9 | 731.88 | 489.38 | Nov' 2015 | Mar'2021 | 1055.78 | 31.67 | 103.41 |  | 113.496 | 1304.356 | [11 empty] | 52.91 |  |  |  | 542.29
9 | TST/TS/400kV Nirmal Power Transmission Scheme-Power Evacuation from M/s. SCCL 2x600MW units and for upcoming 1x800MW units. /F.Revised approval/NO 07/2018-19 dated 19.07.2018 | Nirmal Power Transmission Scheme (P-12-02, S-12-30, S-12-31) | 290.408 | 422.93 | 569.28 | 456.7 | Dec'2015 | Mar'2022 | 943.9339 | 28.037 | 78.61 |  | 100.468 | 1151.0489 | [11 empty] | 152.13 |  |  |  | 608.83
10 | TS/TST/Invest. Approval/PTR Augmentation/400kV Malkaram & Shankerpally No 11/2017, 17-18 dated 30.08.2017 | Augmentation Scheme-III (A-17-03) | 0.0036841 | - | 0 | 0.0036841 | Dec'2017 | Nov'2019 | 74.4433 |  |  |  |  | 74.4433 | [11 empty] | 28.6 |  |  |  | 28.6037 |  |  | 100
11 | TST/TS/Rayadurg System Improvement Scheme.Approval/NO 02/2018-19 dated 24.05.2018 | Rayadurg System Improvement Scheme (S-17-08) | 0.072673 | - | 0.07 | 0.67 | Sep'2018 | May' 2021 | 1469.0147 | 43.63 | 117.4 |  | 156.36 | 1786.4047 | [11 empty] | 199.56 |  |  |  | 200.23
12 | TS/TST/Investment approval/Telangana STPP-1 (2x800MW) NO, 10/2017 dated 23.08.2017 | Telangana STPP-I Power Evacuation (P-16-01) | 106.4911 | 124.24 | 106.49 | 104.51 | Oct'2017 | May' 2021 | 1013.6087 | 30.107 | 105.26 |  | 107.88 | 1256.8557 | [11 empty] | 448.56 |  |  |  | 553.07
13 |  | Ring Main Transmission Scheme (S-05-02) |  |  |  | 0 | [19 empty] | 2.04 |  |  |  | 2.04 |  |  | 100
14 |  | 400kV Augmentation Scheme-II (A-11-01) |  |  |  | 0 | [19 empty] | 0.51 |  |  |  | 0.51 |  |  | 100
15 |  | Wind Power Evacuation Scheme (P-12-04) |  |  |  | 0 | [19 empty] | 2.72 |  |  |  | 2.72 |  |  | 100
[6 empty] | 1734.1637 | [19 empty] | 1747.62 |  |  |  | 3481.7837
DC Works
1 |  | Execution of 2 Nos Feeder bays and 8 Nos Metering Bays at STPP,Jaipur (D-17-02) |  |  |  | 9.71 | June'2017 | Mar'2020 | 28.21 |  |  |  |  | 28.21 | [11 empty] | 12.93 |  |  |  | 22.64 |  |  | 100
2 |  | 2 Nos Bay Extensions at 400kV Dichpally SS (D-15-09) |  |  |  | 0 | [19 empty] | 3.07 |  |  |  | 3.07 |  |  | 100
3 |  | Diversion of 400kV Gajwel-Shply TMDC Line (D-18-02) |  |  |  | 0 | [19 empty] | 6.54 |  |  |  | 6.54 |  |  | 100
| Total |  |  |  | 3997.31 | 1743.8737 | [7 empty] | 11400.61 | [11 empty] | 1770.16 |  |  |  | 3514.0337
Chief Engineer/400kV

## 2019-20
Format 1.1(d) ABSTRACT OF INVESTMENT PLAN ( FY 2019-20) OF (400kV Schemes)
(Amount Rs. in Crs)
Base Year 2019-20
Sl No. | Project Code | Project Title |  |  | Expenditure as on 31.03.2018 | Opening Balance as on 31.03.2019 | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
|  |  | Expenciture as on 31.03.2018) | Budget (as on 05.03.2018) |  |  |  |  | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
1 | APT/TS/SCCL(Jaipur)-Evacuation-400kV Quad D/C /F-INVST-42/2013 | Jaipur Power Transmission Scheme P-10-01 | 149.252 | 86.33 | 577.83 | 0 | Mar'2013 | Mar' 2021 | 686.42 | 20.59 | 61.59 |  | 73.79 | 842.39 | [7 empty] | 3.5 |  |  |  | 3.5 |  |  |  | 3.5
2 | APT/TS/400kV Suryapet/F-INVST-28/2014 | Suryapet Power Transmission Scheme (S-14-02) | 649.2424 | 790.09 | 943.11 | 5.96 | Jul'2013 | Mar' 2021 | 1426.53 | 42.796 | 144.8 |  | 153.35 | 1767.476 | [7 empty] | 8 |  |  |  | 8 |  |  |  | 13.96
3 | Lr.No.APERC/Secy/DD(Trans)/F:E-700-8/2014 dated 06.08.2014 | Reactor Scheme -II (S-14-01) | 46.6751 | 23.49 | 46.68 | 0 | Sep'2016 | Mar' 2020 | 80.737 |  |  |  |  | 80.737 | [7 empty] | 0.5 |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 100
5 | TST / TS / 400kV Dindi Substation /Trans. improvement scheme /Invest. Appoval No.16/15, Dt.02.01.2016 | Dindi System Improvement Scheme (P-15-01) | 126.0068 | 72.8 | 116.44 | 38.09 | Nov' 2015 | Mar' 2021 | 251.97 | 7.56 | 27.08 |  | 34.92 | 321.53 | [7 empty] | 13 |  |  |  | 13 |  |  |  | 51.09
6 | TST / TS / KTPS VII STAGE (1x800MW)/POWER TRANSMISSION/INVEST. APPROVAL/Revised approval 17/17 , 2017-18, dec'2017 | KTPS 1x800Mw, VII stage Power Evacuation scheme (P-15-04,S-15-24,S-16-05) | 378.6576 | 364.93 | 396.75 | 741.65 | Jul'2015 | Mar'2022 | 1150.3092 | 34.17 | 105.61 |  | 122.43 | 1412.5192 | [7 empty] | 81 |  |  |  | 81 |  |  |  | 822.65
7 | TST/TS/765kV Wardha –Hyderabad Link Transmission scheme-Erection of 400kV Sub stations at Maheshwaram and Manikonda with connected Transmission network investment proposal revised approval NO 16/17-2017-18 Dt.19.12.2017 | 765kV Wardha –Hyderabad Link Transmission scheme (S-15-13) | 447.2782 | 279.52 | 454.88 | 214.44 | Nov' 2015 | Mar'2021 | 1037.6982 | 30.82 | 100.08 |  | 110.45 | 1279.0482 | [7 empty] | 103 |  |  |  | 103 |  |  |  | 317.44
8 | TST/TS/315 MVA PTR,Augmentation/DICHPALLY,VELTOOR,Gajwel/revised APPROVAL NO 03/17,2017-18 dated 04.05.2017 | Augmentation Scheme(A-15-11,A-15-10) | 45.3393 | 26.67 | 53.9 | 0 | Feb'2016 | Mar' 2020 | 95.5909 |  |  |  |  | 95.5909 | [7 empty] | 0.5 |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 100
9 | TST/TS/Bhadradri (4X270) MW Thermal power Transmission/ Investment Approval NO17/15, Dt.02.01.2016 | Bhadradri Thermal Power Transmission Scheme 4 X 270 MW (P-15-03,S-12-23,S-15-20,S-15-21,S-15-22,S-15-25) | 617.0321 | 516.9 | 731.88 | 37.65 | Nov' 2015 | Mar'2021 | 1055.78 | 31.67 | 103.41 |  | 113.496 | 1304.356 | [7 empty] | 27 |  |  |  | 27 |  |  |  | 64.65
10 | TST/TS/400kV Nirmal Power Transmission Scheme-Power Evacuation from M/s. SCCL 2x600MW units and for upcoming 1x800MW units. /F.Revised approval/NO 07/2018-19 dated 19.07.2018 | Nirmal Power Transmission Scheme (P-12-02, S-12-30, S-12-31) | 290.408 | 422.93 | 569.28 | 142.69 | Dec'2015 | Mar'2022 | 943.9339 | 28.037 | 78.61 |  | 100.468 | 1151.0489 | [7 empty] | 43 |  |  |  | 43 |  |  |  | 185.69
11 | TS/TST/Invest. Approval/PTR Augmentation/400kV Malkaram & Shankerpally No 11/2017, 17-18 dated 30.08.2017 | Augmentation Scheme-III (A-17-03) | 0.0036841 | - | 0 | 0.0036 | Dec'2017 | Mar'2020 | 74.4433 |  |  |  |  | 74.4433 | [7 empty] | 2 |  |  |  | 2 |  |  |  | 2.0036 |  |  | 100
12 | TST/TS/Rayadurg System Improvement Scheme.Approval/NO 02/2018-19 dated 24.05.2018 | Rayadurg System Improvement Scheme (S-17-08) | 0.072673 | - | 0.07 | 200.23 | Sep'2018 | May' 2021 | 1469.0147 | 43.63 | 117.4 |  | 156.36 | 1786.4047 | [7 empty] | 700 |  |  |  | 700 |  |  |  | 900.23
13 | TS/TST/Investment approval/Telangana STPP-1 (2x800MW) NO, 10/2017 dated 23.08.2017 | Telangana STPP-I Power Evacuation (P-16-01) | 106.4911 | 124.24 | 106.49 | 538.25 | Oct'2017 | May' 2021 | 1013.6087 | 30.107 | 105.26 |  | 107.88 | 1256.8557 | [7 empty] | 184 |  |  |  | 184 |  |  |  | 722.25
14 | To be Applied | Yadradri Power Evacuation | - |  |  | 0 | Jan'2020 | Mar' 2024 | 1887.67 | 56.07 | 209.7 |  | 200.91 | 2354.35 | [7 empty] | 14 |  |  |  | 14 |  |  |  | 14
15 | Applied & approval is pending | KTPP System Improvement Scheme |  |  |  | 0 | Jan'2020 | Mar' 2024 | 372.58 | 11.07 | 30.92 |  | 39.66 | 454.23 | [7 empty] | 15.5 |  |  |  | 15.5 |  |  |  | 15.5
16 | Applied & approval is pending | Reactor Scheme -III |  |  |  | 0 | Jan'2020 | May'2022 | 201.44 | 5.98 | 20.92 |  | 21.44 | 249.78 | [7 empty] | 5 |  |  |  | 5 |  |  |  | 5
DC Works
|  | Execution of 2 Nos Feeder bays and 8 Nos Metering Bays at STPP,Jaipur (D-17-02) |  |  |  | 0 | June'2017 | Mar'2020 | 28.21 |  |  |  |  | 28.21 | [7 empty] | 1.5 |  |  |  | 5.57 |  |  |  | 5.57 |  |  | 100
15 | To be Applied | KTPP System Improvement Scheme |  |  |  |  | 2019-01-01 | 2022-03-01 | 467.5145 |  |  |  |  | 467.5145 | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Total |  |  |  | 3997.31 | 1918.9636 | [7 empty] | 14458.97 | [7 empty] | 1201.5 |  |  |  | 1201.5 |  |  |  | 3120.4636
Chief Engineer/400kV

## 2020.21
Format 1.1(d) ABSTRACT OF INVESTMENT PLAN ( FY 2020-21) OF (400kV Schemes)
(Amount Rs. in Crs)
Base Year 2020-21
Sl No. | Project Code | Project Title |  |  |  | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
|  |  | SAP ( as on 31.03.2018) | Budget (as on 05.03.2018) | final as on 31.03.2018 |  |  | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
1 | APT/TS/SCCL(Jaipur)-Evacuation-400kV Quad D/C /F-INVST-42/2013 | Jaipur Power Transmission Scheme | 149.252 | 86.33 | 577.83 | Mar'2013 | Mar' 2021 | 686.42 | 20.59 | 61.59 |  | 73.79 | 842.39 | [7 empty] | 1 |  |  |  | 1 |  |  |  | 4.5 |  |  | 100
2 | APT/TS/400kV Suryapet/F-INVST-28/2014 | Suryapet Power Transmission Scheme | 649.2424 | 790.09 | 943.11 | Jul'2013 | Mar' 2021 | 1426.53 | 42.796 | 144.8 |  | 153.35 | 1767.476 | [7 empty] | 4 |  |  |  | 4 |  |  |  | 17.96 |  |  | 100
3 | TST / TS / 400kV Dindi Substation /Trans. improvement scheme /Invest. Appoval No.16/15, Dt.02.01.2016 | Dindi System Improvement Scheme | 126.0068 | 72.8 | 116.44 | Nov' 2015 | Mar' 2021 | 251.97 | 7.56 | 27.08 |  | 34.92 | 321.53 | [7 empty] | 16 |  |  |  | 16 |  |  |  | 67.09 |  |  | 100
4 | TST / TS / KTPS VII STAGE (1x800MW)/POWER TRANSMISSION/INVEST. APPROVAL/Revised approval 17/17 , 2017-18, dec'2017 | KTPS 1x800Mw, VII stage Power Evacuation scheme | 378.6576 | 364.93 | 396.75 | Jul'2015 | Mar'2022 | 1150.3092 | 34.17 | 105.61 |  | 122.43 | 1412.5192 | [7 empty] | 28.85 |  |  |  | 28.85 |  |  |  | 851.5
5 | TST/TS/765kV Wardha –Hyderabad Link Transmission scheme-Erection of 400kV Sub stations at Maheshwaram and Manikonda with connected Transmission network investment proposal revised approval NO 16/17-2017-18 Dt.19.12.2017 | 765kV Wardha –Hyderabad Link Transmission scheme | 447.2782 | 279.52 | 454.88 | Nov' 2015 | Mar'2021 | 1037.6982 | 30.82 | 100.08 |  | 110.45 | 1279.0482 | [7 empty] | 92 |  |  |  | 92 |  |  |  | 409.44 |  |  | 100
6 | TST/TS/Bhadradri (4X270) MW Thermal power Transmission/ Investment Approval NO17/15, Dt.02.01.2016 | Bhadradri Thermal Power Transmission Scheme 4 X 270 MW Power Evacuation Scheme | 617.0321 | 516.9 | 731.88 | Nov' 2015 | Mar'2021 | 1055.78 | 31.67 | 103.41 |  | 113.496 | 1304.356 | [7 empty] | 10 |  |  |  | 10 |  |  |  | 74.65 |  |  | 100
7 | TST/TS/400kV Nirmal Power Transmission Scheme-Power Evacuation from M/s. SCCL 2x600MW units and for upcoming 1x800MW units. /F.Revised approval/NO 07/2018-19 dated 19.07.2018 | Nirmal Power Transmission Scheme | 290.408 | 422.93 | 569.28 | Dec'2015 | Mar'2022 | 943.9339 | 28.037 | 78.61 |  | 100.468 | 1151.0489 | [7 empty] | 33 |  |  |  | 33 |  |  |  | 218.69
8 | TST/TS/Rayadurg System Improvement Scheme.Approval/NO 02/2018-19 dated 24.05.2018 | Rayadurg System Improvement Scheme | 0.072673 | - | 0.07 | Sep'2018 | May' 2021 | 1469.0147 | 43.63 | 117.4 |  | 156.36 | 1786.4047 | [7 empty] | 300 |  |  |  | 300 |  |  |  | 1200.23
9 | TS/TST/Investment approval/Telangana STPP-1 (2x800MW) NO, 10/2017 dated 23.08.2017 | Telangana STPP-I Power Evacuation | 106.4911 | 124.24 | 106.49 | Oct'2017 | May' 2021 | 1013.6087 | 30.107 | 105.26 |  | 107.88 | 1256.8557 | [7 empty] | 67 |  |  |  | 67 |  |  |  | 789.25
10 | To be Applied | Yadradri Power Evacuation | - |  |  | Jan'2020 | Mar' 2024 | 1887.67 | 56.07 | 209.7 |  | 200.91 | 2354.35 | [7 empty] | 577.75 |  |  |  | 577.75 |  |  |  | 591.75
11 | Applied & approval is pending | KTPP System Improvement Scheme |  |  |  | Jan'2020 | Mar' 2024 | 372.58 | 11.07 | 30.92 |  | 39.66 | 454.23 | [7 empty] | 125 |  |  |  | 125 |  |  |  | 140.5
12 | Applied & approval is pending | Reactor Scheme -III |  |  |  | Jan'2020 | May'2022 | 201.44 | 5.98 | 20.92 |  | 21.44 | 249.78 | [7 empty] | 80 |  |  |  | 80 |  |  |  | 85
| Total | [11 empty] | 14179.9888 | [7 empty] | 1334.6 |  |  |  | 1334.6 |  |  |  | 4450.56
Chief Engineer/400kV

## 2021.22
Format 1.1(d) ABSTRACT OF INVESTMENT PLAN ( FY 2021-22) OF (400kV Schemes)
(Amount Rs. in Crs)
Base Year 2021-22
Sl No. | Project Code | Project Title |  |  |  | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
|  |  | SAP ( as on 31.03.2018) | Budget (as on 05.03.2018) | final as on 31.03.2018 |  |  | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year (Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
4 | TST / TS / KTPS VII STAGE (1x800MW)/POWER TRANSMISSION/INVEST. APPROVAL/Revised approval 17/17 , 2017-18, dec'2017 | KTPS 1x800Mw, VII stage Power Evacuation scheme | 378.6576 | 364.93 | 396.75 | Jul'2015 | Mar'2022 | 1150.3092 | 34.17 | 105.61 |  | 122.43 | 1412.5192 | [7 empty] | 7 |  |  |  | 7 |  |  |  | 858.5 |  |  | 100
7 | TST/TS/400kV Nirmal Power Transmission Scheme-Power Evacuation from M/s. SCCL 2x600MW units and for upcoming 1x800MW units. /F.Revised approval/NO 07/2018-19 dated 19.07.2018 | Nirmal Power Transmission Scheme | 290.408 | 422.93 | 569.28 | Dec'2015 | Mar'2022 | 943.9339 | 28.037 | 78.61 |  | 100.468 | 1151.0489 | [7 empty] | 24 |  |  |  | 24 |  |  |  | 242.69 |  |  | 100
8 | TST/TS/Rayadurg System Improvement Scheme.Approval/NO 02/2018-19 dated 24.05.2018 | Rayadurg System Improvement Scheme | 0.072673 | - | 0.07 | Sep'2018 | May' 2021 | 1469.0147 | 43.63 | 117.4 |  | 156.36 | 1786.4047 | [7 empty] | 220 |  |  |  | 220 |  |  |  | 1420.23 |  |  | 100
9 | TS/TST/Investment approval/Telangana STPP-1 (2x800MW) NO, 10/2017 dated 23.08.2017 | Telangana STPP-I Power Evacuation | 106.4911 | 124.24 | 106.49 | Oct'2017 | May' 2021 | 1013.6087 | 30.107 | 105.26 |  | 107.88 | 1256.8557 | [7 empty] | 20 |  |  |  | 20 |  |  |  | 809.25 |  |  | 100
10 | To be Applied | Yadradri Power Evacuation | - |  |  | Jan'2020 | Mar' 2024 | 1887.67 | 56.07 | 209.7 |  | 200.91 | 2354.35 | [7 empty] | 540 |  |  |  | 540 |  |  |  | 1131.75
11 | Applied & approval is pending | KTPP System Improvement Scheme |  |  |  | Jan'2020 | Mar' 2024 | 372.58 | 11.07 | 30.92 |  | 39.66 | 454.23 | [7 empty] | 134 |  |  |  | 134 |  |  |  | 274.5
| Applied & approval is pending | Reactor Scheme -III |  |  |  | Jan'2020 | May'2022 | 201.44 | 5.98 | 20.92 |  | 21.44 | 249.78 | [7 empty] | 70 |  |  |  | 70 |  |  |  | 155
[13 empty] | 8665.1885 | [7 empty] | 1015 |  |  |  | 1015 |  |  |  | 4891.92
'file:///tmp/in/input.xls'#$2021.22
Chief Engineer/400kV

## 2022.23
Format 1.1(d) ABSTRACT OF INVESTMENT PLAN ( FY 2022-23) OF (400kV Schemes)
(Amount Rs. in Crs)
Base Year 2022-23
Sl No. | Project Code | Project Title |  |  |  | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
|  |  | SAP ( as on 31.03.2018) | Budget (as on 05.03.2018) | final as on 31.03.2018 |  |  | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
1 | To be Applied | Yadradri Power Evacuation | - |  |  | Jan'2020 | Mar' 2024 | 1887.67 | 56.07 | 209.7 |  | 200.91 | 2354.35 | [7 empty] | 335.8 |  |  |  | 335.8 |  |  |  | 1467.55
2 | Applied & approval is pending | KTPP System Improvement Scheme |  |  |  | Jan'2020 | Mar' 2024 | 372.58 | 11.07 | 30.92 |  | 39.66 | 454.23 | [7 empty] | 29.62 |  |  |  | 29.62 |  |  |  | 304.12
| Applied & approval is pending | Reactor Scheme -III |  |  |  | Jan'2020 | May'2022 | 201.44 | 5.98 | 20.92 |  | 21.44 | 249.78 | [7 empty] | 25 |  |  |  | 25 |  |  |  | 180 |  |  | 100
[13 empty] | 2808.58 | [7 empty] | 390.42 |  |  |  | 390.42 |  |  |  | 1771.67
'file:///tmp/in/input.xls'#$2022.23
Chief Engineer/400kV

## 2023.24
Format 1.1(d) ABSTRACT OF INVESTMENT PLAN ( FY 2023-24) OF (400kV Schemes)
(Amount Rs. in Crs)
Base Year 2023-24
Sl No. | Project Code | Project Title |  |  | final as on 31.03.2018 | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
|  |  | SAP ( as on 31.03.2018) | Budget (as on 05.03.2018) |  |  |  | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
1 | To be Applied | Yadradri Power Evacuation | - |  |  | Jan'2020 | Mar' 2024 | 1887.67 | 56.07 | 209.7 |  | 200.91 | 2354.35 | [7 empty] | 210 |  |  |  | 210 |  |  |  | 1677.55 |  |  | 100
2 | Applied & approval is pending | KTPP System Improvement Scheme |  |  |  | Jan'2020 | Mar' 2024 | 372.58 | 11.07 | 30.92 |  | 39.66 | 454.23 | [7 empty] | 8 |  |  |  | 8 |  |  |  | 312.12 |  |  | 100
[13 empty] | 2808.58 | [7 empty] | 218 |  |  |  | 218 |  |  |  | 1989.67
Chief Engineer/400kV