## ANNEXURE-I(A)
Annexure-I(A) DIRECTIVE - 2 THE ACTION PLAN FOR THE NEXT FOUR YEARS FOR REDUCTION OF TECHNICAL LOSSES IS AS GIVEN UNDER
S.No. | Description | Year
|  | 2010-11 | 2011-12 | 2012-13 | 2013-14
1 | No. of new sub-stations proposed for reducing length of 11KV line thereby reducing 11KV line loss | 166 | 140 | 120 | 110
2 | No. of PTRs proposed for augmentation to reduce over loading of existing PTRs | 104 | 90 | 80 | 70
3 | No. of additional PTRs proposed to reduce over loading of existing PTRs and Sub-Stations | 79 | 60 | 50 | 40
4 | Replacement of Electromechanical meters with high accuracy meters | 300000 | 300000 | 300000 | 300000
5 | Replacement out dated age old conductor (line)
| 33 KV | 40 km | 40 km | 35 km | 35 km
| 11 KV | 125 km | 125 km | 125 km | 125 km
| LT | 500 km | 500 km | 500 km | 500 km
6 | Replacement of aged DTRs which are making high technical loss and served for more than 20 continuous years
| 1Ø | 1050 | 1050 | 1050 | 1050
| 3Ø | 1500 | 1500 | 1500 | 1500
7 | Bifurcation of Lines/Feeders
| a) 33 KV Lines/Feeders with >250A | 12 | 12 | 12 | 12
| b) 11 KV Lines/Feeders with > 100A | 45 | 45 | 45 | 45
| c) No. of LT circuits having more than 0.5 km length and to be bifurcated | 3234 | 3234 | 3234 | 3234
8 | Additional 11 KV 2 MVAR capacitor banks proposed for erection & commissioning for reactive power compensation | 108 | 50 | 30 | 15
9 | Additional DTRs proposed for erection under improvement to reduce over loading on existing DTRs | 5000 | 5000 | 5000 | 5000
10 | Additional DTRs proposed under HVDS project to avoid the LT line in the network
| 3Ø - 25 KVA | 2220 | 2220 | 2220 | 2220
| 3Ø - 16 KVA | 2050 | 2050 | 2050 | 2050